## Slide 1: Long Baseline Neutrino Committee December 2018 CERN, Geneva Switzerland
CLOSEOUT Report
December 9, 2018

## Slide 2: Ackowledgements
The LBNC recognizes the effort put into the preparation of the presentations and material by the DUNE Collaboration, and the frank responses to questions and queries.
The committee also appreciated the hospitality by the CERN Neutrino Platform organization and leadership, CERN itself, and Fermilab for their hospitality

## Slide 3: Charge
The LBNC will hear about the progress in a number of areas including the general progress of each of DUNE, LBNF, and ProtoDUNE. There will be in depth presentations covering the development of the Dual Phase option, including a look forward to 2019 with ProtoDUNE DP, and preparations for a TDR. We will also hear about TDR and CDR preparations in a few key areas.
The LBNC will prepare a written report, which will include descriptions of the status of each of these items. Inter alia, this report will inform a presentation of the overall preparations of DUNE, which may be requested for the DOE LBNF-DUNE IPR in early January, 2019.
An abbreviated verbal closeout will be presented on Sunday afternoon.
Our goal will be to leave CERN with an advanced draft of the full report in hand.

## Slide 4: Approach
In order to facilitate achieving this, we have made tentative assignments for the attending LBNC members.
Note that both Angela Fava, our Scientific Secretary and David MacFarlane, our outgoing chair are expected to be active participants.
The assignments are shown below;
  the name in Bold Face is requested to take the lead in writing.
  We are looking for approximately 0.5 – 0.75 pages per item except for the Dual Phase which has several sub sections, so should be longer.
  We will discuss the expectations in the Executive session at the beginning of the meeting, but if anyone feels that the task is not acceptable, please contact mont@jlab.org.

## Slide 5: Assignments
DUNE Overall Status 50 mins (35+15) Stefan Soldner Rembold -- Exec Summary: Montgomery
LBNF Status 45 mins (30+10) Chris Mossey
LBNF Status: Laxdal, MacFarlane
ProtoDUNE-SP Report (and lessons-learned) 45 min (35+10) Gina Rameika
PD SP Status: Charlton, Fava, Montgomery
Dual-Phase
  Results from the 1x1x3 m^3 Demonstrator 30 mins (20+10) Sebastien Murphy
  LEM Production & Testing 30 mins (20+10) Edoardo Mazzucato
  CRP Assembly & Cold-Box Testing 30 mins (20+10) Dominique Duchesneau
  ProtoDUNE-DP Installation 30 mins (20+10) Filippo Resnati
  DUNE-DP IDR & TDR Status 30 mins (20+10) Dario Autiero
DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Mondal

## Slide 6: Assignments
TDR/CDR Preparation Status
  Overall View/Plan/Status 35 mins (25+10) Tim Bolton (Remote)
TDR Overall Status: Charlton, Montgomery
  Physics TDR Status/Preview 35 mins (25+10) Jon Urheim
Physics TDR Status: Heinemann, Huber
  Computing Organization Status 35 mins (25+10) Heidi Schellman
Computing Plans: Boehnlein, Heinemann
  APA TDR Status/Preview 35 mins (25+10) Christos Touramanis
APA TDR Status: Monroe, MacFarlane,
Near Detector CDR Status/Preview 35 mins (25+10) Alan Bross
Near Detector Status Mondal, Huber, Fava

## Slide 7
  LBNF is making sustained progress with major advances at the far site:
  Reliability projects have commenced following the work safety stoppage
  There is now 100M$ earmarked for pre-excavation work with no road blocks foreseen
  Critical Pre-excavation construction packages (16/17) have been awarded
  Significant progress on the design of the Far Site excavation phase (60% design complete in November 2018 with interface workshops planned at CERN in early 2019).
  Nevertheless some LBNF milestones have moved since August due to vendor feedback in the far site and a lack of definition in the near site.
  DUNE appears to be well engaged and involved in interface management and review of the Far Site excavation design. We note that the range of design options that can be exercised will continue to narrow at the 90% (Feb 2019) and 100% (May 2019) design review stages
  It will be important to maintain a centralized document server and document approval protocol to support this activity.
LBNF Status: Laxdal, MacFarlane
Notes: - LBNC --> LBNF milestone slid
- more positive words on the successful bidding

## Slide 8: LBNF Status: Laxdal, MacFarlane
  The limitations on the near site funding and uncertainties on the Near Detector (ND) size impacts the Near Site Conventional Facility (NSCF) definition and the NSCF timeline.
  Progress was presented towards a ND concept following adoption by the DUNE EB of the ND task force recommendations and the formation of a ND consortium
  ND options may lead to a more costly NSCF.
  LBNF needs to understand the upper limit on Near Site facility costs by Jan 2019 and shaft and cavern size for preliminary design work as early as July 2019
  A clear science case for the various ND configurations needs to be concluded with some urgency in order to support the LBNF strategy to baseline costs in 2019 (while scheduling contracts in 2022).
  The Beamline work continues to evolve . While progress is being made in identifying international partners, a significant portion of the scope still needs to be assigned. Sufficient resources need to be mobilized to provide CD-2 costing in 2019.
  Recruitment of key personnel is ramping up, including a logistics manager for the Far Site. A comparison between resource actuals and resource planning from the Resource Loaded Schedule would be useful in future meetings.
Notes: - Take "good" out of first bullet
- Last bullet: explicitly say that they need to show the comparison (we got a verbal answer only)
- Third bullet: explicit "near site". Also, the cost of the beamline is clear, it's just the decision on an option that is still needed.

## Slide 9
  LBNF needs to extract as much experience as possible from the p-Dune experience. An operating model would be useful to help clarify LBNF and Dune start-up and future operational needs, e.g., requirements or expectations for the time needed to reach sufficient purity - does the realization of moisture leaching from the protoDUNE detector modify the equipment required for DUNE operation.
  Recommendations -
LBNF Status: Laxdal, MacFarlane
Notes: operational --> operation (reword it and make it less ambitious)
Remove "recommendation"

## Slide 10: PD SP Status: Charlton, Fava, Montgomery, Liu
The LBNC offers its warm congratulations to ProtoDUNE on the construction, filling, operation and successful data-taking of PD SP
The rapid attainment of a 500 V/cm drift field, a 6(+) ms e- lifetime, and noise of 500-600 ENC are highly impressive and very promising for DUNE
We look forward to seeing more results from analysis of beam and CR data from analyses underway or starting – crucial to support the TDRs
We would like to see progress on photon detector data/performance
Prompt documentation on lessons learnt is important throughout, including root cause analyses
Operation of PD SP during 2019 has the strong support of the LBNC
The push to make rapidly a detailed prioritization and scheduling of goals for 2019 operations is strongly supported, informed by needs for the DUNE TDR
The LBNC emphasizes the importance of establishing and studying the operational baseline and its long-term stability, for the TDR
We see the interest of addition of Xe at the end of the run, provided the photon detector performance is sufficient.

## Slide 11: DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Liu, Mondal, Monroe Results from the 1x1x3 m^3 Demonstrator
The 1x1x3 took 400K cosmics in the period July-November 2017 and demonstrated many key technical and performance measures for a Liquid Argon Dual Phase TPC, for example 500v/cm drift field, electron lifetime ~4msec, equal charge sharing between anode collection planes, stable liquid argon level during recirculation, correlation between scintillation light and collected charge. Stable operating conditions required a compromise between the voltages across the induction plane, the LEM and the absolute grid HV; LEMs were operated with electric fields in the range from 23 and 31 kV/cm, most of the data were taken at 28kV/cm corresponding to an effective gain in the range of ~3. Global trips occurred after operating the LEMs for ~ 1hr and it was not possible to bring the LEMs to high fields – prompting a change in the LEM design to incorporate a larger guard ring. A number of additional design changes were implemented based on the results of the demonstrator testing. These results have recently been published in JINST.
Recommendations
None

## Slide 12: DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Liu, Mondal, Monroe LEM Production & Testing
Results were presented for the 74 LEMs produced and tested for CRP1 & CRP2
LEMs were tested up to 3.5 kV (35kV/cm) in Ar at 3.3 bar and have <1 spark/20 minutes
For an optimum induction voltage of 1 kV, stable operation in the cold box was not achieved for HV configurations which give an effective gain ~20; the source of instability is not fully understood. Stable configurations can be achieved by decreasing the induction field between the anode and the top of the LEM and can achieve an effective gain from 24-31
Dark spots were seen in the corner of LEMs in CRP1 following removal from cold box; this was attributed to uncontrolled sparking due to a lack of protection in the power supply.
Following rework, two CRPs are operational though with the limitation above on the induction field and corresponding LEM HV (bottom HV on the LEM)
Further understanding/improvement of LEM design is being addressed; the committee is concerned at the impact of sparking on LEM performance and viability for DUNE-DP
Recommendations
Develop an R&D plan to improve the LEM design to the specification needed for DUNE-DP (stability, gain, reliability, spark rate, operational lifetime)

## Slide 13: DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Liu, Mondal, Monroe CRP Assembly & Cold-Box Testing
The cold-box has proven to be an effective tool for CRP testing and substantially enhances the capabilities of the CERN NP infrastructure; the planarity of CRP distance to liquid level in the CB is stable to within 1.75mm and the relative distance between the liquid and the CRP is stable to 0.25mm.
4 CRPs are being prepared for installation in ProtoDUNE-DP, two of these will be dummies (i.e. with no LEMs or anodes); construction time was approximately 1 CRP/month; CRP4 will be delivered to CERN at the end of January
Following initial tests: modifications to grid tension, HV connection and HV distribution were implemented; for CRP1, 4 LEMs were removed cleaned and re-installed (see above); for CRP2, 1 LEM was replaced by a spare (insufficient time to clean)
Recommendations
Feed back lessons learned from assembly defects requiring rework into CRP construction and QA/QC plan (e.g. residual flux on wires, grid wire tension at cold, HV shorts on grid)

## Slide 14: DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Liu, Mondal, Monroe ProtoDUNE-DP Installation
The external cryogenic system has been completed following the conclusion of PD-SP operation with beam.
Proximity cryogenic systems were installed in SEP2018.
Installation of 4 CRPS in the DP cryostat is in progress, two of these CRPS will be dummies
A problem appeared during the insertion of CRP3 in the cryostat where 3 wires broke in the process and 7 more in the following days
The installation schedule presently shows closing of the TCO by week 14 of 2019, with filling and purification completing by week 28, 2019 (22nd July)
No cosmic data-taking plan was presented
Lessons learned from ProtoDUNE-SP operations will be of use in ProtoDUNE-DP operations
Recommendations
Develop a plan for incorporation of commissioning measurements, and if possible cosmic ray data, from ProtoDUNE-DP which will inform the DUNE-DP TDR on key performance metrics

## Slide 15: DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Liu, Mondal, Monroe DUNE-DP IDR & TDR Status
CISC scope for DP will be identical to SP except for the inclusion of additional instrumentation to monitor temperatures and pressures in the gas phase region of the cryostat. Mention was also made regarding the performance of extended computational fluid dynamics (CFD) simulations of the LAr volume.
The ProtoDUNE design is used as the basis for the TDR, and is described in detail in the IDR
The last chapter of the DUNE-DP TDR, DP-CRP, is to be submitted 28/6/19 – this is before ProtoDUNE-DP is planned to take any cosmic data
It was not clear when there would be reviewable design for the 600kV supply and its use in the DUNE-DP cathode for a 12m drift.

## Slide 16: DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Liu, Mondal, Monroe DUNE-DP IDR & TDR Status
Recommendations
Develop a plan whereby performance data from operation of cold box and ProtoDUNE-DP/SP tests can be incorporated into the DUNE-DP TDR
Quantify the tradeoff between LEM gain and physics performance and scope
Develop a combined simulation and performance measurement plan to demonstrate the validity of the extrapolation of ProtoDUNE-DP performance to a 12m drift distance
A number of optimizations are planned to the design of the field cage, cathode and ground in extending the ProtoDUNE-DP designs to the full 12 m detector required for DUNE-DP. The DUNE-DP TDR should present the plan by which these changes to the design are qualified.

## Slide 17: TDR Overall Status: Charlton, Montgomery
The general organisation and planning of the TDRs looks good, including the provision to the LBNC of “2nd drafts” early, mixed across TDR volumes
The committee appreciates the willingness of the collaboration to share these drafts to facilitate timely review
The LBNC expects to need multiple, detailed, iterations on the design and performance as outlined in the individual chapters
It is important that an overview of each volume, including the big picture design and relation to physics requirements, is available at the start of the review process – this should contain the drivers of the design described in the rest of the volume, not simply summarise that design
Recommendations
The LBNC appreciates the production of the “DUNE Far Detector (Single Phase) Design Choices and Physics Connections” document, but asks to see the physics connections further developed in the TDR
Recommendations

## Slide 18: Physics TDR Status: Heinemann, Huber
The committee is impressed by the advanced outline of the physics TDR, and encouraged that much material has been collected in a first draft.
The structure and scope of the document seems adequate but no scientific results were presented
The tools & methods chapter appears to be on good track to provide a realistic (albeit maybe pessimistic) basis for the physics analysis chapters
The committee looks forward to a concise summary (planned in the Exec. Summary) of which physics analyses place the most stringent requirements on which aspects of the detector performance
The strategy to use full simulation and reconstruction for the most important science drivers and parametric simulation for others is sensible
In particular in the oscillation section, adequate attention appears to be paid to systematic uncertainties (including the use of different event generators)
Recommendations -
The ~250 pages envisaged should not be exceeded. Details should be outsourced into separate documents and/or appendices if needed

## Slide 19: Computing Plans: Boehnlein, Heinemann
We congratulate the Computing Operations team on the success of ProtoDune physics data collection and reconstruction as well as MC11
All 7M ‘good beam data/triggers’ were processed within 3 calendar weeks.
The reconstruction is demonstrably working and 2nd gen algorithms are being developed, benefiting from the LArSoft shared algorithm base.
Distributed resources are being used extensively
ProtoDune Computing “Lessons Learned” documents are being written
The ProtoDune experience gives confidence that the scale of Computing for DUNE is tractable
The Computing Consortium is in the process of being formed
A logical set of organizing principles is being developed.
These include a WLCG-like model & working within the broader HEP computing community
A new management team is being assembled; this is an essential next step. A positive development is the appointment of a new technical lead from FNAL.

## Slide 20: Computing Plans: Boehnlein, Heinemann
Recommendations
For the computing strategy summary in the TDR we recommend a tight focus, stressing the impact of the ProtoDune experience, a short description of the consortium model and long lead-time items, such as SURF WAN.

## Slide 21: APA TDR Status: Monroe, MacFarlane
The APA TDR is well-informed by the ProtoDUNE programme.
The APA design is mature. A small number of changes are proposed with respect to the design used in ProtoDUNE.
Full APA production is planned to start in 2020 in the UK and 2021 in 3 sites in the US.
We encourage the collaboration to systematically examine the PSL vs. Daresbury APAs for differences in production or performance, in time to inform the QA/QC plan for the TDR.
The timescale for testing the three final-version APAs of mid-2020 is approximately 6 months after full APA production launch in the UK is planned. We encourage the collaboration to consider this ordering.
The statement was made that the studies of ProtoDUNE-SP that feed into the TDR will be decided in Jan. 2019. This seems late given the goal of TDR 2nd draft delivery to the LBNC in Dec. 2018.
The TDR should address the issue of testing longevity vs. further optimization of detector components. We emphasize the importance of system-level longevity testing for the cold electronics.

## Slide 22: APA TDR Status: Monroe, MacFarlane
Recommendations -
The requirements that connect the physics drivers to the technical specifications of the APAs should be concisely, quantitatively stated in the TDR. The trade-offs between the low vs. high performance range of technical specifications should be articulated clearly.
The criteria, process and time line for down-selection decisions should be specified in the cases where multiple technology options go forward in the TDR.
The TDR should specify how sites will be qualified to mitigate differences in production site performance.

## Slide 23: Near Detector Status Mondal, Huber, Fava
Proposed Near Detector suite consists of a LArTPC , a Multi-Purpose Detector (MPD) consisting of a HPgTPC, an ECAL and 3D Scintillator Tracker (3DST) in a magnet.
The DUNE –PRISM concept envisage LArTPC and probably MPD to be mobile and make measurements at several off-axis positions along with on-axis measurements. will help to simultaneously constrain neutrino flux, cross sections and energy smearing.
Detailed simulation effort is ongoing to understand the systematics reach of this detector concept.
The concept appears to be interesting and LBNC looks forward for a full review of the design and its capabilities and its cost in the summer of 2019.
There are several milestones coming up that will need a clear and approved time line for Near Detector.
Recommendations - none

## Slide 24: Exec Summary: Montgomery
DUNE and LBNF have made good progress on a number of fronts.
There are numerous technical issues that will need to be decided on a weekly basis. The EB needs to be aware and to weigh in on the important ones.
The DUNE approach to detector requirements and their justification needs further refinement to tighten connections with the physics performance.
DUNE should be complimented on the Computing Consortium developments.
Congratulations to the Collaboration for the success of ProtoDUNE-SP. This leads to the need for a plan for 2019 operations.
The progress with the DP has been slower than planned.
  Several technical challenges have been encountered.
  The operation of NP02 will occur in the second half of 2019; we encourage the continued strong support of CERN for the Dual Phase effort.
  A program of R&D at the level of the LEM is needed and planned, in parallel with the performance assessment in ProtoDUNE-DP
The Near Detector concept is being developed and should be reviewed in mid 2019.
Recommendations -