## Slide 1
Peter Wilson – SBN Program Coordinator
SBN Oversight Board
8 March 2019
SBN Program Status

## Slide 2: Outline
ICARUS technical progress
SBND technical progress
December Director’s review
DOE Funding
Transition to Operations Planning

## Slide 3: Far Detector - ICARUS
Exterior LAr Filters
Cryogenic Dewars
Cold Vessels (TPCs and PMTs inside)
Proximity Cryogenics
Side CRT
Top CRT and Overburden
(not shown)
Not shown in alcoves (mezzanine and pit):
DAQ racks
Controls racks
Bottom CRT
TPC Electronics
Two 33 ton cranes

## Slide 4: ICARUS Installation Progress
Detector installation work continues on schedule:
  Installation of feedthrough crosses completed
  Feedthrough flanges installed
  First checkout of feedthroughs completed finishing corrections on specific flanges
  North wall CRT modules (repurposed MINOS modules) installed
  Start installation of electronics and power supplies in April
  On track to be ready for LAr fill in summer
TPC 1 Complete
Vessel 2 Ready
Preparing a PMT fiber flange
Flange installation and vertical slice test
Testing TPC flange connectivity
North Wall CRT

## Slide 5: ICARUS Installation Progress
Cryogenics installation work on schedule:
  Proximity cryogenics components delivered from CERN in early December (ten shipping containers)
  Installation started by Demaco on Jan 28
  All 14 valve boxes installed within two weeks
  Transfer line installation progressing well
  Fermilab continues installation of items such as vent lines in parallel
  Controls programming progressing well
  Controls wiring to start shortly
  3 transfer lines damaged in transport from CERN
    Very fast response by CERN and Demaco
    New lines being constructed at Demaco – delivered to FNAL by end of May
    Installation order adjusted to accommodate
Mitigating delays to maintain LAr fill date in July
always safety first!
TPC 1 Complete
Vessel 2 Ready
Rigging valve boxes

## Slide 6: ICARUS Installation Progress
Cryogenics installation work on schedule:
  Proximity cryogenics components delivered from CERN in early December (ten shipping containers)
  Installation started by Demaco on Jan 28
  All 14 valve boxes installed within two weeks
  Transfer line installation progressing well
  Fermilab continues installation of items such as vent lines in parallel
  Controls programming progressing well
  Controls wiring to start shortly
  3 transfer lines damaged in transport from CERN
    Very fast response by CERN and Demaco
    New lines being constructed at Demaco – delivered to FNAL by end of May
    Installation order adjusted to accommodate
Mitigating delays to maintain LAr fill date in July
always safety first!
TPC 1 Complete
Vessel 2 Ready
Installing Vent Line (FNAL Scope)
Current Status

## Slide 7: ICARUS Progress
TPC electronics production in final phase (INFN)
  On track to complete delivery to FNAL by May
Cosmic Ray Tagger (CRT)
  Top CRT panel production starting in Frascati
  Side CRT readout: final design review for SiPM board and cabling on Jan 7
    Responding to recommendations now
  North side install between cryo plant and vessel
    Mounts installed
    Modules cut and wrapped
    Modules installed at end of January
Top CRT Production in Frascati
Side CRT SiPM Board and module cutting @ Wideband lab

## Slide 8: Installation work stop Mar 5-6
Installation work on top the warm vessel was stopped for one day this week in response to three recent injuries:
  Student tripped on top of the vessel (December) – bruises
  Technician (Demaco) had pipe sleeve strike hand (February) – stitches
  Technician (INFN) tripped on top of the vessel (March) – stitches
Paused work: address trip hazards and work rules
  Removed materials and tools
  Advanced the installation of additional decking by several weeks
  Final decking to be installed in stages following completion of work on crosses
  Added safety cones and caution tape to warn of trip hazards
  Updated requirements on usage of hard hats
Held two safety briefings – at stop and restart of work
  Included all collaborators and technical staff currently engaged in the work
Reinforcing daily work planning/safety meetings and communication on plans between the collaboration and Fermilab technical team
TPC 1 Complete
Vessel 2 Ready

## Slide 9: Far Detector Commissioning – cryogenics prep.
Cold vessel engineering note and validation
  Completed verification of CERN FEA by Fermilab analysis engineer
  Engineering note completed by provided to safety committee
  SBN Cryo Working Group initiated: preparing validation and fill plan
Cryogenics system engineering notes completed and reviewed
  Need review of installed system to complete operations clerarance
LAr contract:
  Bid package completed and sent to vendors on Feb 11
  Received two bids on Feb 28; first look
    Both meet schedule requirement of 6 deliveries/week
    Both meet meet or beat technical specifications on contaminants
  Technical evaluation in progress
  On track for LAr fill milestone.
  Thanks to procurement for excellent response time

## Slide 10: ICARUS Milestones to I-1 Ready to Fill
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Vessels rigged into building | P. Wilson | 16-Aug-2018 |  |  | 16-Aug-2018
Manholes welded and vacuum test successful | C. Montanari | 10-Oct-2018 |  |  | 11-Oct-2018
Warm Vessel roof complete | C. James | 15-Nov-2018 |  |  | 31-Oct-2018
Cryo Platform complete | C. James | 15-Dec-2018 |  |  | 04-Oct-2018
Proximity cryogenics installation begins | B. Norris | 15-Jan-2019 |  |  | 28-Jan-2019
DBB & flanges installation complete and tested | A. Fava | 15-Feb-2019 | 1-Mar-2019 | b | 
Cold proximity cryogenics installation complete | B. Norris | 15-Apr-2019 | 25-Apr-2019 | c | 
1st T300 readout installation complete | A. Fava | 15-Mar-2019 | 8-Apr-2019 | d | 
All detector readout installed | A. Fava | 1-May-2019 | 31-May-2019 | e | 
Begin vacuum pumping | C. Montanari | 15-Jul-2019 | 15-May-2019 |  | 
Cryogenic operation approved | B. Norris | 15-Jul-2019 | 28-Jun-2019 |  | 
I1: ICARUS detectors ready to fill with LAr | P. Wilson | 30-May-2019 | 11-Jul-2019 | f | 
Forecast update awaiting details on replacement transfer lines

## Slide 11: Near Detector - SBND
Cryogenic Dewars
TPC
Proximity Cryogenics
Side CRT
Top CRT and Overburden
Readout racks
20 ton crane
Top CRT
Cryostat

## Slide 12: SBND TPC Progress
UK: Manchester completed wiring the 2nd APA at Daresbury lab. Shipped on Feb 25. Arrival at Fermilab in March
US: field cage and 2nd anode plane received at Fermilab on Mar 1
Three (of 4) APAs now in the Dzero assembly facility
  Two in clean tent, one on the alignment fixture. Plan to pair them in late March
  One stored outside tent
TPC assembly and transport frame (atf) in fabrication – delivery to FANL in April
1st UK APA on the alignment fixture
Field cage panels at Yale
Assembly and Transport Frame
1st Yale APA in clean tent

## Slide 13: SBND TPC Electronics Progress
Cold electronics (BNL):
  Design very similar to ProtoDUNE (eg same FE ASIC)
  Use cold qualified commercial off the shelf ADC
Warm backend (Columbia – Nevis)
  Update of MicroBooNE design
Addressed lessons from ProtoDUNE
  FE ASIC “ledge effect” – large charge depositions cause a dead period of several hundred microsecs
  Mitigated by modifying layout of FE board to include 1-2GOhm resistor and operation with higher baseline setting
Successful Production Readiness Review Nov 29
Both cold and warm electronics on track for completion milestones this spring/summer
Ledge effect @protoDUNE
amplitude
Time tic

## Slide 14: SBND Photo Detection Progress
Full PMT system under test in the Coherent CAPTAIN-Mills Detector (CCM) at Los Alamos
  Ready to install in fall 2019
ARAPUCA system
  tested in argon
  feedthroughs ordered
  Production review completed
  Ready to install in summer 2019
Light guide bars
  Production review completed
  Ready to install in fall 2019
CCM preparing to test PMTs at LANL
ARAPUCA prototypes

## Slide 15: SBND CRT/Laser
Production
Bottom and side CRT modules complete
Top CRT modules and laser system production @Bern on track.
CRT Test Setup
Running successfully with 24 modules
Preliminary measurement of BNB bunch shape after BNB bunch rotation turned on on Jan 14 (DocDB #11107).
Upcoming Installation
CRT test setup to conclude data taking in March, to make space for Demaco proximity cryogenics installation
Discovered interference between six bottom CRT modules and final cryostat design.
  Discussion with Bern on how to solve.

## Slide 16: SBND Cryostat
Outer steel structure
  Material delivered to CERN in February
  Preassembly about to start at CERN
  On track for installation at FNAL in May/June
Membrane cryostat
  Design contract being placed by CERN
  Design to start in March
  Material delivery to FNAL in fall for installation late 2019
SBND Cryostat Model

## Slide 17: SBND Cryogenics
Cryogenics Platform
  Installation started this week – complete by early April
Proximity cryogenics
  Equipment delivered in December from CERN
  Installation starting in April when Demaco is done with installation in FD building
  Complete by end of May
Cryo platform design
Crated Valve boxes in ND Building
Preparing for platform install

## Slide 18: Near Detector Personnel Changes
Anne Schukraft has taken over as Technical Coordinator
  Brian Rebel has moved to a joint faculty position at U. Wisconsin / staff position at Fermilab with primary focus on DUNE
  Anne has extensive experience from MicroBooNE and SBN FD CRT
Roberto Acciarri fills the new position of Installation Coordinator
  Roberto has most recently been working on ProtoDUNE-SP based at CERN

## Slide 19: SBND Milestones to S-1 SBND ready to move
Intermediate Milestone | Owner | Baseline Date | Forecast Date (Schedule) |  | Actual Date
First set of APAs shipped to Fermilab | K. Mavrokoridis | 24-Sept 2018 |  | a | 25-Feb-2019
PO for COTS ADCs placed | H. Chen | 10-Oct-2018 |  |  | 30-Oct-2018
All TPC Components at Fermilab | K. Mavrokoridis | 1-Mar-2019 | 19-Mar-2019 |  | 
Complete atf assembly at DAB | J. Zennamo | 1-May-2019 | 18-Apr-2019 | b | 
50% of motherboards delivered to Fermilab | H. Chen | 15-May-2019 | 19-Apr-2019 |  | 
APAs and CPAs installed in atf | J. Zennamo | 15-Jun-2019 | 5-Jun-2019 |  | 
Field cage assembly complete | J. Zennamo | 15-Jul-2019 | 15-Jul-2019 |  | 
Cold electronics installed and tested | H. Chen | 23-Aug-2019 | 20-Aug-2019 |  | 
S1: TPC ready to move to SBN ND | A. Schukraft | 30-Aug-2019 | 23-Aug-2019 |  | 
US APA group decided to ship both their APAs and field cage in one shipment, delaying shipment of the first APA from September to early February. This should have little to no impact on completion the final assembly
The atf biding process has been delayed due to holidays by about 8 days. This delay propagates through to forecast dates of subsequent milestones. We are working on absorbing this delay in the assembly process.
Forecast update awaiting placement of atf contract

## Slide 20: SBN Director’s Review – Dec 2018
Director’s Review for SBN was held held Dec 17-19 2018
The final review report available on the review website:
  Review Final Report
The review committee was pleased with the progress made since the June 2018 review which focused primarily on schedule. The committee congratulates the team for the great progress in getting the far detector modules installed. Progress on the near detector components is also quite impressive.
Total of 16 recommendations (had 34 from June review)
  Expect all but one to be addressed by end of March
  Common theme in comments about need for better documentation: Steve B and Peter W decided to create our own 17th recommendation to address this
Expect next review in December 2019
  Focus on SBND Installation

## Slide 21: DOE Funding
In Spring 2018 we requested an additional $3,900k of funding from DOE to keep the program on track
  Funds needed in the 2019 fiscal year to prevent significant delays for both far and near detectors
  Repeated request at the time of the December 2018 Director’s Review
On January 29, Steve Brice, Tim Meyer and Peter Wilson visited DOE to brief them on financial status of SBN
After the briefing DOE has provided the requested additional funds
This allows critical procurements to proceed unimpeded, for example:
  LAr contract for the far detector
  contribution to near detector cryostat design contract
  near detector cold electronics

## Slide 22: Transition to Operation Planning
At January DOE briefing we also presented a plan for transition to operations
Address commissioning and operations plans for both detectors and associated support (e.g. cryogenics, online computing, data storage)
Transition to Operations Team created
  Angela Aparicio – Neutrino Division (ND) Safety Officer
  Steve Brice – ND Representative
  Angela Fava – Far Detector Deputy Technical Coordinator and Deputy Commissioning Coordinator
  Cat James – Deputy Program Coordinator
  Claudio Montanari – Far Detector Technical Coordinator and Commissioning Coordinator
  Barry Norris – SBN Program Engineer and Head of ND Technical Support Dept
  Dave Schmitz – SBND collaboration representative
  Michelle Stancari – Near Detector Commissioning Coordinator
  Peter Wilson – Program Coordinator, chair of TOT
  Bob Wilson – ICARUS collaboration representative
  Wes Ketchum - Scientific Computing Division representative
Kick-off meeting in February
  Presentations on the organization of experiment operations at Fermilab including support model and example of the MicroBooNE operations organization
Regular meetings to start in March to define organizations and prepare Experiment Operations Plan
Operations Readiness Review organized by Fermilab in fall 2019 to coincide with start of neutrino beam to far detector. Expect 2nd review in 2020 when near detector starts

## Slide 23: Backup

## Slide 24: Notes on milestones to I-1
Arrival of subcontractor delayed by CERN to ensure transport of equipment was completed in advance with schedule contingency
Delivery of last cross and PMT flanges from INFN/CERN completed by end of January
Start delayed by 2 weeks, see a) above. Parts to replace those damaged in shipping are expected to arrive in May, however these parts are not anticipated to impose any delay on installation of other components
Added contingency in materials transport
Added contingency in materials transport
Baseline for I-1 set in March 2018 when delays in delivery of cold shields has not been completely realized. Detailed intermediate milestones were defined and baselined in July 2018

## Slide 25: ICARUS Milestones to I-2 Detector Filled
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Cold shield cooldown complete | C. Montanari | 7-Aug-2019 | 15-Jul-2019 |  | 
Vessels filled with LAr, ready for HV | M. Geynisman | 30-Sept-2019 | 10-Sept-2019 |  | 
Drift HV operational | F. Garcia | 15-Oct-2019 | 10-Sept-2019 |  | 
PMTs operational | G. Raselli | 30-Oct-2019 | 15-Oct-2019 |  | 
Cryogenics commissioning complete | M. Geynisman | 30-Nov-2019 | 22-Oct-2019 |  | 
Cosmic tracks are observed in the TPC | A. Fava | 30-Nov-2019 | 22-Oct-2019 |  | 
I2: detector is filled with liquid argon and ready for physics commissioning (LAr purity adequate for physics has been achieved) | P. Wilson | 30-Nov-2019 | 01-Nov-2019 |  | 

## Slide 26: ICARUS Milestones to I-3a ready for physics data – CRT operational
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Complete installation of Side CRT modules (a) | A. Schukraft | 31-July-2019 | 28-Jun-2019 |  | 
Top CRT panels delivered to Fermilab | U. Kose | 30-Sept-2019 | 31-Jul-2019 |  | 
Slow controls operational for all detector systems | K. Biery | 31-Oct-2019 | 30-Sept-2019 |  | 
DAQ operational with >5Hz output | K. Biery | 31-Oct-2019 | 30-Sept-2019 |  | 
Detector system timing synchronized with beam | K. Biery | 30-Nov-2019 | 31-Oct-2019 |  | 
Trigger system operational | A. Guglielmi | 31-Dec-2019 | 30-Nov-2019 |  | 
Top CRT panels are installed and ORC’ed | U. Kose/A. Fava | 31-Jan-2020 | 5-Dec-2019 |  | 
I3a: ICARUS detectors are ready for physics data – CRT is operational | P. Wilson | 31-Jan-2020 | 17-Dec-2019 |  | 
Notes:
This milestone is currently at T4 in the schedule file. Will promote to T3 at the next schedule statusing

## Slide 27: ICARUS Milestones to I-3b ready for physics data – shielding in place
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Shielding blocks in place | C. James | 28-Feb-2020 | 6-Feb-2020 |  | 
I3b: ICARUS detectors are ready for physics data – Shielding in place | P. Wilson | 28-Feb-2020 | 18-Feb-2020 |  | 

## Slide 28: SBND Milestones to S-2 Ready to Fill
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
GTT Design Study Begins | M. Nessi | 1-Feb-2019 | 2-Jan-2019 |  | 
Delivery of warm box steel | M. Nessi | 15-Jun-2019 | 25-Apr-2019 |  | 
Warm vessel installation complete | M. Nessi | 15-Jul-2019 | 29-Jul-2019 |  | 
TPC Transport to ND building complete | J. Zennamo | 15-Sept-2019 | 3-Sept-2019 |  | 
Cryostat material arrives at Fermilab | M. Nessi | 1-Oct-2019 | 17-Sept-2019 |  | 
Cryostat top plug is ready to attach to atf | M. Nessi | 1-Nov-2019 | 15-Oct-2019 |  | 
Membrane Cryostat Completed | M. Kim | 1-Mar-2020 | 22-Jan-2020 |  | 
Plug welded to cryostat | M. Kim, J. Zennamo | 15-Apr-2020 | 18-Mar-2020 |  | 
Cryogenic operation approved | M. Geynisman | 1-Jul-2020 | 11-Jun-2020 |  | 
S2: SBND detector is ready to fill with liquid Argon | A. Schukraft | 15-Jul-2020 | 11-Jun-2020 |  | 
Comment: We expect intermediate milestone forecast dates to change in the near future as the installation sequence is undergoing some changes. Note, that this will not affect the forecast date of key milestone S2.
As presented at Jan 2019 PMG.

## Slide 29: SBND Milestones to S-3 Detector Filled
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Laser system installation complete | I. Kreslo | 1-Oct-2020 | 10-Apr-2020 |  | 
Detector checkout at 130-150 K complete | M. Stancari | 15-Nov-2020 | 26-Oct-2020 |  | 
Vessels filled with LAr, ready for HV | M. Geynisman | 21-Dec-2020 | 23-Nov-2020 |  | 
Drift HV operational | A. Schukraft | 31-Jan-2021 | 9-Dec-2020 |  | 
PMTs operational | R. Van de Water | 31-Jan-2021 | 2-Dec-2020 |  | 
Cryogenics commissioning complete | M. Geynisman | 28-Feb-2021 | 23-Dec-2020 |  | 
Cosmic tracks are observed in the TPC | M. Stancari | 28-Feb-2021 | 23-Dec-2020 |  | 
S3: SBND detector is filled with liquid argon and ready for physics commissioning (LAr purity adequate for physics has been achieved) | A. Schukraft/M. Stancari | 28-Feb-2021 | 23-Dec-2020 |  | 
As presented at Jan 2019 PMG.

## Slide 30: SBND Milestones to S-4a ready for physics data – CRT operational
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Top CRT panels delivered to Fermilab | I. Kreslo | 1-Jul-2019 | 3-Oct-2019 | a | 
Slow controls operational for all detector systems | S. Gollapinni | 15-Sept-2020 | 17-Aug-2020 |  | 
DAQ operational with >5Hz output | W. Badgett | 1-Nov-2020 | 12-Oct-2020 |  | 
Detector system timing synchronized with beam | W. Badgett | 15-Nov-2020 | 21-Sept-2020 |  | 
Trigger system operational | W. Badgett | 15-Jan-2021 | 2-Dec-2020 |  | 
Top CRT panels are installed and ORC’ed | I. Kreslo | 31-Mar-2021 | 20-Jan-2021 |  | 
S4a: SBND detectors are ready for physics data – CRT is operational | M. Stancari | 31-Mar-2021 | 25-Jan-2021 |  | 
Production of the top CRT modules has been delayed to reflect current SBN schedule and optimize load on the Bern workshop. There is no impact on the overall SBN schedule (Installation is planned to start in Dec 2020).
As presented at Jan 2019 PMG.

## Slide 31: SBND Milestones to S-4b ready for physics data – shielding in place
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Shielding blocks in place | C. James | 21-Apr-2021 | 16-Feb-2021 |  | 
CRT system complete and fully commissioned | I. Kreslo | 30-Apr-2021 | 25-Feb-2021 |  | 
S4b: SBND detectors are ready for physics data – Shielding | M. Stancari | 30-Apr-2021 | 25-Feb-2021 |  | 
As presented at Jan 2019 PMG.