## Sheet1
Audit | Recommendation/Suggestion/Opportunity for Improvement | (Identifier) | Assigned to | Response | Status
2018-02 FNAL QA Audit | It is recommended that the FNAL/LCLS-II project team formally captures in-process lessons learned from external and internal sources and experiences. | 98614 | Stanek | Lessons learned are captured through weekly discussions and recorded in meeting minutes; in addition SLAC is using their LL dbs to record significant LLs | Open
2018-02 FNAL QA Audit | It is recommended that the FNAL/LCLS-II project team conducts an analysis of the terrain and route future cryomodules will to take to SLAC. | 98615 | Stanek | The exact route has been chosen and agreed upon with the shipping companies, and has been valdiated with two successful CM transports. | Open
2018-02 FNAL QA Audit | It is recommended that there is a design review held on the transport fixture. | 98616 | Stanek | Review completed 2018-06 | Closed
2018-02 FNAL QA Audit | It is recommended that major modifications of project-related procedures is formally discussed and documented (i.e. required project reviews). | 98617 | Stanek | There is an agreement between SLAC and FNAL regarding critical procedural aspects which require review and approval by SLAC before implementing changes: fasteners, BPM, transportation system. | Open
2018-02 FNAL QA Audit | It is recommended that the FNAL/LCLS-II project team conduct a formal root cause analysis/HPI on the missing washers. The results of this analysis could highlight other potential areas of unsuspecting opportunities for improvement within the project relating to expertise, assembly, or otherwise. | 98618 | Blowers | HPI investigation was completed, and improvements have been implemented. | Closed
2018-02 FNAL QA Audit | It is recommended that the SLAC/LCLS-II project team further engages the FNAL/LCLS-II project team on DRs that are reported by the team to ensure that possible precursors to larger issues that could impact items on the risk register are discussed accordingly. | 98620 | Stanek | [covered in 2018-11 SLAC QA Audit 2.2.5] | Open
2018-02 FNAL QA Audit | There is an opportunity for the lab to establish a role for Teamcenter that manages the structure of parts and part families, including specifying grade types of materials, as well as other any other aspects of Teamcenter that may be deemed difficult to navigate due to a large amount of information. | 98624 | Mossey | While this is till TBD system-wise, materials and grades for the 3.9 GHz CM follow what was implenented and validated for the 1.3 GHz CM. | Open
2018-02 FNAL QA Audit | There is an opportunity for projects or experiments to ensure that processes are in place that trigger the review of specific details regarding materials and components for equipment or systems (e.g. material grade types, specific properties needed for the system, standards, etc.). | 98636 | Mossey | While this is till TBD system-wise, materials and grades for the 3.9 GHz CM follow what was implenented and validated for the 1.3 GHz CM. | Open
2018-02 FNAL QA Audit | There is an opportunity for the lab to verify there is appropriate awareness by project team members of required project/design reviews as well as the recommended review panel subject matter expertise. | 98654 | Tschirhart | The LCLS-II reviews committee members are suggested and agreed upon between the SLAC System Manager and the FNAL CAM. | Open
2018-02 FNAL QA Audit | There is an opportunity for the lab to eliminate the manual aspects of how parts and materials are ordered from Teamcenter via the Engineering Order Form (EOF) and into an Excel file. | 98657 | Mossey | Current process remains in place | Open
2018-03 SLAC QA Audit | Define specifics for acceptance of fasteners installed on the coldmass upper, and revise the travelers accordingly |  | SLAC | Fastener spreadsheet (ED0007530) completed and changes made to 1.3 GHz CM travelers. Similar work will be done for 3.9 GHz CM. | Closed
2018-03 SLAC QA Audit | Adopt an appropriate design change process for critical characteristics |  | SLAC | Systems Engineering Management Plan revised in 12/2018 to reflect this process | Closed
2018-03 SLAC QA Audit | Require WXCX to provide a corrective action plan regarding fasteners for the coldmass upper assembly |  | SLAC | WXCX provided a written CAP, and its implementation was verified by FNAL | Closed
2018-03 SLAC QA Audit | Inspect fasteners for S/CI |  | SLAC | Fasteners were inspected; no S/CI's found | Closed
2018-03 SLAC QA Audit | Include any fastener-related nonconformances in the Significant NCR communication to SLAC |  | SLAC | FNAL will include any fastener-related NCRs in their monthly SigNCR repor to SLAC | Closed
2018-03 SLAC QA Audit | Adopt XFEL specs for hardware material and torque |  | SLAC | BPM torque specs were adopted; after extensive testing current hardware material specs were kept | Closed
2018-03 SLAC QA Audit | Analyze the transportation system, perform necessary testing, to ensure it fulfills its intended purpose |  | SLAC | An extremely thorough analysis and extensive testing were completed, and the system has now been proven to fulfill its intended purpose | Closed
2018-10 DESY Audit | Install caps on ceramics during warm-end coupler installation | 100970 | Ken Premo | This was considered, but not adopted. Risk is very minimal. It was being done during Berry Bolt installation, however. | Closed
2018-10 DESY Audit | Adopt DESY leak check procedure for warm/cold coupler connestions | 100971 | Ken Premo | This was considered, but not adopted. Current procedure is effective. | Closed
2018-10 DESY Audit | Remove O-ring during installation of the two suspension links | 100972 | Ken Premo | This was implemented | Closed
2018-10 DESY Audit | Replace waveguide washer with an oversized one | 100973 | Ken Premo | This was implemented | Closed
2018-10 DESY Audit | Add protection to the couplers during CM installation into the transportation fixture | 100974 | Kaluzny/Hartsell | Currently risk of damage is being mitigated with adminstrative controls (procedure, training, spotters). When time allows an engineered approach will be considered. | Open
2018-11 SLAC QA Audit | The Project should review, revise, and augment the existing processes for change management of design and production to ensure that there is clear traceability of decisions made by the Project through to implementation by the production lines. | 2 | SLAC | Systems Engineering Management Plan revised in 12/2018 to reflect this process | Closed
2018-11 SLAC QA Audit | Establish common definition of major vs minor nonconformances | 2.2 | SLAC | SLAC/LCLS-II procedure for SigNCRs revised to include these definitions | Closed
2018-11 SLAC QA Audit | Reaffirm reporting of SigNCRs to SLAC; ensure they are purposeful; ensure the "right" roles review/approve them | 2.2.1/2.2.2/2.2.3 | SLAC | Discussed and agreed upon between LCLS-II QA Manager and QARs | Closed
2018-11 SLAC QA Audit | SLAC should establish periodic reviews of NCRs | 2.2.5 | SLAC | NCR data are being shared with SLAC | Closed
2018-11 SLAC QA Audit | Partner labs should document the flow from design to production | 2.3 | Blowers | Flow documented and shared with SLAC | Closed
2018-11 SLAC QA Audit | A formal mechanism should be implemented to communicate and disposition lessons learned at the Project level | 4 | SLAC | SLAC is adopting their LL system for significant LLs | Closed