## Sheet1
Type | Review | Review Recommendations | Notes
EPR | LCLS-II CM Transportation Investigation | Review Recommendations | 13 recommendations: 13 ongoing, 0 closed
EPR | Prototype Cryomodule Dressed Cavity Design Engineering Peer Review | Review Recommendations | 65 concerns: Final report does not indicate status of concerns
EPR | BPM and Gate Valve Review | Review Recommendations | 12 recommendations: 5 open, 7 closed
PDR | Cryogenic System | Review Recommendations | 20 recommendations: 2 ongoing, 18 closed
PDR | CM 3.9GHz / FDR: Cavity 3.9GHz | Review Recommendations | 26 recommendations: 11 open, 15 closed
FDR | Cryogenic System | Review Recommendations | 30 recommendations: 1 open, 27 closed, 2 ongoing
FDR | LCLS-II 3.9 GHz Cryomodule Final Design Review | Review Recommendations | 4 recommendations: Final report does not indicate status of recommendations
FDR | CM Stands | Review Recommendations | 13 recommendations: 9 open, 3 closed
FDR | CM Interconnection | Review Recommendations | 7 recommendations: all closed
FDR | CM Production | Review Recommendations | 18 recommendations: all closed
FDR | CM Prototype / Magnet | Review Recommendations | 20 recommendations: all closed
FDR | CM Prototype / Tuner | Review Recommendations | 14 recommendations: all closed
FDR | CM Prototype | Review Recommendations | 8 recommendations: all closed