## Slide 1: Plan For Installation Of The HEBT
Rich Andrews

## Slide 2: Outline of Presentation
1) Status of HEBT Mechanical Design
  a) Bill of Materials
  b) Examples:
    Photos of existing elements
    Drawing number references
2) HEBT Installation Planning
  a) HEBT Assembly Options
  b) Sequence of Assembly
  c) Particle Free Assembly and Service

## Slide 3
Beamline Element | Status | Support Structure | Drawing No.
HEBT Girder | in house | N/A | See photo
HEBT Girder Add On | Design in progress |  | 
Dump Girder | Design in progress |  | 
SSR-1 Isolation Valve |  | N/A | 
Ion Pump T | Procure elements | Design Complete | TC# F10070746
ACCT | in house | Need design | TC# F10070746
Quadrupole Magnet | in house | Modify Existing Design | TC# F10021417
BPM | in house | Need design | TC# F10018276
Ion Pump T | Procure elements | Design Complete | TC# F10070746
Quadrupole Magnet | in house | Modify Existing Design | TC# F10021417
Fast Acting Valve | in house | Modify Existing Design | 
Dipole Magnet | in house | Design Complete | TC# F10042979
RWCM |  | Need design | TC# F00484270-A
BPM | in house | Need design | TC# F10018276
Housing (wire & slits) | Procure elements | in house | 
Dipole Magnet | in house | Design Complete | TC# F10042979
Ion Pump T | Procure elements | Design Complete | TC# F10070746
Pneumatic Valve | in house | Modify Existing Design | 
Fast Faraday Cup | in house | Design Complete | TC# F1003100
Time of Flight Monitor | in house | Design Complete | TC# F10039331
Housing (wire & slits) | Procure elements | in house | 
Dipole Magnet | in house | Design Complete | TC# F10042979
Cross |  | Future Expansion | 
BPM | in house | Need design | TC# F10018276
Bill of Materials

## Slide 4: Design of HEBT
Elements in the HEBT chosen by the needs of the required beam measurements
Most of the components have been used in the various configurations of the MEBT
The Pumping T’s are a new design driven by the vacuum requirements of the HWR & SSR1
The stand-alone quadrupole magnets incorporate a modification of the support and alignment structure used in the MEBT
Extensive particle free assembly experience:
  In FAST
    From CC1 to the Superconducting Cryo Module
  In PIP2 IT
    Connection of MEBT to the HWR

## Slide 5: Pumping T (w/o Turbo Pump)
This version shows one of the configurations that will be used in the HEBT.
Additional Pumping T’s will not include a NEG Pump

## Slide 6: Other Elements Already In Use
Fast Faraday Cup
(Team Center # F10031000)
Time of Flight
(Team Center # F10039331)

## Slide 7
Portable Clean Room At NML
(this design will be replicated for HEBT Installation)

## Slide 8: HEBT Installation Planning (this is what the final configuration will look like)
MEBT
SSR1
HWR
HEBT
Dump

## Slide 9: HEBT Connection (to SSR1 and Beam Dump)
SSR1
HEBT
Beam Dump and Shielding

## Slide 10: Initial Configuration
SSR-1 Prototype
Pumping Tee with Ion Pump and NEG Pump

## Slide 11: Beam Dump:
SSR1
HEBT
Beam Dump and Shielding
Plan to install Dump and shielding prior to HEBT install

## Slide 12: 1) Install and Align Girder
Anchor to the floor

## Slide 13: 2) Install and Align Beam Dump

## Slide 14: 3) Connect Tee and Spool
Portable cleanroom will be required at this point

## Slide 15: 4) Begin addition of concrete shielding blocks

## Slide 16: 5) Surround beam pipe with steel bricks

## Slide 17: 6) Continue construction with concrete shield blocks

## Slide 18: 7) Add 2.0” of steel around dump (4 sides)
This is conceptual for the steel. It will need to be secured to the floor and adjacent pieces

## Slide 19: 8) Add concrete blocks around sides (1.5’ thick on East side & 3’ thick on the West side)

## Slide 20: 9) Complete shielding on top and rear end (3’ everywhere)
This assembly is conceptual and needs some further definition:
  The design of the steel structure may be modified to require such large pieces
  Some tuning of the block configuration may also be required
The duration of the assembly of the shielding is estimated to take between 2 to 4 weeks
  This does not include time required to collect materials
  Most materials are located on site
  There are some exceptions:
    2” steel may need to be procured
    “E” blocks are in short supply and may need to be procured as well

## Slide 21: HEBT Installation Starting Configuration

## Slide 22: HEBT Assembly Options
Plan A
  Assemble complete girder in Class 10 Clean Room
    Move to cave and connect to SSR-1 and Beam Dump
Plan B
  Assemble components into sub-assemblies in Class 10 Clean Room
    Locate sub-assemblies on a free standing girder
      Rough align
      Make interconnections using a portable clean room
    Blank flanges on the ends
    Move into position between the SSR-1 and the Beam Dump
    Rough align assembly and anchor to the floor
    Final align
Plan C
  Move empty girder into position, align and anchor
    Install sub-assemblies (initial work done in Class 10 Clean Room)
      Rough align sub-assemblies
    Using a Portable Clean Room, make the interconnections
Will depend on the status of SSR1 testing

## Slide 23: Installation Planning
Plan B Location
Plan C Location
(in situ)

## Slide 24
Plan C is the preferred choice:

## Slide 25: Sequence Of Assembly
Pre-assembly Work:
  SSR1 and Dump shall be installed and aligned first
  Assemble all HEBT subcomponents in the Class 10 Clean Room:
    Pumping Tees
    Valves (Pneumatic and Fast)
    Scrapers
    BPM and spool subassemblies
    All instrumentation
Mount sealed components and subassemblies on their respective girders
  May be located in situ or in the CMTF Hi Bay
  A portable clean rom will be required
  Rough align on the girder (Alignment task)
Connect HEBT to SSR1 and the Dump:
  Pumping Tee to HEBT Connection
  HEBT to Dump Girder Connection

## Slide 26: 1) Starting Point: (for HEBT Installation)
SSR1 Installed with Pumping Tee
Dump Installed w/ Shielding

## Slide 27
2) Install Girders:
Installed, Aligned and Anchored

## Slide 28
3) Install Major Devices
(Particle Free Cleaned and Blanked Off)
(Pumping T’s, ACCT, Fast Faraday Cup, RWCM, Time of Flight, Scrapers, Gate Valves, Magnet Bottom Halves)
Rough Align these devices

## Slide 29
4) Install Spools Between Devices
(From US to DS)
(Portable Clean Room required for this step)
Leak Check Assembly:
  Low Particulate Vacuum Cart will be used
  RGA scan of assembly after

## Slide 30
5) Install Magnets (top halves)
Final Align Magnets and Devices
This installation task is estimated to require between 4 to 6 weeks

## Slide 31: Particle Free Assembly and Service
The HEBT will be prepared for particle free service using procedures developed here at Fermilab:
  Slow Flow Pumping Cart will be used for both start-up and bringing the system back to atmospheric pressure
    ED0000373 (Operation of the mass-flow vacuum cart)
Any newly procured items will be cleaned in a Class 10 Cleanroom:
  All elements on the Pumping Tee
  Beam Pipe (with bellows and BPM’s)
  We will use the standard practices that have been developed here at Fermilab
    ED0003571 (Cleaning for particle-free vacuum service)
Already installed items (that have been previously cleaned) will not be disassembled if:
  We can do an RGA analysis to previously installed equipment to demonstrate their cleanliness:
    Fast Faraday Cup
    Time of Flight Monitor
    Beam Dump
  In all cases, these elements will be blown off to demonstrate that they are particle free

## Slide 32: Particle Free Assembly
An example of a subcomponent built from newly procured elements
An example of a subcomponent built from elements already in use

## Slide 33: Summary:
Most of the HEBT elements are in house:
  Magnets
  Time of Flight monitor
  Fast Faraday Cup
  Fast Acting Valve
  ACCT
  RWCM
  BPM’s
    Will need some rework
    Also need to consider how they will be mounted so the positioning is assured
Additional design work required:
  Dump Shielding (securing the steel, fitting the blocks into the design)
  Some of the support structures (most will be derivatives of existing designs)
  Portable cleanroom
Procurement required:
  Housings for Slits
  Girders (3 required) need to be procured; one girder is in house
  Hardware for spools (tubing, bellows and flanges)
  Cleanroom components