## SP-PDS
Responsibility Commitment Level Table
1 (Best) | Written commitment from national funding agency
2 | Oral commitment from national funding agency
3 | Institutional expression of interest with likely funding support identified
4 | Institutional expression of interest
5 | Researcher/PI expression of interest
WBS | WBS Element Name | WBS Dictionary (Concise) | Deliverables | Responsible Institutions | Responsible Agency | Responsibility Commitment Level
DUNE
2 | Single Phase 10KT 1
2.4 | Single-Phase Photon Detector System
2.4.1 | Project Management (Milestones, Reviews)
2.4.1.1 | Light collector WG Project Management | Light collector reviews and milestones
2.4.1.1.1 | Final light collector technology review | Final light collector review | Approval | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.1.2 | Light collector technologyconfirmation | Final confirmation of baseline light collector design | Final confirmation of light collector selection | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.1.3 | Light collector pre-production review | Light collector pre-production review | Approval to begin light collector fabrication | CSU/UNICAMP | USA/BRAZIL | 3
2.4.3.1.4 | Light collector production QC setup complete | MILESTONE-- Light collector QA/QC approved | QC plan and equipment in place | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.1.5 | Light collector production start | MILESTONE-- Module production begins | PD light collector construction start | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.1.6 | Light collector first article delivered | MILESTONE-- First module delivery | First modules delivered to integration site | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.1.7 | Light collector final article delivered | MILESTONE-- Final module delivery | Final modules delivered to the integration site | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.2 | Photosensor WG Project Management | Photosensor reviews and milestones
2.4.1.2.1 | Photosensor pre-production review | Pre-production review of photosensors, mounting PCBs | Approval to begin photosensor procurement/fabrication | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.2.2 | Contracts placed for purchasing of production photosensors | MILESTONE-- Purchase contract let | Photosensor procurement contracts placed | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.2.3 | Photosensor production QC test station complete | MILESTONE-- QA plan and equipment complete | QC plan/test stations complete | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.2.4 | Photosensor first article delivered | MILESTONE-- First photosensor PCBs delivered | First cold boards delivered | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.2.5 | Photosensor final article delivered | MILESTONE-- Final photosensor PCBs delivered | Final cold boards delivered | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3 | Electronics/Cables/Calibration WG Project Management | Electronics, cables, monitoring reviews and milestones
2.4.1.3.1 | Electronics/cables pre-production review | Electronics, cables, pre-production review | Approval to begin electronics, and cables purchasing and fabrication | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.2 | Electronics /cables QC test station complete | MILESTONE-- QA plan and equipment complete | QC plan and equipment in place | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.3 | Electronics/cables production start | MILESTONE-- Electronics/cabling production begin | Electronics/cabling construction begins | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.4 | Electronics/cables first article delivered | MILESTONE-- Electronics/cabling first delivery | Electronics/cabling first articles delivered | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.5 | Electronics/cables final article delivered | MILESTONE-- Electronics/cabling final delivery | Electronics/cabling final articles delivered | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.6 | Calibration/monitoring pre-production review | Calibration/monitoring pre-production review | Approval to begin calibration/monitoring system purchasing and fabrication | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.7 | Calibration/monitoring QC test station complete | MILESTONE-- QA plan and equipment complete | QC plan/testing station for calibration/monitoring in place | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.8 | Calibration/monitoring production start | MILESTONE-- Monitoring system production begin | Calibration/monitoring system fabrication begins | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.9 | Calibration/monitoring first article delivered | MILESTONE-- Monitoring system first delivery | Calibration/monitoring system first articles delivered | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.3.10 | Calibration/monitoring final article delivered | MILESTONE-- Monitoring system final delivery | Calibration/monitoring system final articles delivered | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.4 | Integration WG Project Management | Integration and installation reviews and milestones
2.4.1.4.1 | Photon system /APA/CPA/CE Integration Review | Photon detector/APA/CPA/CE Integration Review | Approval to proceed with PD design/integration plan | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.4.2 | Photon System integration plan/tooling review | Photon detector integration tooling review | PD/Cabling integration plan approved | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.4.3 | Photon system installation plan/tooling review | Photon detector installation plan review | PD FD installation plan approved | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.4.4 | Photon system/APA Integration start | MILESTONE-- Photon detector integration begins | PD Integration begins | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.4.5 | Photon system/APA Integration finished | MILESTONE-- Photon detector integration end | PD Integration complete | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.4.6 | Photon system Installation (SURF) Start | MILESTONE-- Photon Detector installation begins | PD installation/Cabling Begins | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.4.7 | Photon system Installation (SURF) Stop | MILESTONE-- Photon detector installation ends | PD installation/Cabling Complete | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.5 | Software and Physics WG Project Management | Software and physics reviews and milestones
2.4.1.5.1 | Integrated Simulation framework complete | MILESTONE-- Simulation Framework Complete | Simulation framework complete | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.5.2 | Integrated Reconstruction framework complete | MILESTONE-- Reconstruction framework complete | Reconstruction framework complete | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.5.3 | Simulation/Reconstruction framework review | Review of simulation/reconstruction framework | Approval of physics and simulation framework packages | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.5.4 | Online Monitoring Suite complete | MILESTONE-- Online monitoring suite complete | Online monitoring package complete | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.5.5 | Online monitoring review | DAQ/Management review of online monitoring suite | Online monitoring suite approval | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.5.5 | Online Database project complete | MILESTONE-- Online database complete | Online database complete | CSU/UNICAMP | USA/BRAZIL | 3
2.4.1.5.6 | Project database review | DAQ/Management review of online database | Online database approval | CSU/UNICAMP | USA/BRAZIL | 3
2.4.2 | Physics and Simulations
2.4.2.1 | Light Collector WG Physics/Simulations | Simulations and performance requirements of light collectors
2.4.2.1.1 | Photon Detector Part of Final Geometry | Final photon detector geometry in detector simulation
2.4.2.2 | Photo Sensor WG Physics/Simulations | Simulations and performance requirements of light collectors
2.4.2.2.1 | Photosensor response parameterization or simulation | Parametric simulation of photosensors
2.4.2.3 | Electronics/Cables/Calibration WG Physics/Simulations | Simulations and performance requirements of elect/cabling
2.4.2.3.1 | Electronics, DAQ, Trigger Simulation | Simulations of PD electronics in DAQ/triggering
2.4.2.3.2 | Trigger/filter Development | Developement of algorithms for triggering/event filtering
2.4.2.4 | Integration WG Physics/Simulations | Incorporation of integration/installation data into sim
2.4.2.4.1 | Photon Detector Positions and Channel Map in Final Geometry | Photon detector positions and channel mapping in sim
2.4.2.4.2 | Collection of relevant QC/QA data into database | Integration of PD QC/QA data into project database
2.4.2.5 | Software and Physics WG Physics/Simulations | Photon detector system physics/simulation studies
2.4.2.5.1 | Simulation | Photon detector simulation studies
2.4.2.5.1.1 | Simulation of Light Formation in LAr | Simulation of Light Formation in LAr
2.4.2.5.1.2 | Validate Material and Optical Properties | Validate Material and Optical Properties
2.4.2.5.1.3 | Integrate Light Collector, Sensor, Electronics/Trigger with LAr light simulation | Integrate PD system with LAr light simulation
2.4.2.5.2 | Reconstruction | Event reconstruction studies with PD system
2.4.2.5.2.1 | Reconstruct light and associate with the TPC | Develop tools to reconstruct light and link to TPC tracks
2.4.2.5.2.2 | Calorimetry with Light | Develop tools to perform light-based calorimetry
2.4.2.5.2.3 | Study PID with Pulse Shape Discrimination | Develop tools toperform PID with light signals
2.4.2.5.3 | Online Software | Develop online software tools for PD system
2.4.2.5.3.1 | Online Monitoring | Develop online monitoring tools
2.4.2.5.3.2 | Slow Controls | Develop slow control tools
2.4.2.5.3.3 | Stable Data Running Mode | Develop stable data running mode
2.4.2.5.3.4 | Calibration Running Mode | Develop running mode for PD monitoring/calibration
2.4.2.5.4 | Databases | Integrate PD system with DUNE online database
2.4.2.5.4.1 | Calibration Database | Integrate PD calibration/monitoring with DUNE calibration database
2.4.2.5.4.2 | Hardware Database | Integrate PD hardware QC/QA with DUNE hardware database
2.4.3 | Design, Engineering and R&D
2.4.3.1 | Light Collector WG Design, Engineering and R&D | Final light collector pre-production engineering, testing and verification
2.4.3.1.1 | Light Collector Module | Final modifications to light collector design based on pre-prod review
2.4.3.1.1.1 | ARAPUCA- Design | Final pre-production modifications fab. drawings X-ARAPUCA design | ARAPUCA-Final 10kt Conceptual Design |  | Brazil | 3
2.4.3.1.1.2 | ARAPUCA-Engineering Design | Final engineering verification of X-ARAPUCA design | ARAPUCA-Final 10kt Engineering/Calculations |  | Brazil | 3
2.4.3.1.1.3 | ARAPUCA-Materials Testing/Verification | Final materials testing/verification for X-ARAPUCA design | ARAPUCA-Final 10kt Bill of Materials |  | Brazil | 3
2.4.3.1.1.4 | ARAPUCA-Final Development Modeling | Final pre-production PD modules (PD module 0) | ARAPUCA-Final Prototypes for Final Testing |  | Brazil | 3
2.4.3.1.2 | Final Production Preparation | Testing of final prototypes and system engineering
2.4.3.1.2.1 | Testing of PD Module Prototypes | Final pre-production prototype testing | Comparative Testing results in LAr |  | Brazil | 3
2.4.3.1.2.2 | System Configuration Final Selection | Final design/engineering PD/PA/CPA/CE Interfaces | Final PD Module Configuration Selection |  | Brazil | 3
2.4.3.1.2.3 | Final Engineering Design | Generation of final engineering reports, fabrication drawings | Final Module and Booster Design(s) Ready for Fabrication |  | Brazil | 3
2.4.3.2 | Photo Sensor WG Design, Engineering and R&D | Final photo sensor pre-production engineering, testing and verification
2.4.3.2.1 | Evaluation, Qualification, and Selection of Photosensors | Final selection of photosensors | Selected photosensors |  | Italy | 3
2.4.3.2.2 | Tested Array and Ganging Configuration | Final verification of actively ganged photosensors | Optimal ganging scheme(s) |  | Italy | 3
2.4.3.2.3 | Cold Board Design and Prototyping | Final verification of passively ganged photosensor mounting PCB | Fabricated Cold Board prototype(s) |  | Italy | 3
2.4.3.2.4 | Tested Photosensor assemblies | Final verification of assembled photosensor mounting board | Tested Cold Board prototype(s) |  | Italy | 3
2.4.3.2.5 | Preliminary negotiations with sensor vendors | Begin negotiations with photosensor vendors | Frozen product, cost estimate and proposed method of delivery |  | Italy | 3
2.4.3.2.6 | QA/QC Plan | Finalize photosensor QC/QA plan based of prototype tests | QA/QC procedure |  | Italy | 3
2.4.3.3 | Electronics/Cables/Calibration WG Design, Engineering and R&D | Final Electronics/cables/calibration pre-production engineering, testing and verification
2.4.3.3.1 | Readout Electronics Design | Final modifications to warm readout electronics design | Pre-production electronic module design |  | Peru, Colomia | 4
2.4.3.3.3 | Photon Detector Cable Selection/Validation | Final testing/verification of photon detector cables |  |  |  | 4
2.4.3.3.3.1 | Cold Signal Cable Selection/Validation | Final verification of cold cables (nside and outside APA) | Selected cold signal readout cables/connectors |  | Peru, Colomia | 4
2.4.3.3.3.3 | Warm signal cable Selection/Validation | Final verificatin of warm (outside cryostat) cables | Selected warm signal readout cables/connectors |  | Peru, Colomia | 4
2.4.3.3.4 | Photon Detector Power Supply Selection/Validation | Final selection and verification of DC powr supplies for warm electronics |  |  |  | 4
2.4.3.3.4.1 | Non-bias voltage power supply Selection/Validation | Selection and verification of lov-voltage front-end electronics supplies | Selection of non-bias power supplies |  | Peru, Colomia | 4
2.4.3.3.5 | Grounding scheme for PD electronics/cables/power supplies | Final design and validation of PD system grounding plan | Dune/PD grounding plan |  | Peru, Colomia | 4
2.4.3.3.6 | PDS Monitoning/Calibration System | Final selection and verification of LED flasher monitoring system
2.4.3.3.6.1 | Pre-production monitoring design | Final design and engineering of monitoring system
2.4.3.3.6.2 | Monitoring system Materials Selection | Monitoring system materials verification
2.4.3.3.6.3 | Monitoring system Prototyping | Final pre-production prototype fabrication and testing
2.4.3.3.7 | Signal cable feedthru selection/validation | Final engineering design, and prototype verification of PD signal feedthrough |  |  | Brazil | 3
2.4.3.4 | Integration WG Design, Engineering and R&D | Final Integration/Installation pre-production engineering, testing and verification
2.4.3.4.1 | System Engineering | Final design verification of PD system engineering
2.4.3.4.1.1 | Development of QA Plan (specification of tests/facilities) | Development of QA Plan (specification of tests/facilities)
2.4.3.4.1.1.1 | Material Selection/Characterization | Material Selection/Characterization | Database of approval of all PD materials to be used in DUNE for cryogenic performance |  | Brazil/USA | 3
2.4.3.4.1.1.2 | Aging tests for material coatings | Aging tests for material coatings | Approval of all coatings materials to be used in DUNE |  | Brazil/USA | 3
2.4.3.4.1.1.3 | Aging tests for photosensorss | Aging tests for photosensorss | Approval of photosensor studies for DUNE |  | Italy | 3
2.4.3.4.2 | External Interface Specifications (with other subsystems) | Final specification of system interface documents | Creation and maintenance of DUNE interface documents |  | Brazil/USA | 3
2.4.3.4.3 | Internal Interface Specifications (within PDS subsystem) | Final cross-check of internal PD subsystem interfaces | Creation and maintenance of PD internal interface documents |  | Brazil/USA | 3
2.4.3.4.4 | Development of QC Plans (for all components) | Final QC plan and verification | Supervision of QC/QA plans for all PD components |  | Brazil/USA | 3
2.4.3.4.5 | Develop Cable Routing Plan | Final verification and interface drawings for cable routing plan | Complete final cable routing plan |  | Brazil/USA | 3
2.4.3.4.6 | Design Cable Support Structures | Final fabrication drawings and engineering for cable supports | Approved final cable management plan |  | Brazil/USA | 3
2.4.3.4.7 | Finalize Installation Plan | Develop PD installation plan | PD Integration plan |  | Brazil/USA | 3
2.4.3.4.9 | Finalize Plan for connecting cables to feedthroughs | Plan for Cable-feedthrough connections, installation handling | Installation & cabling of PDs into crypstat |  | Brazil/USA | 3
2.4.3.4.10 | Design Pre-Integration QC test Facility | Design of pre-integration test facility | Integration testing equipment design |  | Brazil/USA | 3
2.4.3.4.11 | Design Pre-Installation QC test Facility | Design of pre-installation test facility | Pre-installation PD test apparatus design |  | Brazil/USA | 3
2.4.4 | Production Setup
2.4.4.1 | Light Collector WG Production Setup | Production tooling and QC equipment for X-ARAPUCA fabrication
2.4.4.1.1 | Light collector fabrication tooling | Tooling to fabricate light collector frames and optical filters/coatings
2.4.4.1.1.1 | Incoming QC Equipment | Incoming QC test equipment for mechanical components | Incoming materials acceptance equipment |  | Brazil | 3
2.4.4.1.1.2 | Optical compontnt/coating. | Equipment to fabricate.coat optical filters/reflectors | Fabrication Tooling Complete |  | Brazil | 3
2.4.4.1.1.3 | Module Assembly Mechanical Assembly Tooling | Tooling to align and position PD compontnes during assembly | Fabrication Tooling Complete |  | Brazil | 3
2.4.4.1.2 | Post-Assembly Test Stand Development | Optical scanner and cryogenic test facilities for post-assembly testing. | Post-Assembly Test Stand(s) |  | Brazil/USA | 3
2.4.4.2 | Photo Sensor WG Production Setup | Procurement planning and test stand for incoming photosensor QC/QA
2.4.4.2.1 | SiPM Procurement | Photosensor procurement process
2.4.4.2.1.1 | Specification of devices and terms of purchase | Specification of devices and terms of purchase | Contract with vendor |  | Italy | 3
2.4.4.2.1.2 | Generation of a Purchase Order | Generation of a Purchase Order | Order placed with vendor |  | Italy | 3
2.4.4.2.2 | SiPM Test Stand(s) Development | SiPM Test Stand(s) Development
2.4.4.2.2.1 | SiPM Warm Test Stand(s) Development | Warm test stands for incoming and post-mounting photosensor tests | Room Temperature Test Stand(s) |  | Italy | 3
2.4.4.2.2.2 | SiPM Cold Test Stand(s) Development | Cryogenic test stands for post-mounting photosensor tests | Cryogenic Temperature Test Stand(s) |  | Italy | 3
2.4.4.3 | Electronics/Cables/Calibration WG Production Setup | Test stands and fabrication stations for electronics/cabling/monitoring
2.4.4.3.1 | Design/Fabricate readout Electronics Test Stand | Test stand for QC testing warm front end readout electronics | Front end electronics test stand |  | Peru, Colomia | 4
2.4.4.3.2 | Design/fabricate cold active ganging test stand | Test stand for QC testing of cold active ganging circuits | SiPM board test station |  | Peru, Colomia | 4
2.4.4.3.3 | Design/fabricate Photon Detector Cable test stand | Test stand for post-assembly continuity checks of assembled PD cables | Cable test stands |  | Peru, Colomia | 4
2.4.4.3.4 | Photon Detector Power Supply test stations | Test stations for validation of DC power supplies
2.4.4.3.4.1 | Non-bias voltage power supply test station | Test station for non-bias low voltage DC power supplies | Non-bias voltage power supply test station |  | Peru, Colomia | 4
2.4.4.3.5 | PDS Monitoning/Calibration test station | Test station for monitoring system diffusers and optical fibers | Calibration/monitoring equipment QA/QC test station
2.4.4.3.6 | Signal cable feedthru Test Station | Test station for post-assembly vacuum and electrical feedthrough tests | Cryostat flange test station |  | Brazil | 3
2.4.4.4 | Integration WG Production Setup | Integration WG Production Setup |  |  |  | 3
2.4.4.4.1 | Fabrication of pre-integration QC test Facility | QC test equipment for integration including scanner, continuity | Warm scanner and cold box readout system |  | Brazil, USA | 3
2.4.4.4.2 | Fabrication of pre-installation QC test Facility | QC test equipment for installation including continuity, operational readout system | warl pre-installation test stand. |  | Brazil, USA | 3
2.4.5 | Production
2.4.5.1 | Light Collector WG Production | Production and QC testing of PD modules
2.4.5.1.1 | Light collector module Production Fabrication Components | Fabrication of PD module components
2.4.5.1.1.1 | Module Assembly Components (Mechanical) | Fabrication/procurement of frame and electrical routing components | Components for PD Module Fabrication |  | Brazil | 3
2.4.5.1.1.2 | Optical components (Filters, coatings) | Fabrication/procurement of optical components (filters, reflectors, WLS bars) | Components for PD Module Fabrication |  | Brazil | 3
2.4.5.1.1.3 | PD module assembly | Assmebly of PD modules | Assembled |  | Brazil | 3
2.4.5.1.2 | APA-PD Interface hardware/Cabling | Fabrication/procurement/assembly of APA-PD interface hardware | PD cables and mounting hardware installid in APA frame |  | Brazil | 3
2.4.5.1.3 | Post-Assembly Testing | Post-assembly QC testing of PD modules
2.4.5.1.3.1 | Post-Assembly Testing – Scanner Response | Scanning of completed PD modules in LED scanner | Post-Assembly Testing (Prior to Shipping) |  | Brazil | 3
2.4.5.1.3.2 | Post-Assembly Testing – Cryogenic Stability | Cryogenic immersion and operation of completed PD modules | Post-Assembly Testing (Prior to Shipping) |  | Brazil | 3
2.4.5.1.4 | Production Shipping | Shipping of PD modules from assembly site to integration facility | Crates, Shipping & Storage for PD Podules (Pre-Install) |  | Brazil | 3
2.4.5.2 | Photo Sensor WG Production | Photosensor procurement, assembly to PCBs, testing
2.4.5.2.1 | Procure SiPMs | Procure SiPMs from vendor(s) | Purchased SiPMs |  | Italy | 3
2.4.5.2.2 | SiPM Testing | SiPM incoming testing
2.4.5.2.2.1 | Specification of testing procedures and parameters | Specification of testing procedures and parameters | Qualification Criteria |  | Italy | 3
2.4.5.2.2.2 | Warm testing of SiPMs | Warm testing of SiPMs Prior to mounting) | SiPMs ready for mounting on cold board |  | Italy | 3
2.4.5.2.2.3 | Warm testing of cold board | Warm testing of photosensors mounted to cold board | Cold board ready for cryo testing |  | Italy | 3
2.4.5.2.2.4 | Cold testing of cold board | Cryogenic testing of assembled cold boards | Tested Cold Boards ready for PD modules |  | Italy | 3
2.4.5.2.2.5 | Testing Documentation and QC Database | Documentation of testing results in QC database | QA/QC database |  | Italy | 3
2.4.5.2.3 | Cold Board Production | Fabrication of passive-ganging cold photosensor mounting boards
2.4.5.2.3.1 | Cold Board Fabrication | Procurement of cold passive/ganging PCBs | Fabricated cold board |  | Italy | 3
2.4.5.2.3.3 | Cold Board Testing | Pre-assembly testing of cold passive/ganging PCBs | Cold board ready for mounting of SiPMs |  | Italy | 3
2.4.5.2.3.4 | Mounting of SiPMs on Cold Board | Mounting of photosensors on cold board | Cold board ready for warm testing of ganged sensors |  | Italy | 3
2.4.5.3 | Electronics/Cables/Calibration WG Production | Fabrication/procurement of electronics/cabling/calibration system
2.4.5.3.1 | Readout Electronics | Fabrication and testing of warn readout electronics
2.4.5.3.1.1 | Readout Electronics Fabrication | Procurement and fabrication of warm readout electronics | Fabricated Front-end readout electronics units for 150 APAs |  | Peru, Colomia | 4
2.4.5.3.1.2 | Readout Electronics Testing | Post-assembly testing of warm readout electronics | Tested Front-end readout electronics units for 150 APAs |  | Peru, Colomia | 4
2.4.5.3.2 | Photosensor Cold Active Ganging | Fabrication and testing of cold photosensor active ganging circuits
2.4.5.3.2.1 | Photosensor Cold Active Ganging Fabrication | Procurement and fabrication of cold photosensor active ganging circuits | 3000 stuffed active ganging PCBs |  | Italy | 3
2.4.5.3.2.2 | Photosensor Cold Active Ganging testing | Post assembly testing of cold photosensor active ganging circuits | 3000 Tested cold active ganging boards |  | Italy | 3
2.4.3.3.3 | Photon Detector Cable Fabrication/testing | Fabrication and testing of PD cables
2.4.5.3.3.1 | Cold Signal/Bias Cable | Fabrication and testing of PD cryogenic signal/bias cables
2.4.5.3.3.1.1 | Cold Signal/Bias Cable Fabrication | Procurement and fabrication of PD cryogenic signal/bias cables | Cold signal/Bias cables (21 configurations) fabricated |  | Peru, Colomia | 4
2.4.5.3.3.1.2 | Cold Signal Cable Testing | Testing of assembled PD cryogenic signal/bias cables | Cold signal/bias cables (21 configurations) tested |  | Peru, Colomia | 4
2.4.5.3.3.3 | Warm signal cable | Fabrication and testing of PD warm (outside cryostat) signal/bias cables
2.4.5.3.3.3.1 | Warm signal cable Fabrication | Procurement and fabrication of PD warm signal/bias cables | Warm signal cables (4 configurations) fabricated |  | Peru, Colomia | 4
2.4.5.3.3.3.2 | Warm signal cable Testing | Testing of assembled PD warm signal/bias cables | Warm signal cables (4 configurations) tested |  | Peru, Colomia | 4
2.4.5.3.4 | Photon Detector Power Supply Procurement/Testing | Photon Detector Power Supply Procurement/Testing
2.4.5.3.4.1 | Non-bias voltage power supply | Procurement and testing of low-voltage DC power supplies
2.4.5.3.4.1.1 | Non-bias voltage power supply Procurement | Procurement of low-voltage DC power supplies | non-bias power supplies procured |  | Peru, Colomia | 4
2.4.5.3.4.1.2 | Non-bias voltage power supply testing | Testing of low-voltage DC power supplies | Non-bias power supplies tested |  | Peru, Colomia | 4
2.4.5.3.5 | Grounding Materials PD electronics/cables/power supplies Procurement | Procurement of grounding supplies/materials for PD grounding | Grounding materials for 150 APAs |  | Peru, Colomia | 4
2.4.5.3.6 | PDS Monitoning/Calibration System | Procurement and testing of PD monitoring/calibration system
2.4.5.3.6.1 | Monitoring system procurement/Fabrication | Procurement and fabrication of PD monitoring system | Monitoring/calibration system (optical fibers, diffusers, LED drivers) for 1 10kt detector
2.4.5.3.6.2 | Monitoring systemTesting | Testing of PD monitoring system | QA/QC tests of Monitoring/calibration system (optical fibers, diffusers, LED drivers) for 1 10kt detector
2.4.5.3.7 | Signal cable feedthrough | Procurement, fabrication and testing of cryogenic feedthrough plate
2.4.5.3.7.1 | Signal cable feedthrough Fabrication/Procurement | Signal cable feedthrough Fabrication/Procurement | Signal cable feedthroughs procured |  | Brazil | 3
2.4.5.3.7.2 | Signal cable feedthrough testing | Signal cable feedthrough testing | Signal cable feedthroughs tested |  | Brazil | 3
2.4.6 | Integration (Integration/Test Facility)
2.4.6.1 | Light Collector WG Integration (Global Integration Facility) | Will capture any PD module fabrication work at ITF | NONE |  | N/A
2.4.6.2 | Photo Sensor WG Integration (Global Integration Facility) | Will capture any Photosensor work at ITF | NONE |  | N/A
2.4.6.3 | Electronics/Cables/Calibration WG Integration (Global Integration Facility) | Will capture any electronics/cabling/monitoring work at ITF | NONE |  | N/A
2.4.6.4 | Integration WG Integration (Global Integration Facility)
2.4.6.4.1 | Operation of pre-integration QC test facility | Personel to operate test facility at ITF | Tested modules at integration facility |  | Brazil/USA | 3
2.4.6.4.2 | Personel for PD integrtion into APAs | Dedicated PD labor for integrating components and PD modules | Tested modules at integration facility |  | Brazil/USA | 3
2.4.6.4.3 | Test photon detectors/cables on APAs (Integration Facility?) | Dedicated PD labor for post-integration testing at ITF | Integrated PD modules tested |  | Brazil/USA | 3
2.4.7 | Installation (Activity at SURF)
2.4.7.1 | Light Collector WG Installation (Activity at SURF) | Will capture any PD module fabrication work at SURF | NONE |  | N/A
2.4.7.2 | Photo Sensor WG Installation (Activity at SURF) | Will capture any PD module fabrication work at SURF | NONE |  | N/A
2.4.7.3 | Electronics/Cables/Calibration WG Installation (Activity at SURF) | Will capture any PD module fabrication work at SURF | NONE |  | N/A
2.4.7.4 | Integration WG Installation (Activity at SURF)
2.4.7.4.1 | Pre-APA Installation | Specialized labor for pre-installation photon detector QC checkout | Final pre-installation testing of PD modules |  | Brazil/USA | 3
2.4.7.4.2 | Connect cryostat flange cables | Specialized labor for pre-installation photon detector cabling/continuity checks | PD cables connected in cryostat and tested |  | Brazil/USA | 3
2.4.7.4.3 | Initial Operation/qualification of PD system | Specialized labor for post-installation PD test operation and checkout | Initial operational testing in cryostat |  | Brazil/USA | 3
2.4.7.4.4 | Analysis of PDS Performance | Specialized abor for analysis of PD test operation and checkout | Final post-installation performance testing |  | Brazil/USA | 3
2.4.7.5 | Software and Physics WG Installation (Activity at SURF) | Specialized labor for final inclusion of PD location mapping and QC data in DUNE database | NONE |  | Brazil/USA | 3

## WBS Dictionary Detailed
WBS | WBS Element Name | WBS Dictionary (Concise) | WBS Dictionary (Expanded)
DUNE
2 | Single Phase 10KT 1
2.4 | Single-Phase Photon Detector System
2.4.1 | Project Management (Milestones, Reviews)
2.4.1.1 | Light collector WG Project Management | Light collector reviews and milestones | Reviews and scheduling milestones for light collector designs, components and modules
2.4.1.1.1 | Final light collector technology review | Final light collector review | Review of light collector designs for performance against PD requirements, cost effectiveness, and risk.
2.4.1.1.2 | Light collector technologyconfirmation | Final confirmation of baseline light collector design | Milestone marking selection of final light collector system design
2.4.1.1.3 | Light collector pre-production review | Light collector pre-production review | Pre-production review of light collector system. Project and Consortium approval to place contracts and begin fabrication of PD light collector components
2.4.3.1.4 | Light collector production QC setup complete | MILESTONE-- Light collector QA/QC approved | Milestone marking Light collector QC plan and hardware approved
2.4.1.1.5 | Light collector production start | MILESTONE-- Module production begins | Milestone marking beginning of light collector construction
2.4.1.1.6 | Light collector first article delivered | MILESTONE-- First module delivery | Milestone marking delivery of the first PD modules to the integration site
2.4.1.1.7 | Light collector final article delivered | MILESTONE-- Final module delivery | Milestone marking delivery of the final PD modules to the integration site
2.4.1.2 | Photosensor WG Project Management | Photosensor reviews and milestones | Reviews and scheduling milestones for photosensor designs, components and cold board assemblies
2.4.1.2.1 | Photosensor pre-production review | Pre-production review of photosensors, mounting PCBs | Pre-production review of Photosensor. Project/consortium approval to place procurement contracts and begin testing of photosensors and assembly of cold PCBs
2.4.1.2.2 | Contracts placed for purchasing of production photosensors | MILESTONE-- Purchase contract let | Milestone marking completion on major procurement contracts for photosensors
2.4.1.2.3 | Photosensor production QC test station complete | MILESTONE-- QA plan and equipment complete | Milestone marking completion of the QC plan and testing equipment for photosensors
2.4.1.2.4 | Photosensor first article delivered | MILESTONE-- First photosensor PCBs delivered | Milestone marking delivery of first tested/assembled SiPM mounting cold boards to PD assembly site
2.4.1.2.5 | Photosensor final article delivered | MILESTONE-- Final photosensor PCBs delivered | Milestone marking delivery of final tested/assembled SiPM mounting cold boards to PD assembly site
2.4.1.3 | Electronics/Cables/Calibration WG Project Management | Electronics, cables, monitoring reviews and milestones | Reviews and scheduling milestones for electronics/cabling/calibration designs and components
2.4.1.3.1 | Electronics/cables pre-production review | Electronics, cables, pre-production review | Pre-production review of electronics, and cables. Project/consortium approval to place procurement contracts and begin assembly and testing of electronics and cables. This line includes all PD electronics, cables and power supplies, inside and outside the cryostat.
2.4.1.3.2 | Electronics /cables QC test station complete | MILESTONE-- QA plan and equipment complete | Milestone marking completion of QC plan and testing equipment
2.4.1.3.3 | Electronics/cables production start | MILESTONE-- Electronics/cabling production begin | Milestone marking beginning of electronics/cabling production
2.4.1.3.4 | Electronics/cables first article delivered | MILESTONE-- Electronics/cabling first delivery | Milestone marking delivery of first electronics/cabling
2.4.1.3.5 | Electronics/cables final article delivered | MILESTONE-- Electronics/cabling final delivery | Milestone marking delivery of final electronics/cabling
2.4.1.3.6 | Calibration/monitoring pre-production review | Calibration/monitoring pre-production review | Pre-production review of calibration/monitoring system. Project/consortium approval to place procurement contracts and begin assembly and testing calibration/monitoring system
2.4.1.3.7 | Calibration/monitoring QC test station complete | MILESTONE-- QA plan and equipment complete | Milestone marking completion of the calibration/monitoring system QC plan and equipment
2.4.1.3.8 | Calibration/monitoring production start | MILESTONE-- Monitoring system production begin | Milestone marking calibration/monitoring system fabrication beginning
2.4.1.3.9 | Calibration/monitoring first article delivered | MILESTONE-- Monitoring system first delivery | Milestone marling first item delivery of calibration/monitoring system components
2.4.1.3.10 | Calibration/monitoring final article delivered | MILESTONE-- Monitoring system final delivery | Milestone marling final item delivery of calibration/monitoring system components
2.4.1.4 | Integration WG Project Management | Integration and installation reviews and milestones | reviews and scheduling milestones for PD integration tasks. These tasks include integration planning and supervision both within the PD group (between the PD working groups, for example light collectors and photosensors) and between the PD consortium and other consortia (such as between the PD and the APA consortia for example. All inter-consortium interfaces would be supervised in this fashion). This section is also responsible for materials certification in LAr, and overall project safety.
2.4.1.4.1 | Photon system /APA/CPA/CE Integration Review | Photon detector/APA/CPA/CE Integration Review | Project management review of PD/APA/CPA/CE integration plans
2.4.1.4.2 | Photon System integration plan/tooling review | Photon detector integration tooling review | Project management review of PD/cabling integration plan Includes review of pre and post-integration testing, cabling, and integration tooling
2.4.1.4.3 | Photon system installation plan/tooling review | Photon detector installation plan review | Project management review of PD installation cabling plan into FD. Includes cabling and testing plans.
2.4.1.4.4 | Photon system/APA Integration start | MILESTONE-- Photon detector integration begins | Milestone marking beginning of integration of PD cables and modules into APA assemblies
2.4.1.4.5 | Photon system/APA Integration finished | MILESTONE-- Photon detector integration end | Milestone marking ind of integration of PD cables and modules into APA assemblies
2.4.1.4.6 | Photon system Installation (SURF) Start | MILESTONE-- Photon Detector installation begins | Milestone marking the beginning of PD installation/cabling into the 10KT detector
2.4.1.4.7 | Photon system Installation (SURF) Stop | MILESTONE-- Photon detector installation ends | Milestone marking the completion of PD installation/cabling into the 10KT detector
2.4.1.5 | Software and Physics WG Project Management | Software and physics reviews and milestones | Reviews and schedule milestones regarding software development and physics simulation
2.4.1.5.1 | Integrated Simulation framework complete | MILESTONE-- Simulation Framework Complete | Milestone marking completion of the simulation framework for integrating the PD into the DUNE FD
2.4.1.5.2 | Integrated Reconstruction framework complete | MILESTONE-- Reconstruction framework complete | Milestone marking completion of the physics reconstruction framework for integrating the PD into the DUNE FD reconstruction package
2.4.1.5.3 | Simulation/Reconstruction framework review | Review of simulation/reconstruction framework | Project management review of PD simulation and reconstruction frameworks
2.4.1.5.4 | Online Monitoring Suite complete | MILESTONE-- Online monitoring suite complete | Milestone marking completion of the online monitoring suite providing slow control and monitoring feedback of PD performance during operation
2.4.1.5.5 | Online monitoring review | DAQ/Management review of online monitoring suite | Project management review of online monitoring suite
2.4.1.5.5 | Online Database project complete | MILESTONE-- Online database complete | Milestone marking completion of the online database for the PD system. Database will allow for access to production QC records as well as records of previous online monitoring data for tracking PD performance during operation
2.4.1.5.6 | Project database review | DAQ/Management review of online database | Project management review of online database
2.4.2 | Physics and Simulations
2.4.2.1 | Light Collector WG Physics/Simulations | Simulations and performance requirements of light collectors
2.4.2.1.1 | Photon Detector Part of Final Geometry | Final photon detector geometry in detector simulation | Add the light collectors, with final dimensions, to the as-built simulated geometry.
2.4.2.2 | Photo Sensor WG Physics/Simulations | Simulations and performance requirements of light collectors
2.4.2.2.1 | Photosensor response parameterization or simulation | Parametric simulation of photosensors | Define the simulation of the photosensor responses to single photoelectrons or as a function of photoelectrons collected.
2.4.2.3 | Electronics/Cables/Calibration WG Physics/Simulations | Simulations and performance requirements of elect/cabling
2.4.2.3.1 | Electronics, DAQ, Trigger Simulation | Simulations of PD electronics in DAQ/triggering | Simulate the behavior of electronics/DAQ/trigger strategy. Iterate with simulation to optimize performance.
2.4.2.3.2 | Trigger/filter Development | Developement of algorithms for triggering/event filtering | Strategies for mitigating total data rate from the photon detection system.
2.4.2.4 | Integration WG Physics/Simulations | Incorporation of integration/installation data into sim
2.4.2.4.1 | Photon Detector Positions and Channel Map in Final Geometry | Photon detector positions and channel mapping in sim | Place photon detectors in their final positions, and with their correct channel numbers, as in the as-built geometry.
2.4.2.4.2 | Collection of relevant QC/QA data into database | Integration of PD QC/QA data into project database | Integration WG is responsible to collect relevant data with other PDS-WGs from QC/QA components to feed database
2.4.2.5 | Software and Physics WG Physics/Simulations | Photon detector system physics/simulation studies
2.4.2.5.1 | Simulation | Photon detector simulation studies | Offline simulation of the photon detector system
2.4.2.5.1.1 | Simulation of Light Formation in LAr | Simulation of Light Formation in LAr | Simulate the generation of light in liquid Argon.
2.4.2.5.1.2 | Validate Material and Optical Properties | Validate Material and Optical Properties | Collect the optical properties (e.g. scattering length) of liquid argon and reflectivity of detector materials, input to simulation.
2.4.2.5.1.3 | Integrate Light Collector, Sensor, Electronics/Trigger with LAr light simulation | Integrate PD system with LAr light simulation | Develop integrated simulation as part of DUNE simulation incorporating design and algorithm for detector response developed in the light collector, sensor, electronics, and integration groups.
2.4.2.5.2 | Reconstruction | Event reconstruction studies with PD system
2.4.2.5.2.1 | Reconstruct light and associate with the TPC | Develop tools to reconstruct light and link to TPC tracks | Reconstruct optical signals and associate them with reconstructed objects in the TPC. This is what sets position and time resolution.
2.4.2.5.2.2 | Calorimetry with Light | Develop tools to perform light-based calorimetry | Use the total amount of light collected to reconstruct particle energies.
2.4.2.5.2.3 | Study PID with Pulse Shape Discrimination | Develop tools toperform PID with light signals | Use the relative amount of early and late light for particle identification.
2.4.2.5.3 | Online Software | Develop online software tools for PD system | Software which runs on the operating detector
2.4.2.5.3.1 | Online Monitoring | Develop online monitoring tools | Monitor behavior of optical detecturs while running
2.4.2.5.3.2 | Slow Controls | Develop slow control tools | Software for controlling and monitoring photosensors in the detector.
2.4.2.5.3.3 | Stable Data Running Mode | Develop stable data running mode | Develop run mode for normal data taking.
2.4.2.5.3.4 | Calibration Running Mode | Develop running mode for PD monitoring/calibration | Develop run mode for taking calibration data.
2.4.2.5.4 | Databases | Integrate PD system with DUNE online database
2.4.2.5.4.1 | Calibration Database | Integrate PD calibration/monitoring with DUNE calibration database | Database to hold calibration constants for use by the reconstruction.
2.4.2.5.4.2 | Hardware Database | Integrate PD hardware QC/QA with DUNE hardware database | Database to track QC measurements of components. Should contain any measured optical properties of photosensors for access by offline simulation and reconstruction.
2.4.3 | Design, Engineering and R&D
2.4.3.1 | Light Collector WG Design, Engineering and R&D | Final light collector pre-production engineering, testing and verification
2.4.3.1.1 | Light Collector Module Design | Final modifications to light collector design based on pre-prod review | Light collector modules collect VUV LAr scintillation light, shift the incident 128nm light to a wavelength detectable by our photosensors (SiPMs-- ~ 400 to 500nm sensitive range), and gather the light onto the active area of the SiPMs.
2.4.3.1.1.1 | X-ARAPUCA- Design | Final pre-production modifications fab. drawings X-ARAPUCA design | ARAPUCA-Conceptual Design Production Module
2.4.3.1.1.2 | X-ARAPUCA-Engineering Design | Final engineering verification of X-ARAPUCA design | ARAPUCA-Engineering Drawings and Calculations for Production Module
2.4.3.1.1.3 | ARAPUCA-Materials Testing/Verification | Final materials testing/verification for X-ARAPUCA design | ARAPUCA-Materials Selection for Production Module
2.4.3.1.1.4 | ARAPUCA-Final Development Prototypes | Final pre-production PD modules (PD module 0) | ARAPUCA-Prototypes Necessary for Final Comparison. Assume 30 full-scale prototypes for final testing plan
2.4.3.1.2 | Final Production Preparation | Testing of final prototypes and system engineering
2.4.3.1.2.1 | Testing of PD Module Prototypes | Final pre-production prototype testing | Final Cryogenic Tests of Prototype PD Modules
2.4.3.1.2.2 | Final system configuration design | Final design/engineering PD/PA/CPA/CE Interfaces | Final design/engineering PD/PA/CPA/CE Interfaces
2.4.3.1.2.3 | Final Engineering Design | Generation of final engineering reports, fabrication drawings | Final Engineering for Selected PD Configuration (Pre-Fabrication), including engineering reports and production drawings, prior to pre-production review
2.4.3.2 | Photo Sensor WG Design, Engineering and R&D | Final photo sensor pre-production engineering, testing and verification | Light collected in the photon collector modules is converted to electrical signals using Geiger-mode silicon photodiodes, variously knows as SiPMs or MPPCs. Photosensor candidates must be evaluated based on many operational parameters, including cryogenic performance, photon detection efficiency, and single-PE detection capability. In addition, many SiPMs will be ganged onto a single readout channel to save cost and decrease cable plant size. This section captures photosensor evaluation, mounting PCB and ganging studies. Boards for ganging studies will be produced under 2.4.3.3.3
2.4.3.2.1 | Evaluation, Qualification, and Selection of Photosensors | Final selection of photosensors | Appraisal of photosensors and their packaging from different vendors for use in Lar
2.4.3.2.2 | Tested Array and Ganging Configuration | Final verification of actively ganged photosensors | Evaluation of ganging including active (cold amplification) and passive schemes. .
2.4.3.2.3 | Cold Board Design and Prototyping | Final verification of passively ganged photosensor mounting PCB | Design and fabrication of cold board incorporating mechanical and electrical constraints/features
2.4.3.2.4 | Tested Photosensor assemblies | Final verification of assembled photosensor mounting board | Testing and evaluation of cold board with mounted photosensors
2.4.3.2.5 | Preliminary negotiations with sensor vendors | Begin negotiations with photosensor vendors | Initial Discussions towards production procurement
2.4.3.2.6 | QA/QC Plan | Finalize photosensor QC/QA plan based of prototype tests | Plan for quality control and assurance of production sample
2.4.3.3 | Electronics/Cables/Calibration WG Design, Engineering and R&D | Final Electronics/cables/calibration pre-production engineering, testing and verification | Testing of baseline designs for PDS readout electronics and cable plans (including cryostat penetration) will be analyzed and modifications will be made as required to meet PD performance requirements. Final prototype SiPM mounting and ganging circuitry (active and/or passive SiPM ganging) will be fabricated under this line. Powr supplies and grounding schemes will also be finalized. The PDS calibration/monitoring system will also be designed and final prototypes produced and evaluated.
2.4.3.3.1 | Readout Electronics Design | Final modifications to warm readout electronics design | Final pre-productions revisions/modifications to readout electronics
2.4.3.3.3 | Photon Detector Cable Selection/Validation | Final testing/verification of photon detector cables
2.4.3.3.3.1 | Cold Signal Cable Selection/Validation | Final verification of cold cables (nside and outside APA) | Final selection/validation of cold signal readout cables/connectors
2.4.3.3.3.3 | Warm signal cable Selection/Validation | Final verificatin of warm (outside cryostat) cables | Final selection/validation of warm signal readout cables/connectors
2.4.3.3.4 | Photon Detector Power Supply Selection/Validation | Final selection and verification of DC powr supplies for warm electronics
2.4.3.3.4.1 | Non-bias voltage power supply Selection/Validation | Selection and verification of lov-voltage front-end electronics supplies | Final selection/validation of production non-bias power supplies
2.4.3.3.5 | Grounding scheme for PD electronics/cables/power supplies | Final design and validation of PD system grounding plan | Coordination with pd integration group, DUNE grounding and APA/DAQ to develop grounding plan
2.4.3.3.6 | PDS Monitoning/Calibration System | Final selection and verification of LED flasher monitoring system
2.4.3.3.6.1 | Pre-production monitoring design | Final design and engineering of monitoring system | Design of PD monitoring (calibration?) system
2.4.3.3.6.2 | Monitoring system Materials Selection | Monitoring system materials verification | Final selection and certification of materials for monitoring system
2.4.3.3.6.3 | Monitoring system Prototyping | Final pre-production prototype fabrication and testing | Final pre-production prototyping of monitoring system.
2.4.3.3.7 | Signal cable feedthru selection/validation | Final engineering design, and prototype verification of PD signal feedthrough | Signal cable feedthrough for cryostat flange
2.4.3.4 | Integration WG Design, Engineering and R&D | Final Integration/Installation pre-production engineering, testing and verification | Final integration planning for Photon detectors, including supervision of inter-consortia integration planning, Supervision and collection of materials certification for Lar/hygene requirements, Oversight of cable routing and support designs (inside and outside cryostat), cryostat feedthrough flange, and pre-integration and pre-cryostat installation QC facilities
2.4.3.4.1 | System Engineering | Final design verification of PD system engineering | System engineering specific to PD integration
2.4.3.4.1.1 | Development of QA Plan (specification of tests/facilities) | Development of QA Plan (specification of tests/facilities) | QA plan developed (determination of specs for tests and associated facilities)
2.4.3.4.1.1.1 | Material Selection/Characterization | Material Selection/Characterization | Program for material selection and characterization
2.4.3.4.1.1.2 | Aging tests for material coatings | Aging tests for material coatings | Progam for aging tests of coatings
2.4.3.4.1.1.3 | Aging tests for photosensorss | Aging tests for photosensorss | Program for aging tests of photosensors
2.4.3.4.2 | External Interface Specifications (with other subsystems) | Final specification of system interface documents | Develop specifications of all interfaces with external subsystems
2.4.3.4.3 | Internal Interface Specifications (within PDS subsystem) | Final cross-check of internal PD subsystem interfaces | Develop specifications of all interfaces with PDS subsystems
2.4.3.4.4 | Development of QC Plans (for all components) | Final QC plan and verification | Develop quality control program for all PDS components
2.4.3.4.5 | Develop Cable Routing Plan | Final verification and interface drawings for cable routing plan | Deliver cable routing plan (Inside and outside cryostat)
2.4.3.4.6 | Design Cable Support Structures | Final fabrication drawings and engineering for cable supports | Design and specify cable tray and strain relief elements inside and outside cryostat
2.4.3.4.7 | Finalize Installation Plan | Develop PD installation plan | Develop PD installation plan
2.4.3.4.9 | Finalize Plan for connecting cables to feedthroughs | Plan for Cable-feedthrough connections, installation handling | Provide plan for Cable-feedthrough connections, installation handling requirements
2.4.3.4.10 | Design Pre-Integration QC test Facility | Design of pre-integration test facility | Design of pre-integration test facility
2.4.3.4.11 | Design Pre-Installation QC test Facility | Design of pre-installation test facility | Design of pre-installation test facility
2.4.4 | Production Setup
2.4.4.1 | Light Collector WG Production Setup | Production tooling and QC equipment for X-ARAPUCA fabrication | Planning and producing assembly tooling for PD light collector production. Assumes a target production and testing rate of approximately 20 PD modules per week (average over 18 months)
2.4.4.1.1 | Light collector fabrication tooling | Tooling to fabricate light collector frames and optical filters/coatings
2.4.4.1.1.1 | Incoming QC Equipment | Incoming QC test equipment for mechanical components | Test equipment (go-nogo gauges, pin gauges, etc.) requires to perform incoming material inspectinos and certify material compliance.
2.4.4.1.1.2 | Optical components/coating. | Equipment to fabricate.coat optical filters/reflectors | Optical coating and test equipment for coating filter plates and
2.4.4.1.1.3 | Module Assembly Mechanical Assembly Tooling | Tooling to align and position PD compontnes during assembly | Design and Fabrication of Tooling required for module assembly hardware. Assume 4 module assembly stations, based on ProtoDUNE experience
2.4.4.1.2 | Post-Assembly Test Stand Development | Optical scanner and cryogenic test facilities for post-assembly testing. | Post-Assembly Test Stand for 10kt PD Modules. Used to QC test all PD modules immediately following fabrication, Includes 2 scanners and approptiate go-nogo test stations
2.4.4.2 | Photo Sensor WG Production Setup | Procurement planning and test stand for incoming photosensor QC/QA | Planning and producing assembly tooling for PD photosensor production. Assumes a target production and testing rate of approximately 20 PD modules per week (average over 18 months) Actual throughput of testing facilities will be determined once PD designs finalized
2.4.4.2.1 | SiPM Procurement | Photosensor procurement process | Preparations for procurement of photosensors for the DUNE PDS
2.4.4.2.1.1 | Specification of devices and terms of purchase | Specification of devices and terms of purchase | Agreement with vendor on device specification and terms of delivery
2.4.4.2.1.2 | Generation of a Purchase Order | Generation of a Purchase Order | Generation of purchase requisition
2.4.4.2.2 | SiPM Test Stand(s) Development | SiPM Test Stand(s) Development | Development of test stand(s) for the production photosensors
2.4.4.2.2.1 | SiPM Warm Test Stand(s) Development | Warm test stands for incoming and post-mounting photosensor tests | Development of test stand(s) for testing photosensors at room temperatures. Modification/Duplicate of NIU test stand. Includes "Waffle pack" storage
2.4.4.2.2.2 | SiPM Cold Test Stand(s) Development | Cryogenic test stands for post-mounting photosensor tests | Development of test stand(s) for testing photosensors at cryogenic temperatures (Modification/Duplicate of CSU test stand)
2.4.4.3 | Electronics/Cables/Calibration WG Production Setup | Test stands and fabrication stations for electronics/cabling/monitoring | Planning and producing assembly tooling for PD electronics/cables/monitoring production. Assumes a target production and testing rate of approximately 20 PD modules per week (average over 18 months), and cable harnesses. Also includes power supplies (bias voltage and non bias voltage supplies)
2.4.4.3.1 | Design/Fabricate readout Electronics Test Stand | Test stand for QC testing warm front end readout electronics | Design and fabricate test stand to allow for QA/QC measurements on front end readout boards and FEB controllers
2.4.4.3.2 | Design/fabricate cold active ganging test stand | Test stand for QC testing of cold active ganging circuits | Design and fabricate test stand (cryogenic and warm) for testing assembled SiPM mounting/ganging PCBs
2.4.4.3.3 | Design/fabricate Photon Detector Cable test stand | Test stand for post-assembly continuity checks of assembled PD cables | Design and fabricate a test stend (cryogenic) for testing PD cables (bias and signal, 22 configurations) for use inside cryostat, as well as a warm test stand for external cables
2.4.4.3.4 | Photon Detector Power Supply test stations | Test stations for validation of DC power supplies
2.4.4.3.4.1 | Non-bias voltage power supply test station | Test station for non-bias low voltage DC power supplies | Design and fabricate test stand to allow for QA measurements on non-bias power supplies
2.4.4.3.5 | PDS Monitoning/Calibration test station | Test station for monitoring system diffusers and optical fibers | Design and fabricate test stand to allow for QA measurements on calibration/monitoring system components
2.4.4.3.6 | Signal cable feedthru Test Station | Test station for post-assembly vacuum and electrical feedthrough tests | Design and fabricate test stand to allow for QA measurements on assembled cryostat flange units
2.4.4.4 | Integration WG Production Setup | Integration WG Production Setup | This section covers development and fabrication of test stands for PD modules before integration into the APA frames and integrated PDs prior to installation in the cryostat. This testing will be informed by the ProtoDUNE effort, and will consist of warm scanning of each module using a movable light source in a device similar to that used in ProtoDUNE prior to installation, cryogenic operational testing in a gasseous cold box immediately following integration into the APA (at the integration facility), and electrical testing of the SiPMs and cables immediately prior to installation into the cryostat. Also included are in-situ continuity checking equipment for cable installation into the APA frames.
2.4.4.4.1 | Fabrication of pre-integration QC test Facility | QC test equipment for integration including scanner, continuity | Construction of pre-integration test facility(s).
2.4.4.4.2 | Fabrication of pre-installation QC test Facility | QC test equipment for installation including continuity, operational readout system | Construction of pre-integration test facility(s).
2.4.5 | Production
2.4.5.1 | Light Collector WG Production | Production and QC testing of PD modules | PD light collector production. Assumes a target production and testing rate of approximately 20 PD modules per week (average over 18 months)
2.4.5.1.1 | Light collector module Production Fabrication Components | Fabrication of PD module components | Based on July-2018 ARAPUCA concept. Single-sided light collectin on external APA frames (100 APAs, 1000 modules), double-sided readout of central APAs (50 APAs, 500 modules)
2.4.5.1.1.1 | Module Assembly Components (Mechanical) | Fabrication/procurement of frame and electrical routing components | Mechanical components for ARAPUCA module fabrication. Based on ProtoDUNE experience and primarily supported by vendor estimates
2.4.5.1.1.2 | Optical components (Filters, coatings) | Fabrication/procurement of optical components (filters, reflectors, WLS bars) | Dichroic filters, Vikuiti, coatings
2.4.5.1.1.3 | PD module assembly | Assmebly of PD modules | Assembly of ARAPUCA modules (assume approx. 20/week) Assume 10 person-hours per module. Based on module assembly experience gained during ProtoDUNE
2.4.5.1.2 | APA-PD Interface hardware/Cabling | Fabrication/procurement/assembly of APA-PD interface hardware | Hardware for PD Installation into APA Frame, including cabling
2.4.5.1.3 | Post-Assembly Testing | Post-assembly QC testing of PD modules
2.4.5.1.3.1 | Post-Assembly Testing – Scanner Response | Scanning of completed PD modules in LED scanner | Post-Assembly Testing of Response to UV Illumination. Assume 1/2 hour per module, 1 technician and one student, plus supervision.
2.4.5.1.3.2 | Post-Assembly Testing – Cryogenic Stability | Cryogenic immersion and operation of completed PD modules | Post-Assembly Testing of Stability in LN2. Assume 1500 modules, 8 modules per test, $500 LN2 per test, 4 hours per test (1 student, one technician,+ supervision)
2.4.5.1.4 | Production Shipping | Shipping of PD modules from assembly site to integration facility | Shipping of PD Modules to Pre-Installation Storage Facility & Req'd Facility
2.4.5.2 | Photosensor WG Production | Photosensor procurement, assembly to PCBs, testing | PD photosensor production. Assumes a target production and testing rate of approximately 20 PD modules per week (average over 18 months) Actual thruput of testing facilities will be determined once PD designs finalized. This task includes photosensor testing, mounting board fabrication and testing, mounting board assembly and testing (along with active ganging circuitry where appropriate), and QC testing of completed assemblies
2.4.5.2.1 | Procure SiPMs | Procure SiPMs from vendor(s) | Place purchase order, receive SiPMs. Assume Hamamatsu MPPC (S13360-6050CQ-SMD, $21/MPPC), 192 per module, 1500 modules
2.4.5.2.2 | SiPM Testing | SiPM incoming testing | Testing of production photosensors
2.4.5.2.2.1 | Specification of testing procedures and parameters | Specification of testing procedures and parameters | Elucidation of procedures and parameters to be measured
2.4.5.2.2.2 | Warm testing of SiPMs | Warm testing of SiPMs Prior to mounting) | Room temperature testing of photosensors (unmounted). Assume 3 minutes per photosensor, student labor. Assume EDIA and faculty supervision
2.4.5.2.2.3 | Warm testing of cold board | Warm testing of photosensors mounted to cold board | Testing of ganged and mounted photosensors at room temperature.
2.4.5.2.2.4 | Cold testing of cold board | Cryogenic testing of assembled cold boards | Cryogenic testing of ganged and mounted photosensors.
2.4.5.2.2.5 | Testing Documentation and QC Database | Documentation of testing results in QC database | Bookeeping associated with the testing. Assume 0.5 hours per module EDIA, plus faculty supervision
2.4.5.2.3 | Cold Board Production | Fabrication of passive-ganging cold photosensor mounting boards | Production of board which will interface to the collectors and be immersed in Lar
2.4.5.2.3.1 | Cold Board Fabrication | Procurement of cold passive/ganging PCBs | Fabrication of board by commercial vendor. Assume 32 boards/module, 1500 modules, $5.01/board
2.4.5.2.3.3 | Cold Board Testing | Pre-assembly testing of cold passive/ganging PCBs | Incoming QC tests of the cold board
2.4.5.2.3.4 | Mounting of SiPMs on Cold Board | Mounting of photosensors on cold board | Soldering of SiPMs to cold board
2.4.5.3 | Electronics/Cables/Calibration WG Production | Fabrication/procurement of electronics/cabling/calibration system | Assembly of PD electronics/cables/monitoring production. Assumes a target production and testing rate of approximately 20 PD modules per week (average over 18 months), and cable harnesses. Also includes power supplies (bias voltage and non bias voltage supplies)
2.4.5.3.1 | Readout Electronics | Fabrication and testing of warn readout electronics
2.4.5.3.1.1 | Readout Electronics Fabrication | Procurement and fabrication of warm readout electronics | Fabrication of front-end readout electronics. Based on Mu2e electronics. 4 channels per ARAPUCA module, 40 channels per APA (1 front end board (FEB) per APA, $2,208 per FEB). Assume 1 FEB controller module per 6 FEBs (1 row of APAs in DUNE, $2,000/FEB controller board).
2.4.5.3.1.2 | Readout Electronics Testing | Post-assembly testing of warm readout electronics | testing of front-end readout electronics. Assume 4 hours testing per FEB, 4 hours testing per controller module
2.4.5.3.2 | Photosensor Cold Active Ganging | Fabrication and testing of cold photosensor active ganging circuits
2.4.5.3.2.1 | Photosensor Cold Active Ganging Fabrication | Procurement and fabrication of cold photosensor active ganging circuits | Based on FNAL (Cancelo) active ganging circuit. Assume 2 active ganging boards per module, 1500 modules, $25 per board. Assume boards supplied stuffed from vendor.
2.4.5.3.2.2 | Photosensor Cold Active Ganging testing | Post assembly testing of cold photosensor active ganging circuits | Assume 3000 active ganging boatds, 20 minutes per board (student tech), plus supervision,
2.4.3.3.3 | Photon Detector Cable Fabrication/testing | Fabrication and testing of PD cables
2.4.5.3.3.1 | Cold Signal/Bias Cable | Fabrication and testing of PD cryogenic signal/bias cables
2.4.5.3.3.1.1 | Cold Signal/Bias Cable Fabrication | Procurement and fabrication of PD cryogenic signal/bias cables | Fabrication of cold signal/bias cables (10 configurations for 75 upper APAs, 11 configurations for 75 lower APAs). Uses ProtoDUNE connector/cable combination. Cables pre-mounted in APA frames (prior to wire wrapping) Based on vendor estimates, engineering estimates for labor.
2.4.5.3.3.1.2 | Cold Signal Cable Testing | Testing of assembled PD cryogenic signal/bias cables | Testing of cold signal cables.
2.4.5.3.3.3 | Warm signal cable | Fabrication and testing of PD warm (outside cryostat) signal/bias cables
2.4.5.3.3.3.1 | Warm signal cable Fabrication | Procurement and fabrication of PD warm signal/bias cables | Fabrication of warm signal/bias cables (one configuration). Uses ProtoDUNE connector/cable combination. Based on vendor estimates, engineering estimates for labor.
2.4.5.3.3.3.2 | Warm signal cable Testing | Testing of assembled PD warm signal/bias cables | Testing of warm signal cables (1 configuration for 150 APAs).
2.4.5.3.4 | Photon Detector Power Supply Procurement/Testing | Photon Detector Power Supply Procurement/Testing
2.4.5.3.4.1 | Non-bias voltage power supply | Procurement and testing of low-voltage DC power supplies
2.4.5.3.4.1.1 | Non-bias voltage power supply Procurement | Procurement of low-voltage DC power supplies | Procure non-bias voltage power supplies for 150 APAs (Cold active ganging). Assume 75 power supplies. Based on Mouser Electronics catalog
2.4.5.3.4.1.2 | Non-bias voltage power supply testing | Testing of low-voltage DC power supplies | Test non-bias voltage power supplies (75 supplies). Assume 1 hour per supply
2.4.5.3.5 | Grounding Materials PD electronics/cables/power supplies Procurement | Procurement of grounding supplies/materials for PD grounding | Procure/fabricate grounding materials for 150 APAs
2.4.5.3.6 | PDS Monitoning/Calibration System | Procurement and testing of PD monitoring/calibration system
2.4.5.3.6.1 | Monitoring system procurement/Fabrication | Procurement and fabrication of PD monitoring system | Procure monitoring/calibration system (optical fibers, diffusers, LED drivers) for 1 10kt detector
2.4.5.3.6.2 | Monitoring systemTesting | Testing of PD monitoring system | test monitoring/calibration system (optical fibers, diffusers, LED drivers) for 1 10kt detector
2.4.5.3.7 | Signal cable feedthrough | Procurement, fabrication and testing of cryogenic feedthrough plate
2.4.5.3.7.1 | Signal cable feedthrough Fabrication/Procurement | Signal cable feedthrough Fabrication/Procurement | Procure signal cable feedthrough flange.
2.4.5.3.7.2 | Signal cable feedthrough testing | Signal cable feedthrough testing | Test signal cable feedthrough flanges.
2.4.6 | Integration (Integration Test Facility)
2.4.6.1 | Light Collector WG Integration (Global Integration Facility) | Will capture any PD module fabrication work at ITF | Intentionally left blank for possible later details
2.4.6.2 | Photo Sensor WG Integration (Global Integration Facility) | Will capture any Photosensor work at ITF | Intentionally left blank for possible later details
2.4.6.3 | Electronics/Cables/Calibration WG Integration (Global Integration Facility) | Will capture any electronics/cabling/monitoring work at ITF | Intentionally left blank for possible later details
2.4.6.4 | Integration WG Integration (Global Integration Facility)
2.4.6.4.1 | Operation of pre-integration QC test facility | Personel to operate test facility at ITF | Testing of components and PD modules
2.4.6.4.2 | Personel for PD integrtion into APAs | Dedicated PD labor for integrating components and PD modules | Dedicated PD labor for integrating components and PD modules
2.4.6.4.3 | Test photon detectors/cables on APAs (Integration Facility?) | Dedicated PD labor for post-integration testing at ITF | PDs tested in cold test facility prior to installation into FD SP cryostat
2.4.7 | Installation (Activity at SURF)
2.4.7.1 | Light Collector WG Installation (Activity at SURF) | Will capture any PD module fabrication work at SURF | Intentionally left blank for possible later details
2.4.7.2 | Photo Sensor WG Installation (Activity at SURF) | Will capture any PD module fabrication work at SURF | Intentionally left blank for possible later details
2.4.7.3 | Electronics/Cables/Calibration WG Installation (Activity at SURF) | Will capture any PD module fabrication work at SURF | Intentionally left blank for possible later details
2.4.7.4 | Integration WG Installation (Activity at SURF)
2.4.7.4.1 | Pre-APA Installation | Specialized labor for pre-installation photon detector QC checkout | Final Pre-installation
2.4.7.4.2 | Connect cryostat flange cables | Specialized labor for pre-installation photon detector cabling/continuity checks | Make connection of cables to flanges (warm/cold)
2.4.7.4.3 | Initial Operation/qualification of PD system | Specialized labor for post-installation PD test operation and checkout | Operation and Commissioning of PD system after installation?
2.4.7.4.4 | Analysis of PDS Performance | Specialized abor for analysis of PD test operation and checkout | Initial checkout of completely Installed PD system (prior to handoff)
2.4.7.5 | Software and Physics WG Installation (Activity at SURF) | Specialized labor for final inclusion of PD location mapping and QC data in DUNE database | Intentionally left blank for possible later details

## Cost Book Rollup
NOTE: ESTIMATES ARE NOT FINAL AND VETTED. FOR DISCUSSION ONLY!
WBS | WBS Element Name | M&S | Engineer | Designer | Tech | Student Tech | Grad-Student | Post-Doc | Faculty/Staff
2.4.1 | Project Management (Milestones, Reviews) | 0 | 220 | 0 | 0 | 0 | 880 | 880 | 880
2.4.2 | Physics and Simulations | 0 | 1960 | 0 | 0 | 0 | 0 | 2260 | 0
2.4.3 | Design, Engineering and R&D
2.4.3.1 | Light Collectors Design and Engineering | 185000 | 3040 | 0 | 1440 | 1120 | 0 | 0 | 880
2.4.3.2 | Photo Sensors Design and Engineering
2.4.3.3 | Electronics, Cabling and Monitoring Design and Engineering
2.4.3.4 | Integration and Installation Test Hardware design and Engineering
2.4.4 | Production Setup
2.4.4.1 | Light Collectors Production Setup | 275000 | 640 | 0 | 800 | 880 | 0 | 0 | 160
2.4.4.2 | Photo Sensors Production Setup
2.4.4.3 | Electronics, Cabling and Monitoring Production Setup
2.4.4.4 | Integration and Installation Test Hardware Production Setup
2.4.5 | Production
2.4.5.1 | Light Collector Production | 4312853 | 1960 | 0 | 20000 | 1775 | 0 | 150 | 680
2.4.5.2 | Photo Sensors Production
2.4.5.3 | Electronics, Cabling and Monitoring Production
2.4.6 | DUNE FD Integration
2.4.7 | DUNE FD Installation

## Management Cost Book Detail
NOTE: ESTIMATES ARE NOT FINAL AND VETTED. FOR DISCUSSION ONLY!
Quality of estimate table (M&S)
1 (Best) | Vendor quote of previously-tested and certified component
2 | Vendor quote of designed but untested component. Vendor estimate of tested and certified component
3 | Vendor estimate of untested/certified component. Professional estimate of well-understood component
4 | Professional estimate of conceptual designed component. Generalist estimate of final design item
5 | Generalist estimate of conceptually-designedtask
Quality of estimate table (Labor)
1 (Best) | Time and motion study with final DUNE Design
2 | DUNE Prototype time studies (Ash River, etc.)
3 | Estimate based on similar ProtoDUNE or early prototype task
4 | Professional estimate of conceptual designed task. Generalist estimate of final design task
5 | Generalist estimate of conceptually-designed task
Basis of estimate: Management estimate of required review preparation time based on ProtoDUNE/DUNE Experience
|  |  | M&S | Quality of Estimate (M&S) | Engineer | Designer | Tech | Student Tech | Grad Student | Post-Doc | Faculty/Staff | Quality of Estimate (Labor)
2.4.1 | Project Management (Milestones, Reviews) |  | 0 |  | 220 | 0 | 0 | 0 | 880 | 880 | 880
2.4.1.1 | Light collector WG Project Management | Reviews and scheduling milestones for light collector designs, components and modules |  |  | 40 |  |  |  | 160 | 160 | 160
2.4.1.1.1 | Final light collector technology review | Review of light collector designs for performance against PD requirements, cost effectiveness, and risk. |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.1.2 | Light collector technologyconfirmation | Milestone marking selection of final light collector system design
2.4.1.1.3 | Light collector pre-production review | Pre-production review of light collector system. Project and Consortium approval to place contracts and begin fabrication of PD light collector components |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.3.1.4 | Light collector production QC setup complete | Milestone marking ight collector QC plan and hardware approved
2.4.1.1.5 | Light collector production start | Milestone marking beginning of light collector construction
2.4.1.1.6 | Light collector first article delivered | Milestone marking delivery of the first PD modules to the integration site
2.4.1.1.7 | Light collector final article delivered | Milestone marking delivery of the final PD modules to the integration site
2.4.1.2 | Photosensor WG Project Management | Reviews and scheduling milestones for photosensor designs, components and cold board assemblies |  |  | 20 |  |  |  | 80 | 80 | 80
2.4.1.2.1 | Photosensor pre-production review | Pre-production review of Photosensor. Project/consortium approval to place procurement contracts and begin testing of photosensors and assembly of cold PCBs |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.2.2 | Contracts placed for purchasing of production photosensors | Milestone marking completion on major procurement contracts for photosensors
2.4.1.2.3 | Photosensor production QC test station complete | Milestone marking completion of the QC plan and testing equipment for photosensors
2.4.1.2.4 | Photosensor first article delivered | Milestone marking delivery of first tested/assembled SiPM mounting cold boards to PD assembly site
2.4.1.2.5 | Photosensor final article delivered | Milestone marking delivery of final tested/assembled SiPM mounting cold boards to PD assembly site
2.4.1.3 | Electronics/Cables/Calibration WG Project Management | Reviews and scheduling milestones for electronics/cabling/calibration designs and components |  |  | 40 |  |  |  | 160 | 160 | 160
2.4.1.3.1 | Electronics/cables pre-production review | Pre-production review of electronics, and cables. Project/consortium approval to place procurement contracts and begin assembly and testing of electronics and cables. This line includes all PD electronics, cables and power supplies, inside and outside the cryostat. |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.3.2 | Electronics /cables QC test station complete | Milestone marking completion of QC plan and testing equipment
2.4.1.3.3 | Electronics/cables production start | Milestone marking beginning of electronics/cabling production
2.4.1.3.4 | Electronics/cables first article delivered | Milestone marking delivery of first electronics/cabling
2.4.1.3.5 | Electronics/cables final article delivered | Milestone marking delivery of final electronics/cabling
2.4.1.3.6 | Calibration/monitoring pre-production review | Pre-production review of calibration/monitoring system. Project/consortium approval to place procurement contracts and begin assembly and testing calibration/monitoring system |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.3.7 | Calibration/monitoring QC test station complete | Milestone marking completion of the calibration/monitoring system QC plan and equipment
2.4.1.3.8 | Calibration/monitoring production start | Milestone marking calibration/monitoring system fabrication beginning
2.4.1.3.9 | Calibration/monitoring first article delivered | Milestone marling first item delivery of calibration/monitoring system components
2.4.1.3.10 | Calibration/monitoring final article delivered | Milestone marling final item delivery of calibration/monitoring system components
2.4.1.4 | Integration WG Project Management | reviews and scheduling milestones for PD integration tasks. These tasks include integration planning and supervision both within the PD group (between the PD working groups, for example light collectors and photosensors) and between the PD consortium and other consortia (such as between the PD and the APA consortia for example. All inter-consortium interfaces would be supervised in this fashion). This section is also responsible for materials certification in LAr, and overall project safety. |  |  | 60 |  |  |  | 240 | 240 | 240
2.4.1.4.1 | Photon system /APA/CPA/CE Integration Review | Project management review of PD/APA/CPA/CE integration plans |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.4.2 | Photon System integration plan/tooling review | Project management review of PD/cabling integration plan Includes review of pre and post-integration testing, cabling, and integration tooling |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.4.3 | Photon system installation plan/tooling review | Project management review of PD installation cabling plan into FD. Includes cabling and testing plans. |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.4.4 | Photon system/APA Integration start | Milestone marking beginning of integration of PD cables and modules into APA assemblies
2.4.1.4.5 | Photon system/APA Integration finished | Milestone marking ind of integration of PD cables and modules into APA assemblies
2.4.1.4.6 | Photon system Installation (SURF) Start | Milestone marking the beginning of PD installation/cabling into the 10KT detector
2.4.1.4.7 | Photon system Installation (SURF) Stop | Milestone marking the completion of PD installation/cabling into the 10KT detector
2.4.1.5 | Software and Physics WG Project Management | Reviews and schedule milestones regarding software development and physics simulation |  |  | 60 |  |  |  | 240 | 240 | 240
2.4.1.5.1 | Integrated Simulation framework complete | Milestone marking completion of the simulation framework for integrating the PD into the DUNE FD
2.4.1.5.2 | Integrated Reconstruction framework complete | Milestone marking completion of the physics reconstruction framework for integrating the PD into the DUNE FD reconstruction package
2.4.1.5.3 | Simulation/Reconstruction framework review | Project management review of PD simulation and reconstruction frameworks |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.5.4 | Online Monitoring Suite complete | Milestone marking completion of the online monitoring suite providing slow control and monitoring feedback of PD performance during operation
2.4.1.5.5 | Online monitoring review | Project management review of online monitoring suite |  |  | 20 |  |  |  | 80 | 80 | 80 | 3
2.4.1.5.5 | Online Database project complete | Milestone marking completion of the online database for the PD system. Database will allow for access to production QC records as well as records of previous online monitoring data for tracking PD performance during operation
2.4.1.5.6 | Project database review | Project management review of online database |  |  | 20 |  |  |  | 80 | 80 | 80 | 3

## Phys & Sim Cost Book Detail
NOTE: ESTIMATES ARE NOT FINAL AND VETTED. FOR DISCUSSION ONLY!
Quality of estimate table
1 (Best) | Vendor quote of previously-tested and certified component
2 | Vendor quote of designed but untested component. Vendor estimate of tested and certified component
3 | Vendor estimate of untested/certified component. Professional estimate of well-understood component
4 | Professional estimate of conceptual designed component. Generalist estimate of final design item
5 | Generalist estimate of conceptually-designed item
Quality of estimate table (Labor)
1 (Best) | Time and motion study with final DUNE Design
2 | DUNE Prototype time studies (Ash River, etc.)
3 | Estimate based on similar ProtoDUNE or early prototype task
4 | Professional estimate of conceptual designed task. Generalist estimate of final design task
5 | Generalist estimate of conceptually-designed item
Baasis of estimate: Physicist estimate of required development time based on NoVA Experience
|  |  | M&S | Quality of Estimate (M&S) | Engineer | Designer | Tech | Student | Grad Student | Post-Doc | Faculty/Staff | Quality of Estimate (Labor)
2.4.2 | Physics and Simulations |  | 0 |  | 1960 |  | 0 | 0 | 0 | 2260 | 0
2.4.2.1 | Light Collector WG Physics/Simulations |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.2.1.1 | Photon Detector Part of Final Geometry | Add the light collectors, with final dimensions, to the as-built simulated geometry. | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Not Yet Estimated
2.4.2.2 | Photo Sensor WG Physics/Simulations |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.2.2.1 | Photosensor response parameterization or simulation | Define the simulation of the photosensor responses to single photoelectrons or as a function of photoelectrons collected. | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Not Yet Estimated
2.4.2.3 | Electronics/Cables/Calibration WG Physics/Simulations |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.2.3.1 | Electronics, DAQ, Trigger Simulation | Simulate the behavior of electronics/DAQ/trigger strategy. Iterate with simulation to optimize performance. | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Not Yet Estimated
2.4.2.3.2 | Trigger/filter Development | Strategies for mitigating total data rate from the photon detection system. | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Not Yet Estimated
2.4.2.4 | Integration WG Physics/Simulations |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.2.4.1 | Photon Detector Positions and Channel Map in Final Geometry | Place photon detectors in their final positions, and with their correct channel numbers, as in the as-built geometry. | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Not Yet Estimated
2.4.2.4.2 | Collection of relevant QC/QA data into database | Integration WG is responsible to collect relevant data with other PDS-WGs from QC/QA components to feed database | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Not Yet Estimated
2.4.2.5 | Software and Physics WG Physics/Simulations |  | 0 |  | 1960 |  | 0 | 0 | 0 | 2260 | 0
2.4.2.5.1 | Simulation | Offline simulation of the photon detector system | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.2.5.1.1 | Simulation of Light Formation in LAr | Simulate the generation of light in liquid Argon. | [9 empty] | Not Yet Estimated
2.4.2.5.1.2 | Validate Material and Optical Properties | Collect the optical properties (e.g. scattering length) of liquid argon and reflectivity of detector materials, input to simulation. | [9 empty] | Not Yet Estimated
2.4.2.5.1.3 | Integrate Light Collector, Sensor, Electronics/Trigger with LAr light simulation | Develop integrated simulation as part of DUNE simulation incorporating design and algorithm for detector response developed in the light collector, sensor, electronics, and integration groups. | [9 empty] | Not Yet Estimated
2.4.2.5.2 | Reconstruction |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.2.5.2.1 | Reconstruct light and associate with the TPC | Reconstruct optical signals and associate them with reconstructed objects in the TPC. This is what sets position and time resolution. | [9 empty] | Not Yet Estimated
2.4.2.5.2.2 | Calorimetry with Light | Use the total amount of light collected to reconstruct particle energies. | [9 empty] | Not Yet Estimated
2.4.2.5.2.3 | Study PID with Pulse Shape Discrimination | Use the relative amount of early and late light for particle identification. | [9 empty] | Not Yet Estimated
2.4.2.5.3 | Online Software | Software which runs on the operating detector | 0 |  | 1160 |  | 0 | 0 | 0 | 1060 | 0
2.4.2.5.3.1 | Online Monitoring | Monitor behavior of optical detecturs while running |  |  | 333 |  |  |  |  | 300 |  | 3
2.4.2.5.3.2 | Slow Controls | Software for controlling and monitoring photosensors in the detector. |  |  | 667 |  |  |  |  | 600 |  | 3
2.4.2.5.3.3 | Stable Data Running Mode | Develop run mode for normal data taking. |  |  | 80 |  |  |  |  | 80 |  | 3
2.4.2.5.3.4 | Calibration Running Mode | Develop run mode for taking calibration data. |  |  | 80 |  |  |  |  | 80 |  | 3
2.4.2.5.4 | Databases |  | 0 |  | 800 |  | 0 | 0 | 0 | 1200 | 0
2.4.2.5.4.1 | Calibration Database | Database to hold calibration constants for use by the reconstruction. |  |  | 400 |  |  |  |  | 600 |  | 3
2.4.2.5.4.2 | Hardware Database | Database to track QC measurements of components. Should contain any measured optical properties of photosensors for access by offline simulation and reconstruction. |  |  | 400 |  |  |  |  | 600 |  | 3

## Light Collector Cost Book Detai
NOTE: ESTIMATES ARE NOT FINAL AND VETTED. FOR DISCUSSION ONLY!
Quality of estimate table
1 (Best) | Vendor quote of previously-tested and certified component
2 | Vendor quote of designed but untested component. Vendor estimate of tested and certified component
3 | Vendor estimate of untested/certified component. Professional estimate of well-understood component
4 | Professional estimate of conceptual designed component. Generalist estimate of final design item
5 | Generalist estimate of conceptually-designed item
Quality of estimate table (Labor)
1 (Best) | Time and motion study with final DUNE Design
2 | DUNE Prototype time studies (Ash River, etc.)
3 | Estimate based on similar ProtoDUNE or early prototype task
4 | Professional estimate of conceptual designed task. Generalist estimate of final design task
5 | Generalist estimate of conceptually-designed item
LOOK FOR COMPLETE LIST OF BOE DOCUMENTS IN DOCDB XXXX. ITEMS IN GREEN ARE INCLUDED IN THE LOCAL "LIGHT COLLECTOR BOE" TAB
|  |  | M&S | Engineer | Designer | Tech | Student Tech | Grad Student | Post-Doc | Faculty/Staff
2.4.3.1 | Light Collector Design and Engineering |  | 185000 | 3040 |  | 1440 | 1120 |  |  | 880
|  |  | M&S | Mech Eng. | Tech | Student | Faculty
| 2.4.3.1.1 | Light Collector Module | 150000 | 1920 | 960 | 640 | 160
DESCRIPTION: Final post-TDR Light Collector Module Engineering, Design and Validation
Labor (person hours)
|  |  | Unit | Price/unit | No. req'd | No. Total | Total price | Method of Estimate | Estimate quality (M&S) | BOE |  | Mech. Engineer Support |  |  | Mech. Technician |  |  | Student |  |  | Faculty |  |  | Estimate Quality (Labor) | BOE (T & M Study)
[10 empty] | Click green entries for link to BOE Location |  | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours
| 2.4.3.1.1.1 | ARAPUCA- Design | [9 empty] | 480 | 1 | 480 | 240 | 1 | 240 | 160 | 1 | 160 | 40 | 1 | 40 | 3 | DocDB XXXX
| 2.4.3.1.1.2 | ARAPUCA-Engineering Design | [9 empty] | 480 | 1 | 480 | 240 | 1 | 240 | 160 | 1 | 160 | 40 | 1 | 40 | 3 | DocDB XXXX
| 2.4.3.1.1.3 | ARAPUCA-Materials Testing/Verification | Lot | 50000 | 1 | 1 | 50000 | EE | 4 | DocDB XXXX |  | 480 | 1 | 480 | 240 | 1 | 240 | 160 | 1 | 160 | 40 | 1 | 40 | 3 | DocDB XXXX
| 2.4.3.1.1.4 | ARAPUCA-Final Development Modeling | Lot | 100000 | 1 | 1 | 100000 | EE | 4 | DocDB XXXX |  | 480 | 1 | 480 | 240 | 1 | 240 | 160 | 1 | 160 | 40 | 1 | 40 | 3 | DocDB XXXX
| TOTALS | [5 empty] | 150000 | [6 empty] | 1920 |  |  | 960 |  |  | 640 |  |  | 160
|  |  | M&S | Mech Eng. | Tech | Student | Faculty
| 2.4.3.1.2 | Final Production Preparation | 35000 | 1120 | 480 | 480 | 720
DESCRIPTION: Final testing of pre-productino prototypes before pre-production review
Labor (person hours)
|  |  | Unit | Price/unit | No. req'd | No. Total | Total price | Method of Estimate | Estimate quality (M&S) | BOE |  | Mech. Engineer Support |  |  | Mech. Technician |  |  | Student |  |  | Faculty |  |  | Estimate Quality (Labor) | BOE (T & M Study)
[10 empty] | Click green entries for link to BOE Location |  | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours
| 2.4.3.1.2.1 | Testing of PD Module Prototypes | Lot | 35000 | 1 | 1 | 35000 | EE | 3 | DocDB XXXX |  | 320 | 1 | 320 | 320 | 1 | 320 | 320 | 1 | 320 | 200 | 1 | 200 | 4 | DocDB XXXX
| 2.4.3.1.2.2 | System Configuration Final Selection | [9 empty] | 320 | 1 | 320 |  | 1 | 0 |  | 1 | 0 | 320 | 1 | 320 | 4 | DocDB XXXX
| 2.4.3.1.2.3 | Final Engineering Design | [9 empty] | 480 | 1 | 480 | 160 | 1 | 160 | 160 | 1 | 160 | 200 | 1 | 200 | 4 | DocDB XXXX
| TOTALS | [5 empty] | 35000 | [6 empty] | 1120 |  |  | 480 |  |  | 480 |  |  | 720
|  |  | M&S | Engineer | Designer | Tech | Student Tech | Grad Student | Post-Doc | Faculty/Staff
2.4.4.1 | Light Collector Production Setup |  | 275000 | 640 | 0 | 800 | 880 | 0 | 0 | 160
|  |  | M&S | Mech Eng. | Tech | Student | Faculty
| 2.4.4.1.1 | Light collector fabrication tooling | 225000 | 560 | 640 | 560 | 140
DESCRIPTION: Tooling required for PD module fabrication and alignment
Labor (person hours)
|  |  | Unit | Price/unit | No. req'd | No. Total | Total price | Method of Estimate | Estimate quality (M&S) | BOE |  | Mech. Engineer Support |  |  | Mech. Technician |  |  | Student |  |  | Faculty |  |  | Estimate Quality (Labor) | BOE (T & M Study)
[10 empty] | Click green entries for link to BOE Location |  | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours
| 2.4.4.1.1.1 | Incoming QC Equipment | lot | 25000 | 1 | 1 | 25000 | EE | 3 | DocDB XXXX |  | 80 | 1 | 80 | 160 | 1 | 160 | 80 | 1 | 80 |  |  | 20 | 4 | DocDB XXXX
| 2.4.4.1.1.2 | Optical compontnt/coating. | lot | 150000 | 1 | 1 | 150000 | EE | 3 | DocDB XXXX |  | 320 | 1 | 320 | 320 | 1 | 320 | 320 | 1 | 320 |  |  | 80 | 4 | DocDB XXXX
| 2.4.4.1.1.3 | Module Assembly Mechanical Assembly Tooling | lot | 50000 | 1 | 1 | 50000 | EE | 3 | DocDB XXXX |  | 160 | 1 | 160 | 160 | 1 | 160 | 160 | 1 | 160 |  |  | 40 | 4 | DocDB XXXX
| TOTAL | [5 empty] | 225000 | [6 empty] | 560 |  |  | 640 |  |  | 560 |  |  | 140
|  |  | M&S | Mech Eng. | Tech | Student | Faculty
| 2.4.4.1.2 | Post-Assembly Test Stand Development | 50000 | 80 | 160 | 320 | 20
DESCRIPTION:
Labor (person hours)
|  |  | Unit | Price/unit | No. req'd | No. Total | Total price | Method of Estimate | Estimate quality (M&S) | BOE |  | Mech. Engineer Support |  |  | Mech. Technician |  |  | Student |  |  | Faculty |  |  | Estimate Quality (Labor) | BOE (T & M Study)
[10 empty] | Click green entries for link to BOE Location |  | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours
| 2.4.4.1.2 | Post-Assembly Test Stand Development | ea | 25000 | 2 | 2 | 50000 | EE | 3 | DocDB XXXX |  | 40 | 2 | 80 | 80 | 2 | 160 | 160 | 2 | 320 | 20 | 1 | 20 | 3 | DocDB XXXX
| TOTAL | [5 empty] | 50000 | [6 empty] | 80 |  |  | 160 |  |  | 320 |  |  | 20
|  |  | M&S | Engineer | Designer | Tech | Student | Grad Student | Post-Doc | Faculty/Staff
2.4.5.1 | Light Collector Production |  | 4312853 | 1960 | 0 | 20000 | 1775 | 0 | 150 | 680
|  |  | M&S | Mech Eng. | Mech. Tech. | Physicist
| 2.4.5.1.1 | Light collector module Production Fabrication Components | 4007048 | 975 | 16875 | 375
Description: Unit is per PD module. 10 PD modules per APA. Two module designs: Center APA PD monules collect light from both sides, Outer APA PD modules from only one side. There are 100 outer APAs (1000 PD modules) and 50 center APAs (500 PD modules)
| WBS | Description | No. req'd |  | No. req'd |  | Price/piece | Price/total | Method of Estimate | Estimate quality (M&S) | BOE | Labor (person hours)
|  |  | Per Center APA PD Module | Per Outer APA PD Module | Center APA PD Module 50 APAs | Outer APA PD Module 100 APAs |  |  |  |  | Click on green entries for link to BOE Location | Mech. Engineer Support |  |  | Mech. Technician |  |  | Physicist |  |  | Estimate Quality (Labor) | BOE (T & M Study)
[12 empty] | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours
|  | Module Count |  |  | 500 | 1000
| 2.4.5.1.1.1 | Module Assembly Components (Mechanical)
| 2.4.5.1.1.1.1 | Module End Block | 1 | 1 | 500 | 1000 | 11 | 16500 | VQ | 2 | DocDB XXXX
| 2.4.5.1.1.1.2 | Mid-Supercell Joining Bar | 2 | 2 | 1000 | 2000 | 6.4 | 19200 | VQ | 2 | DocDB XXXX
| 2.4.5.1.1.1.3 | Mid-Module Support Plate | 1 | 1 | 500 | 1000 | 24.75 | 37125 | VQ | 2 | DocDB XXXX
| 2.4.5.1.1.1.4 | Module End Block | 1 | 1 | 500 | 1000 | 11 | 16500 | VQ | 2 | DocDB XXXX
| 2.4.5.1.1.1.5 | ARAPUCA Side Readout Strip | 8 | 8 | 4000 | 8000 | 30 | 360000 | EE | 2 | Side Readout PCB
| 2.4.5.1.1.1.6 | Supercell Filter Alignment Plate | 8 | 4 | 4000 | 4000 | 30.65 | 245200 | VQ | 2 | Filter Alignment Plate
| 2.4.5.1.1.1.7 | Filter Cover Plate | 8 | 4 | 4000 | 4000 | 2.21 | 17680 | VQ | 2 | DocDB XXXX
| 2.4.5.1.1.1.8 | Supercell backing plate | 0 | 4 | 0 | 4000 | 25 | 100000 | EE | 2 | DocDB XXXX
| 2.4.5.1.1.1.9 | Supercell side rail | 8 | 8 | 4000 | 8000 | 21.25 | 255000 | VQ | 2 | SuperCell Side Rail
| 2.4.5.1.1.1.10 | Connector Pin PCB | 1 | 1 | 500 | 1000 | 7.5 | 11250 | EE | 2 | DocDB XXXX | 0.05 | 1500 | 75 | 0.25 | 1500 | 375 |  |  |  | 3 | DocDB XXXX
| 2.4.5.1.1.1.11 | Connector Pin (Mil-max 6955-0-05-15-…) | 10 | 10 | 5000 | 10000 | 0.2 | 3029 | Digi-Key | 2 | DocDB XXXX
| 2.4.5.1.1.1.12 | M3 X 6mm FHMS (SS-304 | 136 | 136 | 68000 | 136000 | 0.04 | 8364 | McMaster | 2 | DocDB XXXX
| 2.4.5.1.1.1.13 | M3 X 6mm PHMS (SS-304) | 128 | 128 | 64000 | 128000 | 0.05 | 9600 | McMaster | 2 | DocDB XXXX
| 2.4.5.1.1.1.14 | M4 X 15mm SHCS (SS-304, captive screw) | 2 | 2 | 1000 | 2000 | 1 | 3000 | EE | 2 | DocDB XXXX
| 2.4.5.1.1.2 | Optical components
| 2.4.5.1.1.2.1 | Dichroic Filter Plate | 48 | 24 | 24000 | 24000 | 30 | 1440000 | VE | 3 | Dichroic Filter Plate
| 2.4.5.1.1.2.2 | PTP Coating (filter plate) | 48 | 24 | 24000 | 24000 | 5 | 240000 | PE | 4 | PTP Coating
| 2.4.5.1.1.2.3 | Wavelength Shifting Plates | 4 | 4 | 2000 | 4000 | 129.5 | 777000 | VE | 3 | WLS Plate VQ
2.4.5.1.1.2.4
| 2.4.5.1.1.2.5 | Vikuiti Side Reflectors (100mm) | 48 | 48 | 24000 | 48000 | 2 | 144000 | VE | 2 | DocDB XXXX
| 2.4.5.1.1.2.6 | Vikuiti Side reflectors (78mm) | 48 | 48 | 24000 | 48000 | 2 | 144000 | VE | 2 | DocDB XXXX
| 2.4.5.1.1.2.7 | Vikuiti Rear reflectors | 0 | 24 | 0 | 24000 | 6.65 | 159600 | VE | 2 | DocDB XXXX
| 2.4.5.1.1.3 | Assembly
| 2.4.5.1.1.3.1 | Module Assembly | [9 empty] | 0.25 | 1500 | 375 | 8 | 1500 | 12000 | 0.1 | 1500 | 150 | 3 | DocDB XXXX
| 2.4.5.1.1.3.2 | Pre-assembly QC | [9 empty] | 0.1 | 1500 | 150 | 1 | 1500 | 1500 | 0.05 | 1500 | 75 | 3 | DocDB XXXX
| 2.4.5.1.1.3.3 | Post-assembly QC | [9 empty] | 0.25 | 1500 | 375 | 2 | 1500 | 3000 | 0.1 | 1500 | 150 | 3 | DocDB XXXX
|  | Totals | [5 empty] | 4007048 | [5 empty] | 975 |  |  | 16875 |  |  | 375
|  |  | M&S | Mech. E | Tech | Post-Doc
| 2.4.5.1.2 | APA-PD Interface hardware/Cabling | 133305 | 300 | 1350 | 150
DESCRIPTION: Mounting rails, mounting rail support brackets, electrical connectors to connect PD modules to wire harness, PD cable strain relief brackets inside APA. Unit is per APA Frame, 150 frames
Labor (person hours)
|  | No. APAs | 150 | [8 empty] | Mech. Engineer Support |  |  | Mech. Technician |  |  | Post Doc |  |  | Estimate Quality (Labor) | BOE (T & M Study)
[12 empty] | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours
|  | Description | Unit | Price/unit | No. req'd/APA | No. Total | Total price | Method of Estimate | Estimate quality (M&S) | BOE
Click green entries for link to BOE Location
| 2.4.5.1.2.1 | PDS C-Channel | ea | 21.5 | 20 | 3000 | 64500 | VE | 3 | DocDB XXXX
| 2.4.5.1.2.2 | PDS Angle Mount | ea | 2.67 | 60 | 9000 | 24030 | VE | 3 | DocDB XXXX
| 2.4.5.1.2.3 | PD Mount Plate | ea | 7.05 | 10 | 1500 | 10575 | VE | 3 | DocDB XXXX
| 2.4.5.1.2.4 | Connector PCB | ea | 10 | 10 | 1500 | 15000 | VE | 3 | DocDB XXXX
| 2.4.5.1.2.5 | Connector sockets | ea | 0.53 | 100 | 15000 | 7950 | VE | 3 | DocDB XXXX
| 2.4.5.1.2.6 | Cable Strain Relief | ea | 1.5 | 50 | 7500 | 11250 | VE | 3 | DocDB XXXX
| 2.4.5.1.2.7 | PD Mount System Installation Labor | [9 empty] | 0.5 | 150 | 75 | 2 | 150 | 300 | 0.25 | 150 | 37.5 | 4 | DocDB XXXX
| 2.4.5.1.2.8 | PD Cable Installation (top APA, 20 cables) | [9 empty] | 1 | 150 | 150 | 4 | 150 | 600 | 0.5 | 150 | 75 | 4 | DocDB XXXX
| 2.4.5.1.2.9 | PD Cable Installation (Bottom APA, 10 cables) | [9 empty] | 0.5 | 150 | 75 | 3 | 150 | 450 | 0.25 | 150 | 37.5 | 4 | DocDB XXXX
|  | Total |  |  |  |  | 133305 | [6 empty] | 300 |  |  | 1350 |  |  | 150
|  |  | M&S | Mech Eng. | Tech | Student | Faculty
| 2.4.5.1.3 | Post-Assembly Testing | 60000 | 535 | 1625 | 1625 | 230
DESCRIPTION: QC testing pf PD modules following assembly, including cryogenic imersion and optical scanning. Unit is per PD module. 1,500 PD modules. Estimates based on ProtoDUNE Experience
| 2.4.5.1.3.1 | Post-Assembly Testing – Scanner Response | [9 empty] | Labor (person hours)
|  |  | Unit | Price/unit | No. req'd | No. Total | Total price | Method of Estimate | Estimate quality (M&S) | BOE |  | Mech. Engineer Support |  |  | Mech. Technician |  |  | Student |  |  | Faculty |  |  | Estimate Quality (Labor) | BOE (T & M Study)
[10 empty] | Click green entries for link to BOE Location |  | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours
| 2.4.5.1.3.1.1 | Load module into scanner | [12 empty] | 0.083333 | 1500 | 125 | 0.083333 | 1500 | 125 |  |  |  | 3 | DocDB XXXX
| 2.4.5.1.3.1.2 | Scan module | [12 empty] | 0.25 | 1500 | 375 | 0.25 | 1500 | 375 |  |  |  | 3 | DocDB XXXX
| 2.4.5.1.3.1.3 | Unload, pack module | [12 empty] | 0.16667 | 1500 | 250 | 0.16667 | 1500 | 250 |  |  |  | 3 | DocDB XXXX
| 2.4.5.1.3.1.4 | Supervision | [9 empty] | 375 | 1 | 375 | [6 empty] | 150 | 1 | 150 | 3 | DocDB XXXX
| 2.4.5.1.3.2 | Post-Assembly Testing – Cryogenic Stability
| 2.4.5.1.3.2.1 | Unpack and load module | [12 empty] | 0.083333 | 1500 | 125 | 0.083333 | 1500 | 125 |  |  |  | 3 | DocDB XXXX
| 2.4.5.1.3.2.2 | Test cycle (8 modules per test cycle) | [12 empty] | 2.6667 | 187.5 | 500 | 2.6667 | 187.5 | 500 |  |  |  | 3 | DocDB XXXX
| 2.4.5.1.3.2.3 | Unload and pack modules | [12 empty] | 0.16667 | 1500 | 250 | 0.16667 | 1500 | 250 |  |  |  | 3 | DocDB XXXX
| 2.4.5.1.3.2.4 | Supervision | [9 empty] | 375 | 1 | 160 | [6 empty] | 150 | 1 | 80 | 3 | DocDB XXXX
Description
| 2.4.5.1.3.2.5 | Testing Materials (LN2, 200 cycles) | Cryostat fill | 300 |  | 200 | 60000 | VE | 4 | DocDB XXXX
|  | Total |  |  |  |  | 60000 | [6 empty] | 535 |  |  | 1625 |  |  | 1625 |  |  | 230
|  |  | M&S | Mech. Eng. | Tech. | Student | Faculty
| 2.4.5.1.4 | Production Shipping | 112500 | 150 | 150 | 150 | 75
DEFINITION: Shipping modules from assembly facility to ITF. Assume 20 PD modules per shipment, 75 shipments.
Labor (person hours)
|  |  | M&S | [8 empty] | Mech. Engineer Support |  |  | Mech. Technician |  |  | Student |  |  | Faculty
|  | Description | Units | Price/unit | Total price |  |  | Method of Estimate | Estimate quality (M&S) | BOE |  | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Hrs/unit | Number | Total hours | Estimate Quality (Labor) | BOE (T & M Study)
Click green entries for link to BOE Location
|  | Crate Fabrication | 75 | 500 | 37500 |  |  | EE | 4 | DocDB XXXX |  |  |  |  | 1.5 | 75 | 112.5 | 1.5 | 75 | 112.5 |  |  |  | 4 | DocDB XXXX
|  | Packing, handling | [12 empty] | 0.5 | 75 | 37.5 | 0.5 | 75 | 37.5 |  |  |  | 4 | DocDB XXXX
|  | Shipping | 75 | 1000 | 75000 |  |  | EE | 4 | DocDB XXXX | [13 empty] | 4 | DocDB XXXX
|  | Supervision | [9 empty] | 1 | 150 | 150 | [6 empty] | 1 | 75 | 75 | 4 | DocDB XXXX
|  | TOTAL |  |  | 112500 | [8 empty] | 150 |  |  | 150 |  |  | 150 |  |  | 75

## Light Collector BOE
NOTE: QUOTES/ESTIMATES ARE NOT FINAL AND VETTED. FOR DISCUSSION ONLY!
WLS Plate VQ

## Integration and Installation
2.4.7.1 | Electronics, Cabling and Monitoring
2.4.7.2 | Post-Installation QA
2.4.7.3 | Post-Installation Detector Comissioning
2.4.6.1 | Light Collectors Integration
2.4.6.2 | Electronics, Cabling and Monitoring
2.4.6.3 | Post-Integration QA