{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Reviewer VE Opportunities List","Utility Sheet"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Reviewer VE Opportunities List","index":0,"n_rows":10,"n_cols":8,"rows_kept":10,"cut":false,"hidden":false,"merged":[[7,4,7,5]]}
[]
[]
["PIP-II Reviewer VE Opportunities List"]
[]
["Date:","2018-01-15"]
["Revision",1]
[]
[null,null,null,null,"Impacted Systems"]
["ID","Date","Title","Description","Level 2 Systems","Level 3/4 Systems","Comments","References"]
[1,"2018-01-22","Elminate HX for Cryo Compressors","The base design assumes that the cryo compressors have a cooling loop that is separated from the site wide industrial cooling water (ICW) by a heat exchanger.  This option would eliminate the closed loop cooling water system for the cryo compressors and instead flow ICW directly through the compressors. This saves the cost of the heat exchanger, pumps and related piping","121.02 SRF & Cryo\r\n121.06 Conv Fac.","121.06.03  CnvF - Cryoplant Building\r\n121.02.05  SRFs - Cryogenics Plant","Requires input from Cryoplant L3M  before finalizing (in process)","PIP-II-doc-155, PIP-II-doc-1025"]

{"sheet":"Utility Sheet","index":1,"n_rows":34,"n_cols":2,"rows_kept":34,"cut":false,"hidden":false,"merged":[]}
["Utility Sheet"]
[]
["L2 WBS","L3/L4 WBS"]
["121.01 Proj. Mgmnt","121.02.02 SRFs - Half Wave Resonator "]
["121.02 SRF & Cryo","121.02.03.02  SRFs - SSRs - SSR1"]
["121.03  Accel Sys","121.02.03.03  SRFs - SSRs - SSR2"]
["121.04  Linac Instal & Comm.","121.02.04.02 SRFs - 650MHz - Low Beta"]
["121.05 Accel Comp Upg.","121.02.04.03  SRFs - 650MHz - High Beta"]
["121.06 Conv Fac.","121.02.05  SRFs - Cryogenics Plant"]
[null,"121.02.06  SRFs - CDS"]
[null,"121.03.02 Accelerator Physics"]
[null,"121.03.03  AccS - HPRF-RFDist"]
[null,"121.03.04  AccS - LLRF"]
[null,"121.03.05  AccS - Magnets and PS"]
[null,"121.03.06  AccS - Vacuum"]
[null,"121.03.07.02 AccS - Cntrl - PIP2IT Controls"]
[null,"121.03.07.03 AccS - Cntrl - PIP-II Controls"]
[null,"121.03.08  AccS - Safety Systems"]
[null,"121.03.09.02 AccS - BI - for PIP2IT"]
[null,"121.03.09.03  AccS - BI -  for PIP-II"]
[null,"121.04.02  Inst - Warm Front End"]
[null,"121.04.03  Inst - Test Infrastructure"]
[null,"121.04.04  Inst - Building Infrastructure"]
[null,"121.04.05.05 Inst - LI - Linac Installation"]
[null,"121.04.06  Inst - Beam Commissioning "]
[null,"121.05.02  AccU - TLBA"]
[null,"121.05.03  AccU - Transferline Installation"]
[null,"121.05.04  AccU - Booster"]
[null,"121.05.05  AccU - MIRR"]
[null,"121.06.02 CnvF - Site Preparation"]
[null,"121.06.03  CnvF - Cryoplant Building"]
[null,"121.06.04  CnvF - Utility Plant Building"]
[null,"121.06.05  CnvF - Linac Complex"]
[null,"121.06.06  CnvF - Booster Connection"]