## Slide 1: DUNE and LBNF FS post EXC Installation Planning
Marzio Nessi
SURF
19 August 2019

## Slide 2: Our goal in the next 3 days:
Share with you our Far Site (FS) post CF organization plans
Discuss with some details the plans at the Far Site to arrive to the start of the detector installation
    Cavern handover definition
    BSI requirements
    Cryostat installation
    Cryogenics installation
    Surface storage
    Central organized manpower
Then we discuss the Detector installation scenario, including the requirements on the central SDSD and JPO teams. The requirements on the various consortia

## Slide 3: Work organization and actors

## Slide 4: Work organization and actors
At some point in time (T0):
- EXCavation of the North (N) and CUC caverns will be over
- EXCavation of the South (S) cavern will continue for 4-5 months
We would like at this point to define a transition of responsibilities between the contractor in charge of the excavation and FNAL (handover)
A new phase will open, with several new and old actors sharing the same space at least in the N-cavern
At this moment, all activities will be controlled and steered by a new organization (JPO)

## Slide 5: Highest level schedule protected by the EFIG (proposal in P6)

## Slide 6: BSI activities proposal

## Slide 7: Cryostats activities (1/2)

## Slide 8: Cryostats activities (2/2)

## Slide 9: Work organization and actors after handover

## Slide 10: Work organization and actors after handover
Project overall coordination
work force

## Slide 11: On the floor in situ
/ shift

## Slide 12: On the floor in situ
Installation managers
1 person per shift for N cavern
1 person per shift for S cavern
- overview all activities ongoing
- plans all transport and rigging activities
- prepare next days plans
- run daily planning meetings underground
- report to the overall JPO coordination

## Slide 13: On the floor in situ
20 general JPO technicians per cavern (N and S)
Covering many activities:
- Top of cryostat installation
- Technical support in the clean rooms
- Mechanical installation of the DSS, APA, CPA, Field cages inside the cryostat, ….
- Technical support to many activities in caverns and inside cryostats (cable trays, cabling, ….)

## Slide 14: SDSD division manpower (today 4 FTEs)
24/7 on call services
Electricians
3 FTEs
Ventilation
& Network
3 FTEs
Surface Shaft transport/rigging
6 FTEs (2 shifts)
Lower Shaft & Drift transport/rigging
6 FTEs (2 shifts)
Caverns transport/rigging
8 FTEs (2 shifts)
Transport / Riggers
Surface storage/transport/rigging
2 FTEs
Experts
Surveyors
2 FTEs
Welders (cryo) and cabling
3 FTEs
Safety officers
3 FTEs
Contracted manpower
Logistic services
Logistics management
1 FTE
Labs manpower

## Slide 15: What is now needed ?
A safety organization which prepares and overviews all safety files and installation procedures, before individual items are moved and installed underground
A PBS definition and marking of all items which will arrive to SD and will then be stored on surface or moved to the caverns
A DB system associated which links to each item ID his production, travel and safety history
A change request mechanism which allows or not changes to the baseline (schedule, layout, performance,..) once the baseline is defined

## Slide 16: What is now needed ?
A baseline definition related to an internal review system
    Final design reviews
    Readiness reviews
    Installation reviews
    Production follow up reviews
An agreed budget line for all activities in the various domains (LBNF, JPO, DUNE, common funds ….) with a strict follow up mechanism. We need to start exploring manpower sources.
A formal agreement with LBNF/CF on the definition of the caverns handover and the change of responsibility
A formal protection of the top level schedules and milestones

## Slide 17: Now lets go in steps to see where we are with the various activities preparation enjoy the next 3 days!