## Slide 1: Sequencing of handoff between FSCF EXC & BSI for Cryostat Installation
Jolie Macier
19 August 2019

## Slide 2: Outline
LBNF FSCF scope
  Pre-excavation
  Reliability work
  Excavation
  BSI
Handover to FS Integration team

## Slide 3: FSCF Pre-Excavation
Focused on establishing the necessary systems to facilitate major underground excavation.
Includes 28 bid packages, some self-performed by Kiewit Alberici Joint Venture (KAJV), others sub-subcontracted by KAJV.
Tramway Rehabilitation
Ross Shaft Utilities
Crusher Rehabilitation
Skip Loading System
Ore Pass Refurbishment
Excavation
New Substation and Site Electrical
Headframe Remediation & Modifications
Rock Conveyor Supply & Install
Ross Shaft & SURF Reliability Projects

## Slide 4: KAJV Self Performed Work
Tramway Rehabilitation
Surface Waste Rock Handling System
Ore Pass Rehabilitation & Reservoir
Ross shaft work at 5000L
Skip Loader & Spill Collection
Sub Anchors & Supports

## Slide 5: Pre Excavation – Sub Subcontracted Packages
Site Preparation, Surface Civil, General
Fencing
Environmental Abatement – Monitoring
Environmental Abatement – Execution
Structural Steel
Mechanical - Fire Protection
Electrical Systems
Communication Systems
Crusher System Refurbishment
Hoists & Overhead Cranes
Quality Control Services
Noise and Vibration Monitoring
Survey Services
Pre-Mobilization Survey
Security Services
Temp Craft Sanitary Services
General Dumpster & Trash Services
Snow Removal
Work
Service

## Slide 6: FSCF Pre-Excavation Construction
Tramway & Snowshed Progress (for proposed conveyor)

## Slide 7: FSCF Pre-Excavation Construction
Site Clearing for Conveyor

## Slide 8: FSCF Pre-Excavation Construction
Ore Pass Progress (about 50' down, 45% Complete)

## Slide 9: FSCF Pre-Excavation Construction
5000L Progress, reinforced sump slab

## Slide 10: FSCF Pre-Excavation Construction
Electrical Infrastructure @ Surface

## Slide 11: FSCF Pre-Excavation Construction
Ross Headframe Reinforcement

## Slide 12: FSCF Pre-Excavation Construction Crushers

## Slide 13: KAJV CPM, Update thru August 1, 2019

## Slide 14: FSCF - Reliability Projects
Ross Shaft Rehabilitation
Ross Cage is 100% designed, to be delivered in October 2019
Ross Skips are fabricated, delivery in August 2019
Oro Hondo Fan VFD, demo completed, new VFD installed in August, to be completed and commissioned by October 2019
Ross Hoist Drives, Brakes, and Clutches, preliminary design to be completed in August
Refuge Chamber materials delivered in August, to be completed by September 2019
Ross Hoist Bearings and Bushings, Fusion Babbitting work on first set
Ross Hoist motor rebuild has been advertised, proposals due end of August

## Slide 15: FSCF – Excavation
Status
  Subcontracting for EXC underway
      Pre-solicitation advertised in August
      Site Visit on September 10, 2019
      Bids due January 2020
Scope
  As shown in 100% EXC drawings and specifications
Sequence
  To be determined by successful bidder
  Award criteria weighted by quickest schedule

## Slide 16: Handoff to FS Integration
Minimum BSI requirements
  North Cavern floor complete & crane rail installed
  Temporary services:
    Lighting
    Ventilation
    Power
First activities
  Floor survey & leveling
  Crane installation
  Move steel for cryostat floor first
Shared occupancy for cryostat installation
Need fire protection provisions for cold membrane storage underground
Need final ventilation for cold membrane installation

## Slide 17: Summary
  FSCF work continues on all fronts: pre-excavation, reliability work, 1B->1A Early Works Packages
      NOC 40: Blast Doors, 4700L Ventilation Fan, Borehole Grouting
      NOC 50: 3650L Rehabilitation for Raise Bore Early Mobilization
      NOC 51: 4850L Advance Drift to Spray Chamber
  Subcontracting for EXC underway
  FSCF goal to turn-over North Cavern first