## Supported Target
*Potential to mitigate these risks by un-docking exchanger and moving horn closer to manipulators to reduce manipulator spec and operation risk (but accepting more crane operations and associated risks)
[5 empty] | Risk |  |  |  | Time
Target option | Operation | No. repeats | Risk description | Consequence | Consequence Rating 1-5 | Likelihood 1-5 | Risk rating | Mitigation Strategy | Time taken per operation (hrs) | Time taken per target exchange (hrs)
2.2m Supported Target | Either upstream or downstream operations | 15 | Operator view sub-optimal due to window view not serving both ends of horn equally well | Greater risk for each operation requiring manipulator work due to reduced visibility | 1 | 2 | 30 | Optimise window locations as far as possible, use of auxillary cameras | 0.025 | 0.375
| Exhanger installation into work cell | 3 | Damage to replacement equipment during exchanger handling and positioning | Manufacture new replacment exchanger/ target - delay to beam time schedule | 4 | 2 | 24 | Robust and defined exchanger handling procedures e.g. Utilising work cell rail systems to locate exchanger | 1 | 3
| Work cell shielding removal/ replacement | 3 | Damage to horn module with shielding blocks | Repaire horn/horn module - massive delay to beam schedule | 4 | 1 | 12 | Minimise no. of shielding removal and replacement operations. Have spares | 3 | 9
| Horn module location into work cell | 3 | Damage to horn components or replacement parts/ exchanger | Replace parts if exchangeable or replace horn - massive delay to beam schedule | 5 | 2 | 30 | Minimise no. of horn insertions into work cell. Have spares | 120 | 360
| Horn module removal and rotation | 2 | Damage to horn components or replacement parts/ exchanger | Scrap damaged parts and replace - massive delay to beam schedule | 3 | 1 | 6 | Minimise no. horn removals and rotations from work cell. Have spares | 72 | 144
| 2m target exchanger docking and aligning to horn module | 2 | Damaging exchanger or overloading horn by incorrect docking | Scrap damaged parts and replace - massive delay to beam schedule | 4 | 3 | 24 | Design robust interfaces and simple docking procedure, minimise no. docking operations required | 1 | 2
| Align exchange carriage with failed target | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Move carriage to failed target | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Secure failed target to exchanger | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25
| Disconnect target helium pipes | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Make fragile components remotely exchangeable* | 0.25 | 0.25
| Disconnect Hylen device | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Damaging Hylen device instrumentation wiring could render beam based alignment system redundant - effect on physics performance or affect beam schedule | 2 | 2 | 4 | Perform neccesary R&D to produce simple connection for Hylen device that can be reliably made with long reach manipulators* | 1 | 1
| Undo failed target bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.5 | 0.5
| Retract failed target on carriage | 1 | Bonding/sticking of replacement target to downstream support, radioactive debris | Either: target not possible to remove using existing infrastructure causing considerable delay, or scrappage of horn/target leading to massive delay | 5 | 3 | 15 | R&D programme to test interface possible? (catch tray for debris) | 0.25 | 0.25
| Align replacement target with horn bore | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Insert replacement target | 1 | Misalignment of exchanger and horn bore | Unable or difficult to install target due to misalignment, potential damage to replacement target. Either lead to delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.25 | 0.25
| Fasten target fixing bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.5 | 0.5
| Connect target helium pipes | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Potential to damage garlocks, remote replacement may be possible with moderate delay | 2 | 2 | 4 | Make fragile components remotely exchangeable* | 0.25 | 0.25
| Connect Hylen device instrumentation | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators - Potentially tricky procedure | Damage to target components requires a new replacement target - considerable delays. Damage to existing Hylen device infrastructure may lead to loss of beam based alignment and physics penalty or horn scrappage and massive delay | 2 | 2 | 4 | Perform neccesary R&D to produce simple connection for Hylen device that can be reliably made/broken with long reach manipulators* | 1 | 1
| Disconnect replacement target from exchanger | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target plate would make future removal difficult or impossible | 3 | 1 | 3 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25
| Retract target carriage | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Downstream support exchanger docking and alignment | 2 | Damaging exchanger or overloading horn by incorrect docking | Scrap damaged parts and replace - some delay to beam schedule | 2 | 1 | 4 | Not inherently as risky or demanding as a target exchanger (lower mass, angular alignment less critical) | 0.5 | 1
| Align exchange carriage with failed support | 1 | Misalignment of exchanger and horn bore | Difficulty in removing failed support | 1 | 1 | 1 | Low mass/alignment requirement means that exhanger/support could potentially be aligned manually with manipulators | 0.1 | 0.1
| Move carriage to failed support | 1 | Misalignment of exchanger and horn bore | Difficulty in removing failed support | 1 | 1 | 1 | Low mass/alignment requirement means that exhanger/support could potentially be aligned manually with manipulators | 0.1 | 0.1
| Secure failed support to carriage | 1 | Damage to fragile components with manipulators (e.g. spokes/cups/ceramic isolators/ stripping threads) | Minimal assuming components are to be disposed of anyway | 1 | 1 | 1 | Robust engineering design of connections | 0.25 | 0.25
| Undo support helium connectors | 1 | Damage to fragile components with manipulators (e.g. spokes/cups/ceramic isolators/ stripping threads) | Minimal assuming components are to be disposed of anyway | 1 | 1 | 1 | Robust engineering design of connections | 0.25 | 0.25
| Unlatch/unbolt support from mounting flange | 1 | Damage to fragile components with manipulators (e.g. spokes/cups/ceramic isolators/ stripping threads) | Minimal assuming components are to be disposed of anyway | 1 | 1 | 1 | Robust engineering design of connections | 0.25 | 0.25
| Retract failed support on carriage | 1 | Radioactive debris from failed support | work cell contamination | 1 | 2 | 2 | Catch tray on exchanger to avoid spreading of contaminated debris. | 0.1 | 0.1
| Align replacement support with horn bore | 1 | Misalignment of exchanger and horn bore | Difficulty in installing replacement support | 1 | 1 | 1 | Low mass/alignment requirement means that exhanger/support could potentially be aligned manually with manipulators | 0.1 | 0.1
| Locate replacement supports to mounting flange | 1 | Misalignment of exchanger and horn bore | Difficulty in installing replacement support | 3 | 1 | 3 | Low mass/alignment requirement means that exhanger/support could potentially be aligned manually with manipulators | 0.1 | 0.1
| Fasten/latch replacement support | 1 | Damage to fragile components with manipulators (e.g. spokes/cups/ceramic isolators/ stripping threads) | Damage to support components would require a new replacement support sytem - this would cause some delays | 3 | 3 | 9 | Robust engineering design of connections, have available spares | 0.25 | 0.25
| Replace support helium connections | 1 | Damage to fragile components with manipulators (e.g. spokes/cups/ceramic isolators/ stripping threads) | Damage to support components would require a new replacement support sytem - this would cause some delays | 3 | 3 | 9 | Robust engineering design of connections, have available spares | 0.25 | 0.25
| Disconnect replacement support from exchanger | 1 | Damage to fragile components with manipulators (e.g. spokes/cups/ceramic isolators/ stripping threads) | Damage to support components would require a new replacement support sytem - this would cause some delays | 3 | 3 | 9 | Robust engineering design of connections, have available spares | 0.25 | 0.25
| Retract support carriage | 1 | No obvious inherent risk |  | 1 | 1 | 1 |  | 0.1 | 0.1
| Total | 41 |  |  |  | Total | 238 |  | Total | 526.375

## Double Target
*Potential to reduce these risks by un-docking exchanger and moving horn closer to manipulators to reduce manipulator spec and operation risk (but accepting more crane operations and associated risks)
[5 empty] | Risk |  |  |  | Time
Target option | Operation | No. repeats | Risk description | Consequence | Consequence Rating 1-5 | Likelihood 1-5 | Risk rating | Mitigation Strategy | Time taken per operation (hrs) | Time taken per target exchange (hrs)
Double target | Either upstream or downstream operations | 14 | Operator view sub-optimal due to window view not serving both ends of horn equally well | Greater risk for each operation requiring manipulator work due to reduced visibility | 1 | 2 | 28 | Optimise window locations as far as possible, use of auxillary cameras | 0.025 | 0.35
| Exchanger installation into work cell | 2 | Damage to replacement equipment during exchanger handling and positioning | Manufacture new replacment exchanger/ target - delay to beam time schedule | 4 | 2 | 16 | Robust and defined exchanger handling procedures e.g. Utilising work cell rail systems to locate exchanger | 1 | 2
| Work cell shielding removal/ replacement | 2 | Damage to horn module with shielding blocks | Repair horn/horn module - massive delay to beam schedule | 4 | 1 | 8 | Minimise no. of shielding removal and replacement operations. Have spares | 3 | 6
| Horn module location into work cell | 2 | Damage to horn components/ replacement parts/ exchanger or a fit-for-operation already installed target | Replace parts if exchangeable or replace horn - massive delay to beam schedule | 5 | 4 | 40 | Minimise no. of horn insertions into work cell. Have spares | 120 | 240
| Horn module removal and rotation | 1 | Damage to horn components/ replacement parts/ exchanger or a fit-for-operation already installed target | Scrap damaged parts and replace - massive delay to beam schedule | 4 | 4 | 16 | Minimise no. horn removals and rotations from work cell. Have spares | 72 | 72
| 1m target exchanger docking and aligning to horn module | 1 | Damaging exchanger or overloading horn by incorrect docking | Scrap damaged parts and replace - massive delay to beam schedule | 4 | 2 | 8 | Design robust interfaces and simple docking procedure, minimise no. docking operations required | 1 | 1
| Align exchange carriage with failed target | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Move carriage to failed target | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Secure failed target to exchanger | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25
| Disconnect target helium pipes | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Make fragile components remotely exchangeable* | 0.25 | 0.25
| Disconnect Hylen device | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Damaging Hylen device instrumentation wiring could render beam based alignment system redundant - effect on physics performance or affect beam schedule | 2 | 1 | 2 | Perform neccesary R&D to produce simple connection for Hylen device that can be reliably made with long reach manipulators* | 1 | 1
| Undo failed target bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.5 | 0.5
| Retract failed target on carriage | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools
| Align replacement target with horn bore | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Insert replacement target | 1 | Misalignment of exchanger and horn bore | Unable or difficult to install target due to misalignment, potential damage to replacement target. Either lead to delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.25 | 0.25
| Fasten target fixing bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.5 | 0.5
| Connect target helium pipes | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Potential to damage garlocks, remote replacement may be possible with moderate delay | 2 | 2 | 4 | Make fragile components remotely exchangeable* | 0.25 | 0.25
| Connect Hylen device instrumentation | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators - Potentially tricky procedure | Damage to target components requires a new replacement target - considerable delays. Damage to existing Hylen device infrastructure may lead to loss of beam based alignment and physics penalty or horn scrappage and massive delay | 2 | 1 | 2 | Perform neccesary R&D to produce simple connection for Hylen device that can be reliably made/broken with long reach manipulators* | 1 | 1
| Disconnect replacement target from exchanger | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target plate would make future removal difficult or impossible | 3 | 1 | 3 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25
| Retract target carriage | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Downstream target exchanger docking and alignment | 1 | Damaging exchanger or overloading horn by incorrect docking | Scrap damaged parts and replace - massive delay to beam schedule | 4 | 2 | 8 | Design robust interfaces and simple docking procedure, minimise no. docking operations required | 0.5 | 0.5
| Align exchange carriage with failed target | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Move carriage to failed target | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Secure failed target to carriage | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25
| Undo target helium connectors | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Make fragile components remotely exchangeable where possible* | 0.25 | 0.25
| Undo failed target bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of connections | 0.25 | 0.25
| Retract failed target on carriage | 1 | Motor failure, Radioactive debris from failed target | Difficulty in target exchange, work cell contamination | 1 | 1 | 1 | Design in redundancy in linear stages, catch tray on exchanger to avoid spreading of contaminated debris. | 0.1 | 0.1
| Align replacement target with horn bore | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Insert replacement target | 1 | Misalignment of exchanger and horn bore | Unable or difficult to install target due to misalignment, potential damage to replacement target. Either lead to delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1
| Fasten target fixing bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25
| Connect target helium pipes | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, beam window, ceramic He isolators | Potential to damage helium connectors, remote replacement may be possible with moderate delay | 2 | 2 | 4 | Make fragile components remotely exchangeable where possible* | 0.25 | 0.25
| Disconnect replacement target from exchanger | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, beam window, ceramic He isolators | Damage to target components would require a new replacement target sytem - this would cause significant delays | 3 | 1 | 3 | Robust engineering design of connections, make fragile components remotely exchangeable where possible* | 0.25 | 0.25
| Retract target carriage | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 |  | 0.1 | 0.1
| Total | 35 |  |  |  | Total | 222 |  | Total | 328.6

## Cantilever Target
*Potential to mitigate these risks by un-docking exchanger and moving horn closer to manipulators to reduce manipulator spec and operation risk (but accepting more crane operations and associated risks)
[5 empty] | Risk |  |  |  | Time
Target option | Operation | No. repeats | Risk description | Consequence | Consequence Rating 1-5 | Likelihood 1-5 | Risk rating | Mitigation Strategy | Time taken per operation (hrs) | Time taken per target exchange (hrs) | Potential Delay (weeks) | DOE Cost ($K) | Probability % | Expected Delay (weeks) | Expected Cost ($K)
Cantilever target | Exhanger installation into work cell | 1 | Damage to replacement equipment during exchanger handling and positioning | Manufacture new replacment exchanger/ target - delay to beam time schedule | 4 | 2 | 8 | Robust and defined exchanger handling procedures e.g. Utilising work cell rail systems to locate exchanger | 1 | 1 | 16 | 0 | 1 | 0.16 | 0
| Work cell shielding removal/ replacement | 1 | Damage to horn module with shielding blocks | Repair horn/horn module - massive delay to beam schedule | 4 | 1 | 4 | Minimise no. of shielding removal and replacement operations | 3 | 3 | 78 | 2000 | 0.2 | 0.156 | 4
| Horn module location into work cell | 1 | Damage to horn components or replacement parts/ exchanger | Replace parts if exchangeable or replace horn - massive delay to beam schedule | 5 | 3 | 15 | Minimise no. of horn insertions into work cell | 120 | 120 | 52 | 500 | 0.5 | 0.26 | 2.5
| 1.5m target exchanger docking and aligning to horn module | 1 | Damaging exchanger or overloading horn by incorrect docking | Scrap damaged parts and replace - massive delay to beam schedule | 4 | 2 | 8 | Design robust interfaces and simple docking procedure, minimise no. docking operations required | 1 | 1 | 52 | 500 | 0.5 | 0.26 | 2.5
| Align exchange carriage with failed target | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1 | 2 | 0 | 1 | 0.02 | 0
| Move carriage to failed target | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1 | 0.5 | 0 | 1 | 0.005 | 0
| Secure failed target to exchanger | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25 | 0.5 | 0 | 2 | 0.01 | 0
| Disconnect target helium pipes | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Minimal assuming components are to be disposed with failed target and target can still be removed | 2 | 2 | 4 | Make fragile components remotely exchangeable* | 0.25 | 0.25 | 0.5 | 0 | 2 | 0.01 | 0
| Disconnect Hylen device | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Damaging Hylen device instrumentation wiring could render beam based alignment system redundant - effect on physics performance or affect beam schedule | 2 | 1 | 2 | Perform neccesary R&D to produce simple connection for Hylen device that can be reliably made with long reach manipulators* | 1 | 1 | 0.5 | 0 | 2 | 0.01 | 0
| Undo failed target bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.5 | 0.5 | 0.5 | 0 | 2 | 0.01 | 0
| Retract failed target on carriage | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.25 | 0.25 | 0.5 | 0 | 1 | 0.005 | 0
| Align replacement target with horn bore | 1 | Slide stops misaligned with target, motor or slide failure | Difficult or impossible to exchange target - modify/ fix exchanger causing delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1 | 2 | 0 | 1 | 0.02 | 0
| Insert replacement target | 1 | Misalignment of exchanger and horn bore | Unable or difficult to install target due to misalignment, potential damage to replacement target. Either lead to delays to beam schedule | 3 | 1 | 3 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.25 | 0.25 | 2 | 0 | 1 | 0.02 | 0
| Fasten target fixing bolts | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target support plate renders entire horn scrap - replace horn and potentially delay beam schedule | 5 | 2 | 10 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.5 | 0.5 | 52 | 500 | 2 | 1.04 | 10
| Connect target helium pipes | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Potential to damage garlocks, remote replacement may be possible with moderate delay | 2 | 2 | 4 | Make fragile components remotely exchangeable* | 0.25 | 0.25 | 10 | 0 | 3 | 0.3 | 0
| Connect Hylen device instrumentation | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators - Potentially tricky procedure | Damage to target components requires a new replacement target - considerable delays. Damage to existing Hylen device infrastructure may lead to loss of beam based alignment and physics penalty or horn scrappage and massive delay | 5 | 3 | 15 | Perform neccesary R&D to produce simple connection for Hylen device that can be reliably made/broken with long reach manipulators* | 1 | 1 | 52 | 500 | 1 | 0.52 | 5
| Disconnect replacement target from exchanger | 1 | Manipulators working at max. extent. Damage to fragile components - stripping threads, hylen device, beam window, ceramic He isolators | Stripping threads on target plate would make future removal difficult or impossible | 3 | 1 | 3 | Robust engineering design of remotely made bolted connections (thread inserts, material selection etc)* | 0.25 | 0.25 | 20 | 0 | 1 | 0.2 | 0
| Retract target carriage | 1 | Motor failure | Difficult to exchange target | 1 | 1 | 1 | Design in redundancy to slide mechanism i.e. operate linear stages with air tools | 0.1 | 0.1 | 1 | 0 | 1 | 0.01 | 0
| Total | 18 |  |  |  | Total | 99 |  | Total | 129.9 |  |  | Total | 3.016 | 24
[14 empty] | Weeks | 0

## Summary
Option | No. Operations | Replacement Time (Days) | Risk
1) 2.2m Supported Target | 41 | 21.9323 | 238
2) Double Target | 35 | 13.6917 | 222
3) Cantilever Target | 18 | 5.4125 | 99