## 4. Prel. & Final Design Rev.
Preliminary Design Review of Q1/Q3 CryoAssembly |  | May 22nd, 2018
Final Design Review of MQXFA Magnet
# | Recommendations | Code | Owner | Response | Status
1 | The project should proceed to the review for CD3b approval after successful test of the second prototype magnet and a mini technical review to assess the prototype’s results | FDR-1 | G. Ambrosio | Plans were adjusted according to this recommendation. Based on MQXFAP2 test results plans were further changed: we plan to test 3 pre-series magnets before asking CD-3 approval for magnet fabrication. | CLOSED
2 | Extend the risk assessment of the threshold functional specifications, to prepare for the possibility that they might not be met in the production stage, and anticipate risk mitigation strategies. | FDR-2 | G. Ambrosio | We prepared a document with all requirements and mitigation strategy for each requirement if not met during production (US-HiLumi-doc-1723). | CLOSED
3 | Approve current revisions of all documents before the CD3b/CD2. | FDR-4 | G. Ambrosio | All documents for CD-2/3b approved before the review. | CLOSED
4 | The committee recommends agreement with CERN on the complete scope of the project before CD-2. | PDR – Mag./Man. -01 | G. Apollinari | Scope described by the KPPs has been accepted by the CERN HL-LHC Project Leader: US-HiLumi-doc-1172 and US-HiLumi-doc-1175. After discussion with the AUP Federal project Director and Federal Program Manager, an all-encompassing AUP-CERN MOU describing all details of the agreement (parts exchange, financial compensation, etc.) will be prepared after CD-2. | CLOSED

## 24. CD-3c DR_4.19.16 (hidden)
CD-3c Director's Review | 2016-04-19
# | Recommendations | Actions/Response | Responsible Parties | Status

## 25. CD-3c DOE Review_6.17.16 (hidden)
CD-3c DOE Review | 2016-06-17
# | Recommendations | Actions/Response | Responsible Parties | Status