## Slide 1: PIP-II SRF Update

## Slide 2: Status
HWR CM was delivered to FNAL early AM August 16th.
  No apparent issues form transport
    Visually OK, BL vacuum unchanged, accelerometers show < 0.2G
Final integrated leak check before transport found a leak in the 50K thermal shield circuit
  ~1e-4 mBar-l/sec, sensitivity ~1e-7 mBar-l/sec
  Leak check is performed by evacuating insulating vacuum, and pressurizing (~1 atm) individual He ckts
  Given the upcoming lack of resources for HWR activity at ANL (loss of key personnel) it was decided to transport to FNAL for repair
Repair to thermal shield will be added to the already planned/understood CM completion of HWR expected at FNAL (due to transport considerations)

## Slide 3: Thermal Shield

## Slide 4: Thermal Shield

## Slide 5: Thermal Shield
Thermal shield assembly being lifted at Meyer Tool.
The vacuum vessel, magnetic shielding, and thermal shield (with inner/outer covering of MLI) was delivered to ANL as a completed unit/assembly.

## Slide 6: Thermal Shield – Leak Check History
leak checked at Meyer Tool at the end of fabrication (5/19/2015),
leak check at ANL upon receipt of the cryomodule from Meyer Tool (8/6/2015),
leak check at ANL prior to transport from BLDG 366 to 203 for the engineering cool-down (1/19/2016),
leak check at ANL after transport from BLDG 366 to 203 for the engineering cool-down (2/2016),
leak check at ANL during the engineering cool-down with the 50 K circuit at 77K (2/20/2016),
leak check at ANL after transport from BLDG 203 back to 366 after engineering cool-down (4/6/2016),
8/14/2019 leak check at ANL which found a 1.4 e -7 mbar-l/s leak in the cryomodule lower vacuum vessel 50 K circuit.

## Slide 7: HWR Repair and Completion Plan
We were already planning on performing a number of activities related to completion of the HWR CM, as a result of removing or postponing installation of components for transport.
We add to this repair (identification/localization then repair) of the thermal shield process piping.
Work activities structured in 5 Phases (some in parallel)
  Phase I – Post transport checks
  Phase II – Prepare for thermal shield repair
  Phase IIIa/b – Thermal shield repair (offsite/onsite options)
  Phase IV – Post-repair assembly & transport
  Phase V – Final assembly at PIP2IT
  Phase VI – ORC preparations

## Slide 8: Tentative HWR Repair and Completion Schedule
Phase I – Post transport checks
  8/19/19 – 8/28/19
Phase II – Prepare for thermal shield repair
  8/21/2019 – 9/5/2019
Phase IIIa/b – Thermal shield repair (offsite/onsite options)
  IIIa : 9/5/2019 – 10/8/2019
  IIIb : 8/26/19 – 10/11/19
Phase IV – Post-repair assembly & transport
  10/11/2019 – 10/23/2019
Phase V – Final assembly at PIP2IT
  10/1/2019 – 11/19/2019
Phase VI – ORC preparations
  3/11/2019 – 11/18/2019

## Slide 9: HWR Repair and Completion Schedule
Original Schedule : Cooldown 10/9/19 (delivery 8/20/19)
  7 weeks after receipt
New Schedule : Cooldown 11/19/19 (“delivery” 10/12/19)
  5 weeks after “receipt”
  some Phase V work on top plate occurs in parallel with repair activities (if resources available)
    Examples
      Solenoid lead soldering.
      WEKA valve welding/installation
      Jumper cables between FTs/patch panels
      Wiring
      Final tuner piping

## Slide 10: HWR Repair and Completion - Next Steps
Push forward on Phase I activities
Refine schedule, add resources
  Input to BCR for repair activities
  Input for “buy/make” decision for offsite/onsite repair
Begin discussion with MTM re: budgetary estimate
Critical issues:
  Development of procedures, JHAs, other safety documentation, especially for new scope of work
    Examples : safety analyses for CM stands, CM lid stands, lid lifting (ANL procedure exists), thermal shield removal (never done at ANL), thermal shield repair (never done), other mundane tasks
  This can/will be the critical path, need engineering resources
  Offsite repair of TS eliminates some of this burden

## Slide 11: HWR Cryomodule Lessons Learned for Partner Labs (Preliminary)
Fermilab leads and oversee the design of cryomodules with prototyping
Fermilab oversight
  Experienced partner lab: Fermilab provides specification
  Other partner lab: Fermilab provides specification, procedure and QA/QC guidance
  All governed by project planning documents
Priority and commitment of partner labs are essential

## Slide 12: WBS 121.2 SRF Updates – SSR Cryomodules
SSR2: prototype cavity niobium bids received, evaluation is in progress.
SSR1: cold mass assembly is in progress.
SSR1: cryomodule assembly is expected to complete in October.
Issues: SSR1 experienced difficulty to get alignment support due to accelerator shutdown work load.

## Slide 13: WBS 121.2 SRF Updates – 650 Cryomodules
All four prototype couplers qualified at room temperature conditioning stand.
  A pair of EM shield design and traditional design
  50kW CW full reflection

## Slide 14: WBS 121.2 SRF Updates – 650 Cavities
HB650 5-cell tested, cavity performance limited by quench.
  Second cavity in a row has no field emission.
  Second cavity in a row that quenched at 20 MV/m with high Q.
    Cold EP improvement is on the way for the next several cavities