## Slide 1
Peter Wilson – SBN Program Coordinator
Oversight Board
13 September 2019
SBN Program Status

## Slide 2: Outline
ICARUS technical progress
SBND technical progress
Transition to Operations Planning
Booster Neutrino Beam in 2020-21
Upcoming Reviews

## Slide 3: Far Detector - ICARUS
Exterior LAr Filters
Cryogenic Dewars
Cold Vessels (TPCs and PMTs inside)
Proximity Cryogenics
Side CRT
Top CRT and Overburden
(not shown)
Not shown in alcoves (mezzanine and pit):
DAQ racks
Controls racks
Bottom CRT
TPC Electronics
Two 33 ton cranes

## Slide 4: Far Detector Progress
  Cryogenics
    Final few items to complete hardware installation
    Controls and ODH wiring near complete
    Controls programming in progress
  Infrastructure - electricians
Outlets on vessel top completed
Outlets for west mezzanine DAQ racks in progress
Outlets for east mezzanine PMT racks starting
Electrical work continues on critical path
  Readout and DAQ Electronics infrastructure
Main cable tray installation on top of the detector complete
PMT readout racks setup
DAQ racks in place
First EVB/DAQ servers onsite remaining severs due in early October
Networking:
  Cable tray (yellow in photo) components on order, also used for DAQ and PMT fibers
  Network switches in hand
  Completion in October on critical path

## Slide 5: Far Detector Progress
  TPC Front end electronics
    All electronics installed and tested
    Noise characterization studies completed
    Measured effect of building systems on electronic noise (negligible)
    Some noisy channels in a few corner chimneys
      Proposal to make a two day intervention the week of Sept 23
    Cables for wire bias and timing distribution near completion, installation in one to two weeks
  PMT system
Installation of cabling to digitizers and calibration fibers started. Remaining cables in transit from CERN with DAQ servers (early Oct).
Preparing for installation of calibration laser
  CRT system
    North wall dedicated to Simone Marcocci (FNAL postdoc) on Sept 11
    Mounting system for east and west wall CRTs being installed. Main CRT installation after fill.
    Production progress well at Frascatti for top CRT – ship at end of the calendar year.

## Slide 6: Cryogenics Commissioning Activities
  Vacuum operation started 10th June
    Continue pumping until the start of cool-down
  Cool-down and liquid argon filling
    Liquid Argon contract in place – requires >21 day notice to start daily delivery
    LN2 dewar operation approved, certified and filled in July
    LAr dewar operation approved, cetification and fill in next week
    Scheduling of final steps to start LAr fill in progress
      Controls hardware checkout ~ end of September
      Controls programming checkout ~ end of September
      ODH system active - early October
      Final system checkout by CERN and FNAL engineering – early October
      Approval (pORC) to start LN2 cooldown – early October
      Start LN2 cooldown – late October
      Start LAr fill – early November
  CERN engineering participates, in person, starting from final checkout through the fill process.
    Includes monitoring of cold vessel strain gauges
    CERN has a safety documentation & review process similar to Fermilab’s, and the participation satisfies their sign-off procedure

## Slide 7: ICARUS Milestones to I-1 Ready to Fill
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Vessels rigged into building | P. Wilson | 16-Aug-2018 |  |  | 16-Aug-2018
Manholes welded and vacuum test successful | C. Montanari | 10-Oct-2018 |  |  | 11-Oct-2018
Warm Vessel roof complete | C. James | 15-Nov-2018 |  |  | 31-Oct-2018
Cryo Platform complete | C. James | 15-Dec-2018 |  |  | 04-Oct-2018
Proximity cryogenics installation begins | B. Norris | 15-Jan-2019 |  |  | 28-Jan-2019
DBB & flanges installation complete and tested | A. Fava | 15-Feb-2019 |  |  | 15-Mar-2019
Cold proximity cryogenics installation complete | B. Norris | 15-Apr-2019 |  |  | 21-June-2019
1st T300 readout installation complete | A. Fava | 15-Mar-2019 |  |  | 11-Apr-2019
All detector readout installed | A. Fava | 1-May-2019 |  |  | 17-May-2019
Begin vacuum pumping | C. Montanari | 15-Jul-2019 |  |  | 10-June-2019
Cryogenic operation approved | B. Norris | 15-Jul-2019 | 20-Sept-2019 |  | 
I1: ICARUS detectors ready to fill with LAr | P. Wilson | 30-May-2019 | 20-Sept-2019 | f | 
(after July statusing)

## Slide 8: Near Detector - SBND
Cryogenic Dewars
TPC
Proximity Cryogenics
Side CRT
Top CRT and Overburden
Readout racks
20 ton crane
Top CRT
Cryostat

## Slide 9: Near Detector Progress
  TPC Electronics
Production nearing completion – remaining part is
All Front-End Mother Boards delivered to Fermilab and ready to install
  Photon detection systems
    PMTs under test at LANL
Adopted plan to shift R&D photon system from light guide bars + ARAPUCA to ARAPUCA + X-ARAPUCA. X-ARAPUCAs will use electronics developed for light guide bars (based on Mu2e CRT electronics). Aligning with current DUNE development diraction
  TPC assembly (at Dzero):
First Anode Plane pair (of two pairs) complete and ready to install
Cathode Plane Assembly is ready to install
Field cage components are ready to install
assembly and transport fixture (atf) complete
  Need to assemble tenting etc
Completing support beams and mounting components
Technical review of detailed assembly procedures Sept 18-19
  Includes all TPC components and light detection systems
Assembly and transport fixture
Cold electronics reception test at Fermilab

## Slide 10: Near Detector Cryostat
Warm vessel frame preassembly completed at CERN and components delivered to Fermilab in late August
Side plate fabrication at CERN completed and shipped at the end of August. Delivery expected around Oct 1
Shimming and bottom CRT installation start next week
Warm vessel installation starts Sept 30 with team from CERN, INFN and FNAL
Design of membrane completed by GTT. CERN is working with CERN on pricing and delivery schedule.
Installation of the membrane is on critical path for SBND completion
(credit: Roberto Acciarri)
Loading of shipping containers at CERN
Unloading of shipping containers at FNAL

## Slide 11: Near Detector Cryogenics
Demaco completed install of proximity cryogenics July 23.
  Completed work with ~2 week effort in July (estimate was 3-4 weeks)
  Ends a 6 month installation campaign at far and near detector buildings
Remaining FNAL deliverables about to enter final design before procurement: incorporating lessons learned from protoDUNEs and ICARUS
ND Proximity Cryogenics

## Slide 12: SBND Milestones to S-1 SBND ready to move
Intermediate Milestone | Owner | Baseline Date | Forecast Date (Schedule) |  | Actual Date
First set of APAs shipped to Fermilab | K. Mavrokoridis | 24-Sept 2018 |  |  | 4-Mar-2019
PO for COTS ADCs placed | H. Chen | 10-Oct-2018 |  |  | 30-Oct-2018
All TPC Components at Fermilab | K. Mavrokoridis | 1-Mar-2019 |  |  | 27-Mar-2019
Complete atf assembly at DAB | J. Zennamo | 1-May-2019 | 14-Aug-2019 | a | 
50% of motherboards delivered to Fermilab | H. Chen | 15-May-2019 |  |  | 22-May-19
APAs and CPAs installed in atf | J. Zennamo | 15-Jun-2019 | 31-Oct-2019 | b | 
Field cage assembly complete | J. Zennamo | 15-Jul-2019 | 11-Dec-2019 | b | 
Cold electronics installed and tested | H. Chen | 23-Aug-2019 | 23-Jan-2020 | b | 
S1: TPC ready to move to SBN ND | A. Schukraft | 30-Aug-2019 | 28-Jan-2020 | b | 
The atf fabrication delay propagates through the rest of the schedule leading to S1.
Planning to accelerate the schedule by parallelizing some of these tasks. Expect S1 before end of CY 2019.
(after July statusing)

## Slide 13: SBND Milestones to S-2 Ready to Fill
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
GTT Design Study Begins | M. Nessi | 1-Feb-2019 |  |  | 26-Apr-2019
Delivery of warm box steel | M. Nessi | 15-Jun-2019 | 16-Sept-2019 |  | 
Warm vessel installation complete | M. Nessi | 15-Jul-2019 | 15-Nov-2019 |  | 
TPC Transport to ND building complete | J. Zennamo | 15-Sept-2019 | 5-Feb-2020 |  | 
Cryostat material arrives at Fermilab | M. Nessi | 1-Oct-2019 | 12-Nov-2019 | c | 
Cryostat top plug is ready to attach to atf | M. Nessi | 1-Nov-2019 | 25-Mar-2020 | c | 
Membrane Cryostat Completed | M. Kim | 1-Mar-2020 | 22-Jan-2020 | c | 
Plug welded to cryostat | M. Kim, J. Zennamo | 15-Apr-2020 | 9-Jul-2020 | c | 
Cryogenic operation approved | M. Geynisman | 1-Jul-2020 | 30-Sept-2020 | c | 
S2: SBND detector is ready to fill with liquid Argon | A. Schukraft | 15-Jul-2020 | 30-Sept-2020 | c | 
c) Membrane cryostat and top cap schedule are not updated and subject to change
(after July statusing)

## Slide 14: Transition to Operation Planning
Address commissioning and operations plans for both detectors and associated support (e.g. cryogenics, online computing, data storage)
Transition to Operations Team
  Angela Aparicio – Neutrino Division (ND) Safety Officer
  Steve Brice – ND Representative
  Angela Fava – Far Detector Deputy Technical Coordinator and Commissioning Coordinator
  Claudio Montanari – Far Detector Technical Coordinator
  Barry Norris – SBN Program Engineer and Head of ND Technical Support Dept
  Dave Schmitz – SBND collaboration representative
  Michelle Stancari – Near Detector Commissioning Coordinator
  Peter Wilson – Program Coordinator, chair of TOT
  Bob Wilson – ICARUS collaboration representative
  Wes Ketchum - Scientific Computing Division representative
Meetings since February to define organizations and prepare Experiment Operations Plan (EOP)
  Outline of EOP discussed at last meeting.
  EOP is the primary document to be reviewed in the Operations Readiness Review
ND Technical Support Dept finishing Cryogenics Operations Support plan
  Extension of existing support plan for MicroBooNE to support all LAr detectors detectors
  Takes effect as cryo commissioning completes

## Slide 15: BNB Beam – Start of 2019-2020 beam period
Slide from Cons Gattuso of AD Operations
Note: standard FNAL beam schedule is based on US Fiscal year with beam operation typically starting in October (beginning of FY) and ending with a maintenance shutdown of several months at the end of the summer

## Slide 16: Beam schedule in Fiscal Year 2020 (FY20)
Slides from Mary Convery (Deputy Head of Accelerator Division)

## Slide 17: Beam Delivery Goals in 2020
Slides from Mary Convery (Deputy Head of Accelerator Division)
Red = Design
Blue = Base

## Slide 18: Beam in 2021
Expect FY 2021 beam startup to be similar to FY 2020 or slightly later accommodating the 5 month FY2020 shutdown
  BNB startup between Oct 1 and Nov 1
Expect FY 2021 shutdown to be normal duration of about 3 months probably starting in July
Performance curves for BNB delivery of protons/month to BNB should be similar to 2019 and 2020

## Slide 19: Upcoming Reviews
There will be a Operations Readiness Review held by the laboratory in February 2020 covering: SBN Operations Phase 1: Far Detector Only
  Preparation for this review is the responsibility of the collaboration
  A follow-up review will occur when the Near Detector makes the transition to operations
  Exact review date still to be set. Should occur with sufficient time to have established functionality of major detector sytems
The next SBN Director’s Review is scheduled for the week of Feb 17, 2020. The review will be focused on completing the SBND installation and transition of SBND to operations

## Slide 20: Backup

## Slide 21: Safety and Work Planning
Safety of people must remain the top priority for the SBN program. This is the responsibility of everyone involved.
A work planning process was created by Aria Soha (Far Detector Installation Coordinator) which has been used for installation activities by Fermilab, CERN, Demaco, and the collaboration.
  The goal is safe and efficient planning of work
  Flexibility to allow for unknowns is essential
  If the conditions change: stop and discuss the plan before continuing
This process has been adopted for SBND activities
As ICARUS transitions from installation to commissioning Aria’s role as Installation Coordinator is coming to an end, Primary responsibility moves to Commissioning organization
Need to maintain discipline of planning work through these transitions
  Written work plans for major activities
  Work plans will now be presented and reviewed in the Wednesday morning ICARUS meeting
  Hazard Analyses for activities with significant hazards per Fermilab Environment Safety and Health Manual (FESHM) chapter
  Discuss all work of the day at daily Toolbox Meeting (currently at 8am at SBN FD)

## Slide 22: ODH and Work Planning
Before the LN2 is introduced into the cold shields the area below grade in the SBN FD Building will become an Oxygen Deficiency Hazard (ODH) Class 1 area
  Work below grade will only be permitted for ODH Qualified personnel: ODH training and medical exam by Fermilab
  This will remain in effect for the duration of the experiment
  Details of implementation will be communicated in the coming weeks
During cryogenics commissioning (LN2 cooldown and Lar fill) additional restrictions will be in place that will severely limit access below grade
  Will require permission and escort by Cryo team
  These will remain in place until cryogenics have been stabilized after the fill
  Need to get as much installation completed as possible before cooldown
These restrictions encourage us all to plan work on the detector and mezzanines even more carefully to perform remaining installations efficiently and minimize future access