## Slide 1: DUNE Electrical Procurement Challenges
Andrew Laundrie
UW Physical Sciences Lab
DUNE Electronics Review
2019 November 18

## Slide 2: PC Board Challenges
ProtoDUNE quantities were small
Small jobs don’t garner much technical assistance or consistent processing
Many quick-turn companies who may have had or used domestic factories in the past are either going out of business or sending all work overseas
Remaining domestic producers are expensive and likely to deliver small jobs late

## Slide 3: PC Board Challenges
Need to re-calibrate cost expectations
Re-working or discarding less expensive out-of-spec boards will almost certainly result in regular production shortages
Direct communication with the factory is the only way to ensure consistency and receive early warning of production problems
Not many domestic producers left

## Slide 4: PC Board Challenges
Best bargain for manufacturing speed and good communication (so far) has been Imagineering
All of their jobs are sent to Taiwan
Factory questions require translations
Production quality is close to what we want dimensionally
Solder mask and plating consistency not great

## Slide 5: PC Board Challenges
Advance Circuits are 3 to 5 times expensive as Imagineering
Quality is better, delivery was late
In larger quantities the cost would likely drop slightly but probably still 2X budgeted costs
Other domestic producers with credible QA programs should be contacted

## Slide 6: PC Board Challenges
DUNE work appears to be unattractive due to requirements not aligned with industry norms
Quantities will never rival those of large-volume buyers ($3.5B US Sales annually)
DUNE board production goes away eventually
IceCube had similar problems with many suppliers (cables and electronic components)
Finding companies that wanted challenging requirements and unique applications resulted in getting the attention and performance that sales numbers couldn’t attract

## Slide 7: Component Challenges
Components that work great may be discontinued at any time
Capacitors are a high-risk item
The availability of specific model numbers depends on demand as a whole
Pre-buying components like this should be considered if the company can’t agree to a production contract