## Slide 1: Homework item 1: List of boards and highlight the ones that are finalized, and if not finalized what stage of completeness are they in (design process, preproduction, etc)

## Slide 2: All geometry boards except head boards have been inspected and are awaiting additional processing steps. The first set of X-layer head boards received from Advanced Circuits indicated that hole sizes for Mill_Max comonents needed to be changed. These boards have been re-ordered and delivery is pending. All other head boards have been ordered from Imagineering. Delivery is expected by the end of November.

## Slide 3: A small quantity of V-layer head boards have been ordered from BrigitFlex. Initial contact with the vendor is encouraging, as they explained how their manufacturing operation works to some extent. CR Boards and G-Bias boards are near the end of their design process, awaiting the selection of different bias connectors a better component can be identified. PSL has enough capacitors to produce at least 30 CR boards and 30 bias boards.

## Slide 4: All geometry boards will be re-evaluated in terms of trace spacing and layout to reduce voltage gradients to the extent possible. Boards already ordered will likely be used in the first Pre-Production APA unless evaluations suggest that new boards are warranted. Adapter boards are unchanged from the ProtoDUNE design. Production of these boards can begin at any time.