## Slide 1
Peter Wilson – SBN Program Coordinator
Oversight Board
13 December 2019
SBN Program Status

## Slide 2: Outline
ICARUS technical progress
SBND technical progress
Upcoming Reviews

## Slide 3: Far Detector - ICARUS
Exterior LAr Filters
Cryogenic Dewars
Cold Vessels (TPCs and PMTs inside)
Proximity Cryogenics
Side CRT
Top CRT and Overburden
(not shown)
Not shown in alcoves (mezzanine and pit):
DAQ racks
Controls racks
Bottom CRT
TPC Electronics
Two 33 ton cranes

## Slide 4: Far Detector Cryogenics
Cryogenics installation:
  Proximity cryogenics installed
  External cryogenics installed
  Controls hardware installed
  Controls software 95% complete
Installing Ar Vent Line
Rigging valve boxes
Piping installation
Cryogenics Installed

## Slide 5: Cryogenics Commissioning Activities
Cold vessels under vacuum operation since June 10
Liquid Argon contract in place
  Dewar filled, excellent delivered purity (O2 < 0.5ppm)
  21 calendar day notice required to start 1/day deliveries for fill
ODH system active (access restrictions not yet in place)
Final steps to start LAr fill in progress
  Controls hardware checkout – 95% complete
  Controls programming checkout by CERN and FNAL engineers at FNAL (December 2-10) - 50% complete
    Found two fundamental differences in interpretation of controls specification between CERN/FNAL
    Required code corrections understood – completion expected by December 20
    Resume checkout after coding work complete
      Week of Jan 6 remotely from CERN
      Starting Jan 13: CERN and FNAL engineers together at FNAL
  Approval (pORC) to start LN2 cooldown
  Start LN2 cooldown
  Start LAr fill

## Slide 6: Far Detector TPC
TPC readout system installation complete
  96 mini-crates and power supplies
  856 readout cards
  Wire bias and timing/trigger cables
  6 mini-crates fully connected to DAQ for cold commissioning
TPC readout commissioning
  connectivity of all channels verified using internal test-pulse distribution
  tests of average noise level on all wires gave positive results, slightly in excess of measurements taken at the CERN test-facility, and possible interference with PMT readout excluded by operating simultaneously the TPC readout and powering the corresponding 30 PMTs at the nominal voltage.
TPC mini-crates and Power supplies
Detector top near completion

## Slide 7: Far Detector PMT
PMT system - installation completed
  HV and signal cables installed
  HV distribution and readout digitizers installed
  pORC approved;
PMT laser calibration system:
  36 optical fibers installed
  installation of laser in light-tight box in progress
Commissioning:
  Connectivity checked both for PMTs and laser calibration;
  all PMTs powered to nominal voltage in vacuum and tested for dark count and gain verified with LED input, with results consistent with previous measurements at CERN.
PMT readout and HV racks
Detector top near completion

## Slide 8: Far Detector DAQ
Infrastructure and DAQ installation:
  AC power distribution complete
  Cable trays installed
  Central DAQ servers installed
  Network switches installed and configured
  Network fiber installation to top of detector
    Complete to mini-crates in January
  TPC and PMT event builder servers installed (configuration in progress)
DAQ Commissioning
  DAQ chain (event building, run control and online monitoring) tested at the single flange level both for TPC and PMTs
  Partial chain (up to EVB) tested for 4 TPC mini-crates and 1 PMT board simultaneously at 1 Hz
  extensive tests are being planned for the cold commissioning phase
Central Network and Servers
Event Builder Servers

## Slide 9: SBN Control Room
Control room for the SBN-FD is setup in ROC-West
Software for running the DAQ and network connections is in place
Have run DAQ, run control GUI, ECL and several of the monitoring tools from the control room machines since November 21
Starting to write the documentation for shifters
Starting tests with off-site Remote control room
  Testing to date has been done at CSU
Diana (BNL) and Bruce (FNAL) are actively working with the control room and documentation setup

## Slide 10: SBN-FD CRT Updates
Readout electronics have been installed at the north wall side CRT SBN-FD
  Reading 240 channels (8 FEBs)
Commissioning of the north wall is ongoing
Exercising the DAQ and analyzing the data collected, setting the thresholds and working with the calibration
Preparing the bottom CRT to commission side and bottom CRT
Installing the support for the remaining side CRT installation
Pedestal for each FEB after calibration
ADC spectral overlays calibrated in PE, calibration region

## Slide 11: ICARUS Milestones to I-1 Ready to Fill
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Vessels rigged into building | P. Wilson | 16-Aug-2018 |  |  | 16-Aug-2018
Manholes welded and vacuum test successful | C. Montanari | 10-Oct-2018 |  |  | 11-Oct-2018
Warm Vessel roof complete | C. James | 15-Nov-2018 |  |  | 31-Oct-2018
Cryo Platform complete | C. James | 15-Dec-2018 |  |  | 04-Oct-2018
Proximity cryogenics installation begins | B. Norris | 15-Jan-2019 |  |  | 28-Jan-2019
DBB & flanges installation complete and tested | A. Fava | 15-Feb-2019 |  |  | 15-Mar-2019
Cold proximity cryogenics installation complete | B. Norris | 15-Apr-2019 |  |  | 21-June-2019
1st T300 readout installation complete | A. Fava | 15-Mar-2019 |  |  | 11-Apr-2019
All detector readout installed | A. Fava | 1-May-2019 |  |  | 17-May-2019
Begin vacuum pumping | C. Montanari | 15-Jul-2019 |  |  | 10-June-2019
Cryogenic operation approved | B. Norris | 15-Jul-2019 | Jan-2020 |  | 
I1: ICARUS detectors ready to fill with LAr | P. Wilson | 30-May-2019 | Jan-2020 | f | 

## Slide 12: Near Detector - SBND
Cryogenic Dewars
TPC
Proximity Cryogenics
Side CRT
Top CRT and Overburden
Readout racks
20 ton crane
Top CRT
Cryostat

## Slide 13: Near Detector Progress
  TPC Assembly
    All major TPC components delivered to FNAL
    First two (of four) APAs aligned and paired
    Cathode frame assembled
    Assembly facility near complete
    Start assembly early next year
  Photon detection systems
    PMT system test in Coherent Captain Mills detector completed at LANL Ship to Fermilab when ready to install
    ARAPUCA system in production.
Cathode frame assembly
Two APAs ready for alignment
Test fit of adapter plates in PDS box
ARAPUCA Adapter Frame
X-ARAPUCA Adapter
for double -frame

## Slide 14: Atf construction
Need to complete the assembly transport frame (atf) before we can start TPC assembly.
Atf base frame was assembled and welded by the DAB technician team over summer/fall.
What’s next:
  Complete load test
  Add clean tent, roof, develop access procedures
  Finish and install rest pads & support beams for Anodes and Cathode

## Slide 15: Near Detector Progress
  TPC Electronics
  All cold electronics delivered from BNL to FNAL
  Flange crates delivered to FNAL
  Back-end electronics completed at Columbia/Nevis
  Back-end crate installation started at SBN-ND building
  Infrastructure and DAQ
  AC power to mezzanine racks
  Central DAQ servers installed
  Network servers ordered
Flange crate
Cold electronics reception test @ FNAL
TPC Readout crates
Server racks

## Slide 16: Near Detector Cryostat
Warm vessel steel structure
  Preassembly at CERN
  Shimming and bottom CRT installed
  Assembly and welding at FNAL (CERN, INFN and FNAL)
  Top cap design near complete
Cryostat membrane
  Membrane design completed by GTT
  Material procurement out for bids at CERN
  Delivery expected Spring 2020
Completed I-beam structure, CRT panels underneath
Rigging of 13t bottom I-beam structure
Installing final top edge plates
Grinding plate edges to prep for welding

## Slide 17: SBND Milestones to S-1 SBND ready to move
In the process of updating the SBND schedule to reflect expected completion of the cryostat.
  Delivery of cryostat materials to Fermilab (expect spring 2020)
  Installation of membrane cryostat
  Install internal cryogenics
  Assemble and test fit top caps
  Move the detector after the cryostat is ready.
Updated schedule completed in December well in advance of Director’s review

## Slide 18: Upcoming Reviews
The next SBN Director’s Review is scheduled for the week of Feb 25-26, 2020. The review will be focused on completing the SBND installation and transition of SBND to operations
There will be an Operations Readiness Review held by the laboratory: SBN Operations Phase 1: Far Detector Only
  Preparation for this review is the responsibility of the collaboration
  A follow-up review will occur when the Near Detector makes the transition to operations
  Exact review date still to be set. Should occur with sufficient time to have established functionality of major detector systems

## Slide 19: SBND Cryostat Installation
Time lapse video courtesy of Dimitar Mladenov (CERN)

## Slide 20: Backup