## Sheet1
[6 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Trial Assembly Phase 1 | bar: Aug to 2020 May
APA Assembly Frame Installation | bar: Aug
APA Transport and rigging | bar: Aug to 2020 Feb
APA Doublet | bar: Aug to Oct
APA Cabling Test | bar: Oct to 2020 Mar
AR-APA workshop Sept 30-Oct 3 | bar: Oct
PD test at Ash River | bar: Oct; Dec
Fabricate/install CPA Assembly | bar: Dec to 2020 Jan
DUNE CPA installed at AR | bar: 2020 Feb
APA Shipping Frame Tests | bar: 2020 Mar
Trial Assembly Phase 2 | bar: Aug to 2021 Apr
Design DSS Steel Support/Platform System-Barr | bar: Nov to Dec
Review design, bid documents, procure | bar: 2020 Jan to 2020 Feb
Fabricate/Install DSS steel support structure | bar: 2020 Mar to 2020 Apr
Initial Test DSS | bar: 2020 May
Module 0 TPC components delivered | bar: 2020 May to 2020 Jun
First Row installation/deployment tests | bar: 2020 Jun to 2020 Aug
25th Row Installation tests | bar: 2020 Aug to 2020 Oct
Revised installation tooling and TPC | bar: 2020 Oct
First Row installation/deployment tests | bar: 2020 Nov to 2021 Jan
25th Row Installation/Deployment tests | bar: 2021 Feb to 2021 Apr
Trial Assembly Phase 3 | bar: 2021 Apr to 2022 Jun
Planning, designing, review & procure | bar: 2021 Apr to 2021 Sep
Installation of mechanical DSS feed thru | bar: 2021 Oct to 2021 Dec
Installation of mechanical Cable feed thru | bar: 2021 Nov to 2021 Dec
First Row installation/deployment tests | bar: 2022 Jan to 2022 Mar
25th Row Installation/Deployment tests | bar: 2022 Apr to 2022 Jun
ProtoDUNE 2 Trial Assembly | bar: Aug to 2020 Jun
Build first HV FC prototypes
Order materials/fabricate Module 0 components | bar: Dec to 2020 Mar
Module 0 ProtoDUNE 2 FC delivered | bar: 2020 Apr
Module 0 ProtoDUNE 2 CPA,EW delivered | bar: 2020 Apr to 2020 May
Full scale ProtoDUNE 2 installation tests | bar: 2020 Apr to 2020 Aug
ProtoDUNE 2 CERN | 2020 Oct: Ash River Average 2 FTE; 2021 Jul: Ash River Average 2 FTE
Disassembly TCO drift volume | bar: 2020 Oct to 2020 Nov
Open TCO | bar: 2020 Nov to 2020 Dec
Remove ProtoDUNE-SP TPC | bar: 2021 Jan to 2021 Mar
Cryostat Mods, clean roon | bar: 2021 Apr to 2021 Jul
Install ProtoDUNE 2-SP Detector | bar: 2021 Jul to 2021 Dec
Close TCO | bar: 2022 Jan
Fill Detector | bar: 2022 Feb to 2022 Apr
First quaility assessmentof data | bar: 2022 Apr to 2022 Jun
HVS labor
CERN | bar: 2020 Oct to 2022 Jun
LSU long term | bar: 2021 Jul to 2021 Dec
LSU | bar: 2021 Sep
SBU long term | bar: 2021 Jul to 2021 Dec
SBU | bar: 2021 Aug
UTA long term | bar: 2021 Jul to 2021 Dec
UTA | bar: 2021 Jul
ANL | 2021 Jan: 1; 2021 Aug: 1; 2021 Oct: 0.25
BNL | 2020 Oct: 0.5; 2020 Nov: 0.5; 2021 Apr: 0.5; 2021 Jul: 0.5; 2021 Dec: 0.5
Ash River Crew | 2020 Oct: 2; 2020 Nov: 2; 2021 Jan: 2; 2021 Feb: 2; 2021 Mar: 2; 2021 Jul: 2; 2021 Aug: 2; 2021 Sep: 2; 2021 Oct: 2; 2021 Nov: 2; 2021 Dec: 2
Total | [14 empty] | 3.5 | 3.5 | 1 | 4 | 3 | 3 | 1.5 | 1 | 1 | 7.5 | 8 | 7 | 6.25 | 6 | 6.5 | 1 | 1 | 1 | 1 | 1 | 1