## Assessment
Safety by Design (SbD) Hazard Risk Assessment
Date: | 2019-11-16 | Assessed By: | I. Kourbanis
System: | Booster Beam Absorber
Identifier | Potential Hazzard Description | Life Cycle Stage | Who is at risk? | What is at risk? | Pre-Mitigation Severity | Pre-Mitigation Probability | Pre-Mitigation Risk Score | Mitigations | Post-Mitigation Severity | Post-Mitigation Probability | Post-Mitigation Risk Score | Status of Mitigation Implementation | Comments
| Overexposure to radiation from machine operations | Operations | Personnel on access in beamline enclosure |  | Critical | A - Almost Certain | 1 - Very High | Global requirement to supply a radiation safety interlock system. Technical specification for system to be compliant with FRCM Chapter 10. | Critical | E - Rare | 3 - Moderate | Integrated into Design
| Exposure to radiation from the front face of the Beam Absorber during instrumentation inspection. | Operations | Personnel on access in beamline enclosure |  | Medium | C - Possible | 3 - Moderate | Install marble shielding to reduce the radiation exposure. | Low | D - Unlikely | 4 - Low | Integrated into Design
| Exposure to radiation in the case we will have to replace the Booster Injection absorber. | Operations | Personnel on Access |  | High | D - Unlikely | 3 - Moderate | Monolithic absorber shielding design. Integrate shielding into absorber's block. | Low | E - Rare | 5 - Negligible | Integrated into Design
| Exposure to radiation trying to replace the Booster corrector downsream of the absorber. | Multiple | Contractors and Maintenance personnel |  | High | C - Possible | 2 - High | Minimize the radiation exposure by utilizing marble shielding around the absorber. Utilize quick disconnects for fast replacements of the correctors. | Low | C - Possible | 3 - Moderate | Integrated into Design
| Environmental impact in Raw Water. | Operations | Enviroment | Cooling ponds and waters of the state | High | B - Likely | 1 - Very High | Use appropriate shielding around the Beam Absorber. | Minimal | C - Possible | 4 - Low | Integrated into Design
| Exposure to radiation from replacing the downstream ORBUMP magnet | Operations | Contractors and Maintenance personnel |  | High | C - Possible | 2 - High | Utilize quick disconnect with crane handling. | Low | C - Possible | 3 - Moderate | Integrated into Design

## Hazard Severity Matrix
Fermilab QAM 12030TA Table 1
HAZARD SEVERITY
SEVERITY | PEOPLE | ENVIRONMENT | COMPLIANCE | PROPERTY | PROCESS/PROJECT
CRITICAL | Multiple deaths from injury or illness; multiple cases of injuries involving permanent disability; or chronic irreversible illnesses. | Permanent loss of a public resource (e.g. drinking water, air, stream, or river). | Willful disregard for the rules and regulations. | Loss of multiple facilities or program components; (>$5,000,000 total cost*) | Total breakdown identified resulting in loss/shut down of a process or project.
HIGH | One death from injury or illness; one case of injury involving permanent disability; or chronic irreversible illnesses. | Long-term loss of a public resource (e.g., drinking water, air, stream, or river). | Major noncompliance that exposes the Lab to significant potential fines and penalties. | Loss of a facility or critical program component; (>$5,000,000 total cost*) | Major breakdown identified resulting in the failure to attain the budget, schedule, key performance indicators or customer expectations.
MEDIUM | Injuries or temporary, reversible illnesses resulting in hospitalization of a variable but limited period of disability. | Seriously impair the functioning of a public resource. | Significant noncompliance that requires reporting to DOE or other authorities. | Major property damage or critical program component; ($1,000,000 - $5,000,000 total cost*) | Significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations which exposes process/project to potential failure if gap cannot be immediately resolved.
LOW | Injuries or temporary, reversible illnesses not resulting in hospitalization with lost time. | Isolated and minor, but measurable, impact(s) on some component(s) of a public resource. | Programmatic noncompliance with the Lab's Work Smart set. | Minor property damage or critical program component; ($50,000 - $1,000,000 total cost*) | Minor breakdown or gap identified which does not result in significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can be resolved.
MINIMAL | Injuries or temporary illnesses requiring only minor supportive treatment and no lost time. | No measurable impact on component(s) of a public resource | Specific instance of a noncompliance with the Lab's Work Smart set. | Standard property damage or critical program component; (<$50,000 total cost*) | Minor gaps identified which do not compromise the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can easily be resolved.
* total cost = total dollar value including parts, labor, contingency plans, etc. that is necessary to repair/replace property or program component.

## Probability
Fermilab QAM 12030TA Table 2
MISHAP PROBABILITY TABLE
PROBABILITY | DESCRIPTION
A - Almost Certain | Could occur annually
B - Likely | Could occur once in two years
C - Possible | Occurring not more than once in ten years
D - Unlikely | Occurring not more than once in thirty years
E - Rare | Occurring not more than once in one hundred years.

## Risk Assessment Actions
Risk Assessment Codes and Actions
1 - Very High | Unacceptable. Operation not permissible. Immediate action necessary.
2 - High | Remedial actions to be given a high priority.
3 - Moderate | Remedial actions to be taken at an appropriate time. Can be considered an acceptable risk.
4 - Low | Remedial action discretionary.
5 - Negligible | No action necessary.

## Look-up Tables (hidden)
Life Cycle Stage | Severity | Probability |  |  | Risk Matrix |  |  |  | Mitigation Status
|  |  |  | A - Almost Certain | B - Likely | C - Possible | D - Unlikely | E - Rare
Fabrication | Critical | A - Almost Certain | Critical | 1 - Very High | 1 - Very High | 1 - Very High | 2 - High | 3 - Moderate | Integrated into Design
Installation | High | B - Likely | High | 1 - Very High | 1 - Very High | 2 - High | 3 - Moderate | 4 - Low | Specifications and Interfaces Updated
Commissioning | Medium | C - Possible | Medium | 1 - Very High | 2 - High | 3 - Moderate | 3 - Moderate | 4 - Low | Not Implemented
Operations | Low | D - Unlikely | Low | 2 - High | 3 - Moderate | 3 - Moderate | 4 - Low | 5 - Negligible
Equipment Shutdown | Minimal | E - Rare | Minimal | 3 - Moderate | 4 - Low | 4 - Low | 5 - Negligible | 5 - Negligible
Maintenance
Trouble-shooting
Repairs/Replacement
Decommissioning
Disposal or Recycling
Multiple