## Slide 1: CRYO Testing Plan
Mark Convery
February 5, 2020

## Slide 2: Introduction
Want to be ready for a system test in ICEBERG or ProtoDUNE Cold Box by July 1 (and the other one a short time later)
  nEXO version is well matched to ICEBERG Cdet , but not bad for ProtoDUNE Cold Box
Between now and then need:
  Second ASIC version tests
  New Cold Board
  CRYO FEMB
  Interface with WIB
  …..
Provide all other needed info for ASIC down-select in ~Feb 2021
Third ASIC version to be submitted ~July

## Slide 3: Bench Test Setup
Interface
Board

## Slide 4: Problems Observed with Bench Testing Setup
Board interferences and noise coupling in each channel followed clear pattern
  Odd channels much different from even
  Traced to issue on cold board where signal traces were close to power planes
  Also revealed 160kHz noise in external LDO (solved changing LDOs)
  Cold board currently in layout
  Interface board schematic nearly completed (simple change)
New cold board to alleviate these problems now in layout
  Can accommodate new and old ASICs through loading options
  Also need minor changes to interface board – schematic near completion

## Slide 5: ASIC/FEMB Production Schedule
Goals
  Be ready for ICEBERG (or ProtoDUNE Cold Box) test in July
  Have all needed info for down-select (Feb. 2022)
Second ASIC version submitted: Dec. 1, 2019
  Almost identical pin-out to first version
  Expected to be received: Feb. 21
  For first functionality tests, use old cold board
  New cold and interface boards expected: Mar. 1
  Complete bench tests with new boards: May 30
    Need to get a sense of yield
  Third ASIC version submitted ~July (DUNE optimized)
FEMB Schedule
  Can accommodate new or old ASICs via loading options
  Out for Fab: Feb. 22
  Back from Fab: Mar. 7
  First Prototype Stuffed (use old ASIC initially): Mar. 14
  Decision point in April on whether a second version needed
  June 11: Produce ~15 FEMBs with new ASIC (need 10 good ones for ICEBERG or Cold Box)
  Likely will not pre-test ASICs – assuming high yield

## Slide 6: ASIC/FEMB Testing Schedule
March – May: Tests of new ASIC on new cold board
  Use existing ePIX setup – at SLAC
  Functionality March, April
  Performance May
  Also plan to send to MSU for detailed analog testing
March, April: Functionality Tests of FEMB with old ASIC
  Use Xilinx eval board for interface – at Hawaii
May: Functionality Tests of FEMB with new ASIC
  Use Xilinx eval board – at Hawaii
  Focused on functionality, interface – not performance
  Decide if FEMB changes needed
June: Interface FEMB with WIB (could start earlier if WIB available)
July: Ready for ICEBERG test
September: Third version ASICs received
ProtoDUNE Cold Box Test
  Use existing FEMBs, or consider using third ASIC version?
Accelerated lifetime testing

## Slide 7: ASIC/FEMB Production/Testing

## Slide 8: After System tests with NEXO version CRYO
Submission of new DUNE version
  Need results from bench test to be as complete as possible
    Some overlap between testing and design humanpower (Aldo)
  Aim for submission date: July 2020
    Perhaps can advance if testing goes smoothly and/or can offload some testing to physicists
  Chips received ~September 2020
  Bench performance tests needed
  Time for system test?
Long-term lifetime accelerated aging test
  Need to disable internal LDOs to allow elevated voltage test
  Probably also need elevated voltage test of LDOs themselves