## Slide 1: COLDATA Schedule David Christian

## Slide 2: Overview
No change is required to the floor plan or pad frame.
    Some PLL debug outputs will be removed.
    Analog changes will easily fit in the same area used by SMU section of first prototype.

## Slide 3: COLDATA Design Team
FNAL
    Jim Hoff
    Xiaoran Wang (ex SMU)
    Davide Braga
    Christian Gingu (UVM)
  SMU
    Ping Gui
  BNL
    Sandeep Miryala (ex FNAL)

## Slide 4: Responsibilities
Jim Hoff: Digital design & verification
Xiaoran Wang: PLL modifications
Christian Gingu: Verification (UVM)
Sandeep Miryala: Synthesis & PnR
Sandeep Miryala & Davide Braga: Final integration & verification

## Slide 5: Status
Digital Design
    None of the required RTL changes has been made yet.
    I2C Relay: problem is understood, solution is a trivial RTL change
    Timestamp: changes are precisely specified, solution is straightforward.
    Frame Formation: changes are precisely specified, solution is easy.
    Cable Delay (command echo): change is precisely specified; solution is understood.
    Total time required ~ 2 weeks.
  PLL Modifications
    Analog modifications are understood
    2-3 weeks of work to modify layout & simulate

## Slide 6: Goal: Submission on or before June 24
Limiting factor will be Jim Hoff’s schedule
~8 weeks required
    2-3 weeks for digital redesign/synthesis & PnR
    2-3 weeks for analog redesign/layout (does not depend on digital work)
    1 week for full-chip verification
    4 weeks for final assembly and verification
  June 24 is 20 weeks from today and 9 weeks after April 22.