## CORE 2019
last update 9-10-2019
[5 empty] | M&S Total |  |  |  |  | 49462.4332 | 0 | 616.811 | 4725.5552 | 10164.8563 | 9538.8999 | 9661.3857 | 7263.9297 | 4993.3494 | 2497.6458
[5 empty] | Labor Total |  |  |  |  | 35137.2784 | 0 | 299.3328 | 299.3328 | 4856.3929 | 4716.7039 | 7117.5001 | 6977.8111 | 5435.1024 | 5435.1024
[5 empty] | Total |  |  |  | 84599.7116 | 84599.7116 | 0 | 916.1438 | 5024.888 | 15021.2492 | 14255.6038 | 16778.8858 | 14241.7408 | 10428.4518 | 7932.7482
Reviewers | R WBS | System | Detector | item | type | #units | unit format | cost/unit[$] | total CORE[k$] | comment | t0-3 | t0-2 | t0-1 | t0 | t0+1 | t0+2 | t0+3 | t0+4 | t0+5 | Responsibility | CHECK | US project y/n
|  | Cryostat Top Infrastructure |  | 598.6656 |  |  |  |  | [FY19] | 4567.8698
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | SS vertical tubes (feed thrus) | M&S | 239 | tube | 110 | 34.177 | SS tubes to be connected to GTT membrane. 30% added. See detailed information on https://edms.cern.ch/document/2215499 |  |  |  | 34.177 | [5 empty] | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | SS tubes flanges (feed thrus) | M&S | 239 | flange | 560 | 173.992 | max size 250mm. Estimation based on te biggest flange. 30% added. See detailed information on https://edms.cern.ch/document/ 2215500 |  |  |  | 173.992 | [5 empty] | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | manholes | M&S | 4 | manhole | 6500 | 33.8 | Same as im protoDUNE, include shields.30% added. See detailed information on https://edms.cern.ch/document/ 2215502 |  |  |  | 33.8 | [5 empty] | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | gate valves on instrumentation ports | M&S | 12 | valves | 7132 | 111.2592 | CF250 gate valves as in protoDUNE. Just on selected feedthroughs. 30% added. See detailed information on https://edms.cern.ch/document/ 2215505 |  |  |  | 111.2592 | [5 empty] | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | structural supports for feed thrus | M&S | 243 | support | 30 | 9.477 | Steel profiles, cut and prepared.Counting 2 m 50 mm square bars per feedtgrough, 15$/m.. 30% added. https://edms.cern.ch/document/2217828 |  |  |  | 9.477 | [5 empty] | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | gas exhaust pipe | M&S | 860 | m | 50 | 55.9 | Counting 40 CHF/m plus 40 tees, 40 caps, 40 angles and 170 supports, diameter 100mm, 30% added. https://edms.cern.ch/document/2217829 |  |  |  | 33.54 | 22.36 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | exhaust valves | M&S | 243 | valve | 323 | 102.0357 | To control the GAr flux. CERN catalogue. 30% added. See detailed information on https://edms.cern.ch/document/2215515 |  |  |  | 61.2214 | 40.8143 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | flexibles to valves | M&S | 243 | flex tubes | 120 | 37.908 | From protoDUNE, 30% added. See detailed information on https://edms.cern.ch/document/ 2215519 |  |  |  | 22.7448 | 15.1632 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | exhaust valves soft pipe | M&S | 946 | valves | 4 | 4.9192 | soft pipes. 30% added. See detailed information on https://edms.cern.ch/document/ 2215529 |  |  |  | 2.9515 | 1.9677 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | exhaust valves fanout | M&S | 1 | fanout | 10300 | 13.39 | Number of compressed air valves times their cost + a 4 mini-racks. 30% added. See detailed information on https://edms.cern.ch/document/ 2215565 |  |  |  | 8.034 | 5.356 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | gas analysers | M&S | 8 | analyzer | 9571 | 99.5384 | 30% added. See detailed information on https://edms.cern.ch/document/ 2215532 |  |  |  | 59.723 | 39.8154 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | O2 trace analysers | M&S | 8 | analyzer | 9815 | 102.076 | to map possible leaks problems. 30% added. See detailed information on https://edms.cern.ch/document/ 2215535 |  |  |  | 61.2456 | 40.8304 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | primary pumps | M&S | 4 | pumps | 1350 | 7.02 | Primary pump. CERN price. https://edms.cern.ch/document/2220588. 30% added. |  |  |  | 4.212 | 2.808 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | turbo pumps | M&S | 2 | pumps | 9000 | 23.4 | Pumping station: primary pump and turbo pump. 30% added. https://edms.cern.ch/document/2220601 |  |  |  | 14.04 | 9.36 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | He leak checkers | M&S | 2 | analyser | 35125 | 91.325 | We have formal offers. 30% added. https://edms.cern.ch/document/2220602 |  |  |  | 54.795 | 36.53 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | vacuum tools | M&S | 1 | tools | 15000 | 19.5 | selas, clamps, adapters, blind, valves, … Estimated from b.182 experience https://edms.cern.ch/document/2260262/1 |  |  |  | 11.7 | 7.8 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | lights under the mezzanines | M&S | 240 | m | 25 | 7.8 | ~125 $ for 5 m long LED strip (190 lm/m) and power supply for 50 W. https://edms.cern.ch/document/2220587 |  |  |  | 4.68 | 3.12 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | V (power) cable trays + supports | M&S | 860 | m | 35 | 39.13 | 50 cm (conservative) cable trays + 1 m logn 40 mm square bars for the supports every meter of cable tray (conserative). 30% added. See detailed information on https://edms.cern.ch/document/ 2215539 |  |  |  | 23.478 | 15.652 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | signals cable trays + supports | M&S | 860 | m | 35 | 39.13 | 50 cm (conservative) cable trays + 1 m logn 40 mm square bars for the supports every meter of cable tray (conserative). 30% added. See detailed information on https://edms.cern.ch/document/ 2215539 |  |  |  | 23.478 | 15.652 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | copper grounding for the cable trays | M&S | 860 | m | 80 | 89.44 | 1cm diamter copper bundle. 80$/m https://edms.cern.ch/document/2217830/1 |  |  |  | 53.664 | 35.776 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure labor | 1 | specialized welders team det1 | Labor | 3 | FTE years | 99777.6 | 299.3328 | 3 welders for flanges and various supports, specialists. Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 179.5997 | 119.7331 |  |  |  |  | SDSD Labor | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | walking floor | M&S | 1320 | mq | 36.5 | 62.634 | Plywood 24 mm thick. https://edms.cern.ch/document/2217832 |  |  |  |  | 62.634 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | cable tray from CUC to racks mezzanine | M&S | 680 | m | 70 | 61.88 | 50 cm (conservative) cable trays + 2.5 m logn 40 mm square bars for the supports every meter of cable tray. https://edms.cern.ch/document/ 2215539 |  |  |  |  | 61.88 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | power racks on mezzanine | M&S | 78 | rack | 2222 | 225.3108 | standard 42U racks with doors. CERN price. https://edms.cern.ch/document/2217836 |  |  |  |  | 225.3108 |  |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | racks internal power distribution | M&S | 78 | distribution | 304 | 30.8256 | 2x 10 sockets 13 A. https://edms.cern.ch/document/2217833 |  |  |  |  | 18.4954 | 12.3302 |  |  |  | I&I MS | 0 | y
Resnati, Shaw | 131.04.01.06 | Cryostat Top infrastructure | 1 | racks controls + safety | M&S | 78 | control box | 4200 | 425.88 | sensors, fire detectors, controls, ventilation. 30% added. See detailed information on https://edms.cern.ch/document/2215442 |  |  |  |  | 255.528 | 170.352 |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | cryo vertical access doors | M&S | 176 | access | 1200 | 274.56 | access control to stairs external cryo. 6 $/kg x 200 kg of material per door. 30& added. |  |  |  |  | 164.736 | 109.824 |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | miniracks + supports | M&S | 75 | racks | 450 | 43.875 | Rack+2m square bars for support. 30% added https://edms.cern.ch/document/2217829 https://edms.cern.ch/document/2217834/1 |  |  |  |  | 26.325 | 17.55 |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | Water cryo traps | M&S | 4 | units | 10000 | 52 | protoDUNE experience. 30% added. https://edms.cern.ch/document/2217835/1 | [6 empty] | 52 |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 1 | valves for the GN2 insulation control | M&S | 4 | units | 2260 | 11.752 | Actual valve purchaised for ProtoDUNEs. https://edms.cern.ch/document/2217837 | [5 empty] | 11.752 |  |  |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure | 2 | M&S det2 same as det1 | M&S |  |  |  | 2283.9349 | [6 empty] | 913.574 | 913.574 | 456.787 |  | I&I MS | 0 | y
Resnati | 131.04.01.06 | Cryostat Top infrastructure labor | 2 | specialised welders team det2 | Labor | 3 | FTE years | 99777.6 | 299.3328 | 3 welders for flanges and various supports, specialists. Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. | [5 empty] | 179.5997 | 119.7331 |  |  | SDSD Labor | 0 | y
|  | Int Cryogenics |  | 389.1326 | [5 empty] | 1590.6774
David M | 131.04.01.06 | Int Cryogenics | 1 | pipes + fixations | M&S | 1 | all | 611799 | 795.3387 | 30% added. See detailed information on https://edms.cern.ch/document/ 2215445. |  |  |  |  | 795.3387 |  |  |  |  | I&I MS | 0 | y
David M | 131.04.01.06 | Int Cryogenics labor | 1 | assembly work 3 FTE for 6 months | Labor | 1.5 | tec | 99777.6 | 194.5663 | 3 welders cryo pipes and supports specialists. Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. | [5 empty] | 194.5663 |  |  |  | SDSD Labor | 0 | y
David M | 131.04.01.06 | Int Cryogenics | 2 | pipes + fixations | M&S | 1 | all | 611799 | 795.3387 | 30% added. See detailed information on https://edms.cern.ch/document/ 2215445. | [5 empty] | 795.3387 |  |  |  | I&I MS | 0 | y
David M | 131.04.01.06 | Int Cryogenics labor | 2 | assembly work 3 FTE for 6 months | Labor | 1.5 | tec | 99777.6 | 194.5663 | 3 welders cryo pipes and supports specialists. Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. | [6 empty] | 194.5663 |  |  | SDSD Labor | 0 | y
|  | DSS | [7 empty] | 5042.7754
Dimitar | 131.04.01.06 | DSS | 1 | SS rails | M&S | 336 | m | 349 | 152.4432 | Special SS production 6m. See detailed information on https://edms.cern.ch/document/2214560 |  |  | 45.733 | 45.733 | 60.9773 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | DSS | 1 | rail supports + feedthroughs | M&S | 105 | support | 9548 | 1303.302 | Complex regulation system and feedthrough. See detailed information on https://edms.cern.ch/document/2214863 |  |  | 390.9906 | 390.9906 | 260.6604 | 260.6604 |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | DSS | 1 | SS APA,CPA supports to rails and shuttle system | M&S | 450 | SS support | 750 | 438.75 | interface point needs to be identified (not installation tool, but permanent fixations). Should include trollies, beam crawlers, controls, stops, brackets, power, TCO beam and supports. |  |  | 131.625 | 131.625 | 175.5 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | DSS | 1 | Installation equipment | M&S | 1 | varia | 315699 | 410.4087 | gantry top of cryo, portable cleanroom tent for each feedthrough + personnel access, locks and controls, beam crawlers, installation tools, support blocks, survey targets. See detailed information on https://edms.cern.ch/document/2222063 |  |  | 123.1226 | 123.1226 | 164.1635 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | DSS | 1 | installation test equipment, QA, and shipping stuff | M&S | 1 | varia | 166526 | 216.4838 | leak chaser, tooling, test vacuum vessel, shipping rig for going underground, Al pallets, crates for I-beam transport, ultrasonic cleaner, shrink wrap. See detailed information on https://edms.cern.ch/document/2222064 |  |  | 64.9451 | 64.9451 | 86.5935 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | DSS | 2 | same as det 1 | M&S | 1 | sum |  | 2521.3877 |  |  |  |  | 756.4163 | 756.4163 | 504.2775 | 504.2775 |  |  | I&I MS | 0 | y
|  | Cranes |  | 2118.74
Jean-Louis | 131.04.01.03 | Cranes | 1 | bridge crane | M&S | 1 | bridge crane | 285000 | 370.5 | 30% added. See detailed information on https://edms.cern.ch/document/2215247 |  | 111.15 | 111.15 | 148.2 | [5 empty] | SDSD M&S | 0 | y
Jean-Louis | 131.04.01.03 | Hoists | 1 | individual hoists | M&S | 6 | hoist | 50000 | 390 | 30% added. See detailed information on https://edms.cern.ch/document/2215247 |  | 117 | 117 | 156 | [5 empty] | SDSD M&S | 0 | y
Jean-Louis | 131.04.01.03 | Cranes | 1 | Power line (150m) | M&S | 3 | power line | 15300 | 59.67 | 30% added. See detailed information on https://edms.cern.ch/document/2215247 |  | 17.901 | 17.901 | 23.868 | [5 empty] | SDSD M&S | 0 | y
Jean-Louis | 131.04.01.03 | Cranes | 1 | Installation of cranes, hoist, power lines and 1rst inspection | M&S | 1 | installation of handling equipement | 144000 | 187.2 | 100$/h, 40h /week, 6 weeks /6 workers. 30% added. See detailed information on https://edms.cern.ch/document/2215247 |  | 56.16 | 56.16 | 74.88 | [5 empty] | SDSD M&S | 0 | y
Jean-Louis | 131.04.01.03 | Cranes | 1 | small material (slings, …) | M&S | 50 | material | 800 | 52 |  |  | 15.6 | 15.6 | 20.8 | [5 empty] | SDSD M&S | 0 | y
Jean-Louis | 131.04.01.03 | Cranes | 2 | same as det1 | M&S | 1 | sum | 814.9 | 1059.37 |  |  |  | 317.811 | 317.811 | 423.748 |  |  |  |  | SDSD M&S | 0 | y
|  | Mecanical structures |  | 8748.6646
Dimitar | 131.04.01.06 | Infrastructure | 1 | detector mezzanine | M&S | 1 | structure | 226000 | 293.8 | Simple steel support structure, including the floor and fixations to the cryostat. 38.3 tons at 4.2$/kg. See detailed information on https://edms.cern.ch/document/2215252 |  |  | 88.14 | 88.14 | 117.52 |  |  |  |  | SDSD M&S | 0 | y
Dimitar | 131.04.01.03 | Infrastructure | 1 | main bridge | M&S | 1 | bridge | 151619 | 197.1047 | Same beams as cryostat including the floor and fixations to concrete. 26.2 tons at 4.2$/kg. See detailed information on https://edms.cern.ch/document/2215253 |  |  | 59.1314 | 59.1314 | 78.8419 |  |  |  |  | SDSD M&S | 0 | y
Dimitar | 131.04.01.03 | Infrastructure | 1 | hand rails | M&S | 200 | m | 70 | 18.2 | See detailed information on https://edms.cern.ch/document/2214865 |  |  | 5.46 | 5.46 | 7.28 |  |  |  |  | SDSD M&S | 0 | y
Dimitar | 131.04.01.03 | Infrastructure | 1 | connection cryostat-bridge | M&S | 2 | bridge | 14844 | 38.5944 | Simple steel structure, including the floor and fixations to the bridge and the cryostat. 1.7 tons at 4.2$/kg. See detailed information on https://edms.cern.ch/document/2221877 |  |  | 11.5783 | 11.5783 | 15.4378 |  |  |  |  | SDSD M&S | 0 | y
Dimitar | 131.04.01.03 | Infrastructure | 1 | stair to 4910 | M&S | 19 | m | 2500 | 61.75 | See detailed information on https://edms.cern.ch/document/2214866 |  |  | 18.525 | 18.525 | 24.7 |  |  |  |  | SDSD M&S | 0 | y
Dimitar | 131.04.01.03 | Infrastructure | 1 | stairs to mezzanines | M&S | 7 | m | 2000 | 18.2 | See detailed information on https://edms.cern.ch/document/2214867 |  |  | 5.46 | 5.46 | 7.28 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.03 | Infrastructure | 1 | Unforeseen facility modifications | M&S | 4 | /year | 50000 | 260 | post CF contracts: just a guess |  |  | 65 | 65 | 65 | 65 |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.03 | Infrastructure | 1 | licence engineering services | M&S | 6 | /year | 30000 | 234 | SD controls and permits on unforeseen work: just a guess |  |  | 58.5 | 58.5 | 58.5 | 58.5 |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.03 | Infrastructure | 1 | Compensation for lost of time to work | M&S | 8 | compensation | 230000 | 2392 | Liability for work non possible, because external problems. Compensation to firms. Initial estimation |  | 299 | 299 | 299 | 299 | 299 | 299 | 299 | 299 | SDSD M&S | 0 | y
Patrick | 131.04.01.03 | Infrastructure | 1 | Alimak procurement | M&S | 1 | alimakr | 374064 | 486.2832 | offer 2017. add 30%. See detailed information on https://edms.cern.ch/document/2225274 |  |  | 145.885 | 145.885 | 194.5133 |  |  |  |  | SDSD M&S | 0 | y
David | 131.04.01.03 | Infrastructure | 1 | Condensation prevention system | M&S | 1 | pipes | 173000 | 224.9 | Add 30%. See detailed information on https://edms.cern.ch/project/CERN-0000201944 |  |  | 67.47 | 67.47 | 89.96 |  |  |  |  | SDSD M&S | 0 | y
David | 131.04.01.03 | Infrastructure | 1 | Grouting below cryostat | M&S | 1 | spacers | 115000 | 149.5 | Grouting for cryostat floor support, electrical isolation pads to be inserted under the cryostat. Add 30%. Simple estimation (material+hours) |  |  | 44.85 | 44.85 | 59.8 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.03 | Infrastructure | 2 | same as det1 | M&S |  |  |  | 4374.3323 | [6 empty] | 1749.7329 | 1749.7329 | 874.8665 |  | SDSD M&S | 0 | y
|  | Control Rooms |  | 216 | [5 empty] | 534.0535
Giovanna | 131.04.01.03 | Control Rooms | N/A | screens in cntrl | M&S | 20 | TV screen | 740 | 19.24 | underground cntrl room. 30% added. ; https://edms.cern.ch/document/2214197 | [5 empty] | 9.62 | 9.62 |  |  | I&I MS | 0 | y
Giovanna | 131.04.01.03 | Control Rooms | N/A | computers in cntrl | M&S | 25 | computer | 1611 | 52.3575 | underground cntrl room. 30% added. ; https://edms.cern.ch/document/2214197 | [5 empty] | 26.1788 | 26.1788 |  |  | I&I MS | 0 | y
Terri | 131.04.01.03 | Control Rooms | N/A | power distribution in cntrl | M&S | 25 | power socket | 140 | 4.55 | underground cntrl room. 30% added. See detailed information on https://edms.cern.ch/document/2215431 | [5 empty] | 2.275 | 2.275 |  |  | I&I MS | 0 | y
Giovanna | 131.04.01.03 | Control Rooms | N/A | Net distribution in cavern/wifi | M&S | 37 | routers | 10650 | 394.05 | includes switches and copper cables; no uplinks which go into DAQ; NOT WIFI, only ethernet connections to electronics and slow control devices. ; https://edms.cern.ch/document/2214219/1 ; https://edms.cern.ch/document/2214283/1 | [5 empty] | 197.025 | 197.025 |  |  | I&I MS | 0 | y
Patrick | 131.04.01.03 | Control Rooms | N/A | tables and chairs | M&S | 30 | tabel+2 ch | 900 | 27 | misc items, tables, benches, water despencers, microwaves, shelves | [5 empty] | 13.5 | 13.5 |  |  | I&I MS | 0 | y
Patrick | 131.04.01.03 | Control Rooms | N/A | fire life safety/ barack | M&S | 4 | fire life | 2280 | 11.856 | estimate based on 8'x20' control room. Provided by J. Niehoff 650 per sprinkler head (2), 600 per detector (1), with 20% labor difficulties. 30% added | [5 empty] | 5.928 | 5.928 |  |  | I&I MS | 0 | y
Patrick | 131.04.01.03 | Control Rooms | 1 | det 1 cryo room (cpu, screens, table) | M&S | 5 | cntrl room | 2500 | 12.5 | on cryo mezzanine, simple estimation |  |  |  |  | 6.25 | 6.25 |  |  |  | I&I MS | 0 | y
Patrick | 131.04.01.03 | Control Rooms | 2 | det 2 cryo room (cpu, screens, table) | M&S | 5 | cntrl room | 2500 | 12.5 | on cryo mezzanine, simple estimation |  |  |  |  | 6.25 | 6.25 |  |  |  | I&I MS | 0 | y
Patrick | 131.04.01.03 | Control Rooms | 1 | baracks cryo 1+ light + power + desks | M&S | 4 | barack | 27000 | 108 | on cryo mezzanine, simple estimation |  |  |  |  | 54 | 54 |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.03 | Control Rooms | 2 | baracks cryo 2+ light + power + desks | M&S | 4 | barack | 27000 | 108 | on cryo mezzanine, simple estimation | [5 empty] | 54 | 54 |  |  | SDSD M&S | 0 | y
|  | Transport Tools |  | 1853.8443
Patrick | 131.04.01.02 | Transport Tools | N/A | engines | M&S | 1 | engine | 119233 | 155.0029 | 30% added. See detailed information on https://edms.cern.ch/document/ 2225275 |  |  |  | 93.0017 | 62.0012 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | wagons | M&S | 6 | wagon | 18000 | 140.4 | 6 wagons at 18K each. 30% added. See detailed information on https://edms.cern.ch/document/ 2225276 |  |  |  | 84.24 | 56.16 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | mobile crane at shaft botton | M&S | 1 | mob crane | 73000 | 94.9 | 2 electric hoists at shaft bottom with maintenance included See transport tools tab. |  |  |  | 56.94 | 37.96 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | headframe transport tools telehandler rental | M&S | 2 | rental/yr | 72000 | 187.2 | 30% added. See detailed information on https://edms.cern.ch/document/ 2225277 |  |  |  | 112.32 | 74.88 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | headframe transport tools forklift rental | M&S | 5.5 | rental/yr | 42000 | 300.3 | 30% added. See detailed information on https://edms.cern.ch/document/ 2218846 |  |  |  | 180.18 | 120.12 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | headframe transport tools forklift purchase | M&S | 1 | purchase | 100000 | 130 | 30% added. See detailed information on https://edms.cern.ch/document/ 2225278 |  |  |  | 78 | 52 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | All terrain pallet jack for surface | M&S | 1 | purchase | 19000 | 24.7 | 30% added. See detailed information on https://edms.cern.ch/document/ 2225279 |  |  |  | 7.41 | 7.41 | 4.94 | 4.94 |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | fixation material in shaft, guides | M&S | 4 | tool | 25000 | 100 | Guess. More engineering needed |  |  |  | 30 | 30 | 20 | 20 |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | basic rigging equipment | M&S | 1 | tool | 104880 | 136.344 | Surface, 4850, and the caverns. Includes 15% annual replacement costs for the materials.30% added. See detailed information on https://edms.cern.ch/document/ 2225281 |  |  |  | 81.8064 | 54.5376 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | 2 fork lifts underground electric, 6 years | M&S | 12 | rental/y | 30000 | 468 | Based on quotes for needed forklifts |  |  |  | 280.8 | 187.2 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | 1 standup forklift | M&S | 1 | Purchase | 52000 | 67.6 | Standup Forklift to purchase and keep during operations. Includes maintenance |  |  |  | 40.56 | 27.04 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | Personnel Carriers | M&S | 1 | Purchase | 30000 | 39 | Personnel carriers. Include maintenance. See transport tools tab. See detailed information on https://edms.cern.ch/document/ 2225280 |  |  |  | 23.4 | 15.6 |  |  |  |  | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Transport Tools | N/A | Pallet Jacks | M&S | 6 | Purchase | 1333 | 10.3974 | Pallet Jacks for underground, includes maintenance |  |  |  | 6.2384 | 4.159 |  |  |  |  | SDSD M&S | 0 | y
|  | Installation Tools |  | 566.3547 | [5 empty] | 9520.5543
Dimitar | 131.04.01.06 | Installation Tools | 1 | basic clean room structure (metallic str.) | M&S | 1 | structure | 172377 | 224.0901 | Steel framing, door frames, wall supports/framing. Includes all 3 SAS. Weight 41 tons at 4.2$/kg including shipping. See detailed information on https://edms.cern.ch/document/2214868 |  |  |  | 134.4541 | 89.636 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | Installation Tools | 1 | basic clean room structure(walls) | M&S | 1 | walls, roofs | 104000 | 135.2 | All sheeting including all 3 SAS. Total 1'300mq. Offer protoDUNE = 80$/mq. See detailed information on https://edms.cern.ch/document/2214869 |  |  |  | 81.12 | 54.08 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | Installation Tools | 1 | basic clean room structure(doors) | M&S | 6 | door | 1300 | 10.14 | Doors to put in door frames. See detailed information on https://edms.cern.ch/document/2214870 |  |  |  | 6.084 | 4.056 |  |  |  |  | I&I MS | 0 | y
Bill | 131.04.01.06 | Installation Tools | 1 | clean room infrastructure | M&S | 1 | varia | 377261 | 490.4393 | This includes Hepa filter, man doors, electrical distribution, fire suppression, lighting, environmental monitoring, particale counters, ESD Flooring, gowning room and airlock.30% added because large undecertainties in electrical and fire items. 30% added. See detailed information on https://edms.cern.ch/document/2216173 |  |  |  | 294.2636 | 196.1757 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | Installation Tools | 1 | large platforms | M&S | 1 | structure | 62900 | 81.77 | 2 level fixed platforms, including floor and handrail. See detailed information on https://edms.cern.ch/document/2214871 |  |  |  | 49.062 | 32.708 |  |  |  |  | I&I MS | 0 | y
Bill | 131.04.01.07 | Installation Tools | 1 | personnel SAS outfitting | M&S | 1 | varia | 52998 | 52.998 | Benches, racks, storage cabinets, shoe cleaners,etc..Revised from previous estimate for larger team and more changing rooms. No 30% added. See detailed information on https://edms.cern.ch/document/2216176 |  |  |  | 52.998 | [5 empty] | I&I MS | 0 | y
Dimitar | 131.04.01.06 | Installation Tools | 1 | internal bridge crane | M&S | 1 | crane | 69000 | 89.7 | 26m 2 T crane. 30% added. See detailed information on https://edms.cern.ch/document/2214872 |  |  |  | 53.82 | 35.88 |  |  |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.06 | Installation Tools | 1 | external rails (DSS type) + fixations | M&S | 50 | m | 349 | 22.685 | Rails from cryostat to cold boxes + trolleys. 30% added. See detailed information onhttps://edms.cern.ch/document/2214874 |  |  |  | 13.611 | 9.074 |  |  |  |  | I&I MS | 0 | y
Bill | 131.04.01.07 | Installation Tools | 1 | Cold box access lift | M&S | 2 | crane | 56030 | 72.839 | Assume the work can be done with the Ascell/Spider lift. 30% added. See detailed information on https://edms.cern.ch/document/2216358 |  |  |  | 72.839 | [5 empty] | I&I MS | 0 | y
Bill | 131.04.01.06 | Installation Tools | 1 | ventilation system top man holes | M&S | 4 | ventilation | 10450 | 54.34 | Defined by ISO8 ventillaiton requirements. 30% for maintenance on top. Quote is $10.4k per unit. Operations cost in consumables https://edms.cern.ch/document/2221643/1 |  |  |  | 54.34 | [5 empty] | I&I MS | 0 | y
Dimitar | 131.04.01.07 | Installation Tools | 1 | cold boxes | M&S | 3 | cold box | 177000 | 690.3 | 1 cold box = 11 tons Stainles Steel (50K$) + 10 tons insulation (20K$) + 20% of additional material = 84k$. Assembly 3 tecs for 2 months = 48K$ + doors (45K$) = 177K$. 30% added. See detailed information on https://edms.cern.ch/document/2214875 |  |  |  | 414.18 | 276.12 |  |  |  |  | I&I MS | 0 | y
David M | 131.04.01.07 | Installation Tools | 1 | N2 system for cold boxes | M&S | 1 | N2 | 1106000 | 1106 | No 30% added. Need to add labor: 1,520 hr Sr Tech + 3,280 hr Sr Engineer + 1,040 hr Designer. + Manpower to support the testing: 5,520 hr Sr Tech/Operator + 720 hr Engineer. All numbers w/o contingency. No 30% added. See detailed information on https://edms.cern.ch/document/2215077 |  |  |  | 663.6 | 442.4 |  |  |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | CPA assembly tower/frame | M&S | 2 | CPA tool | 20000 | 52 | Final engineering still to be done. Simple estimate by weight. 2 tons/unit at 10$/kg. Does not include the assembly fixture-Consortia scope. 30% added. |  |  |  | 31.2 | 20.8 |  |  |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | APA cable installation infrastructure | M&S | 4 | supports | 8228.5 | 42.7882 | cable reels, sheave, supports etc. 30% added. See detailed information on https://edms.cern.ch/document/2216673 |  |  |  | 25.6729 | 17.1153 |  |  |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.06 | Installation Tools | 1 | cryostat lights+filters | M&S | 1 | light | 22557 | 29.3241 | UV filtered lights. All temporary devices lower via spare feedthroughts. ProtoDUNE experience. 30% added. See detailed information on https://edms.cern.ch/document/2216712 |  |  |  | 17.5945 | 11.7296 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Installation Tools | 1 | temporary power distribution | M&S | 4 | power | 6693 | 34.8036 | inside cryostat. 30% added. See detailed information on https://edms.cern.ch/document/2215432 |  |  |  | 20.8822 | 13.9214 |  |  |  |  | I&I MS | 0 | y
Bill | 131.04.01.07 | Installation Tools | 1 | various mech. tools | M&S | 2 | tools | 44117 | 114.7042 | Clean hand tools in paricular. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2221644 |  |  |  | 68.8225 | 45.8817 |  |  |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | Cleanroom safety tools (PPE,ODH, fire, …) | M&S | 1 | safety | 171145 | 171.145 | Based on recent cost experience from FNAl at SURF. No 30% added. See detailed information on https://edms.cern.ch/document/2216753 | [5 empty] | 119.8015 | 51.3435 |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | consumables, small items / 2 years 2 detectors | M&S | 4 | year sets | 101494 | 405.976 | Material per year for 4 years. No 30% added. See detailed information on https://edms.cern.ch/document/2216764 | [5 empty] | 101.494 | 101.494 | 101.494 | 101.494 | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | clean room initial cleaning | M&S | 2 | varia | 56000 | 145.6 | Based on the protodune experience, multiplied by 4 (surface ratio). 30% added. ProtoDUNE 14K$ | [5 empty] | 72.8 |  | 72.8 |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | spare parts | M&S | 1 | varia | 150000 | 195 | flanges, seals, tools, nuts and bolts, wire/cable, etc. Simple estimation based on protoDUNE experience. 30% added. | [5 empty] | 136.5 | 58.5 |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | electrical diagnostics equipment | M&S | 1 | varia | 205193 | 205.193 | network anylizers scopes, spectrum anylizers, ESD work station, current probes, megOhm meter, etc..No 30%. See detailed information on https://edms.cern.ch/document/2216764 | [5 empty] | 143.6351 | 61.5579 |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | 1 | installation storage equipment | M&S | 1 | varia | 47640 | 61.932 | pallet racks, storage racks, flammable cabinet, general storage cabinets, wire cage. 30% added. See detailed information on https://edms.cern.ch/document/2216991 | [5 empty] | 43.3524 | 18.5796 |  |  | I&I MS | 0 | y
Manhong | 131.04.01.06 | Installation Tools | 1 | floor inside cryostat + supports | M&S | 1 | mq | 203904 | 265.0752 | Based on plywood construction 930mq + ESD in the clean room. 30% added. See detailed information on https://edms.cern.ch/document/2216992 |  |  |  |  | 185.5526 | 79.5226 |  |  |  | I&I MS | 0 | y
Patrick | 131.04.01.07 | Installation Tools | 1 | scissor lifts rental (6 per 48 months) | M&S | 288 | month | 695 | 260.208 | Quote for the scisor lift of $695/month from Rapid City Supplier. 30% added |  |  |  | 65.052 | 65.052 | 65.052 | 65.052 |  |  | I&I MS | 0 | y
Patrick | 131.04.01.07 | Installation Tools | 1 | scaffolding rental/ (6 per 4 years) | M&S | 24 | scaffolding/y | 7500 | 234 | 4 rolling scaffolding inside cryostat and two outside |  |  |  | 58.5 | 58.5 | 58.5 | 58.5 |  |  | I&I MS | 0 | y
Dimitar | 131.04.01.07 | Installation Tools | 1 | machine shop | M&S | 1 | mech shop | 160000 | 208 | most old tools, few new. Simple estimation |  |  |  | 208 | [5 empty] | SDSD M&S | 0 | y
Marzio | 131.04.01.06 | Installation Tools | 2 | same as det1 | M&S |  |  |  | 1414.8823 | Infrastructure (131.04.01.06) | [5 empty] | 424.4647 | 424.4647 | 424.4647 | 141.4882 | I&I MS | 0 | y
Marzio | 131.04.01.07 | installation tools | 2 | same as det1 | M&S |  |  |  | 4041.3684 | Assembly tools (131.04.01.07) | [5 empty] | 1212.4105 | 1212.4105 | 1212.4105 | 404.1368 | I&I MS | 0 | y
Marzio | 131.04.01.07 | Installation Tools | 2 | reuse cold boxes, N2 | M&S |  | reuse |  | -1796.3 | Cold boxes, N2 system | [5 empty] | -1077.78 | -718.52 |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | N/A | Material Handling in cavern and transport from cavern to SAS | M&S | 2 | varia | 235332 | 470.664 | Fork lifts, pallet trucks, pallet racks, dolleys,etc. No 30%. See detailed information on https://edms.cern.ch/document/2217099 | [5 empty] | 470.664 |  |  |  | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | N/A | lifts for photon integration | M&S | 96 | month | 352.14 | 43.9471 | Rental of 2 lifts for 48 months. 30% added. See detailed information on https://edms.cern.ch/document/2217099 | [5 empty] | 10.9868 | 10.9868 | 10.9868 | 10.9868 | I&I MS | 0 | y
Jim / Bill | 131.04.01.07 | Installation Tools | N/A | electronics racks for testing | M&S | 1 | racks | 75186 | 97.7418 | Electronics racks for cold box 3, radk in barracks 2 one rack for testing in the CUC. Includes poer distribution network switch, smoke detector and power cutoff. 30% added. See detailed information on https://edms.cern.ch/document/2217147 | [5 empty] | 97.7418 |  |  |  | I&I MS | 0 | y
Marzio | 131.04.01.02 | Installation Tools | N/A | Benches for eating area outside cleanroom | M&S | 30 | desk | 900 | 35.1 | Basic estimation, 30% added to include substitution of brocken material | [5 empty] | 35.1 |  |  |  | SDSD M&S | 0 | y
Dimitar | 131.04.01.07 | Installation Tools | N/A | Areal Lift | M&S | 1 | lift | 133457.5 | 173.4948 | Pallazani in the cryostat. 27m. Catalogue price 140K$. 30% added. See detailed information on https://edms.cern.ch/document/2214878 |  |  | 173.4948 | [6 empty] | SDSD M&S | 0 | y
Patrick | 131.04.01.07 | Installation Tools | N/A | Lifts general service contract | M&S | 48 | month | 2400 | 149.76 | Service of all lift, fork lifts. 30% added. See detailed information on https://edms.cern.ch/document/ 2225282 | [5 empty] | 37.44 | 37.44 | 37.44 | 37.44 | SDSD M&S | 0 | y
|  | Computer Racks CUC | [7 empty] | 1739.4429
Giovanna | 131.04.01.02 | Computer Racks CUC | N/A | water cooled racks | M&S | 60 | rack | 8132 | 634.296 | Quote for 42U racks with simple PDUs; https://edms.cern.ch/document/2214199 ; https://edms.cern.ch/document/2214222 |  |  |  | 158.574 | 158.574 | 158.574 | 158.574 |  |  | I&I MS | 0 | y
Jack | 131.04.01.02 | Services Racks CUC | N/A | water distribution | M&S | 120 | m | 200 | 31.2 | simple estimation |  |  |  | 18.72 | 12.48 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.02 | Services Racks CUC | N/A | CUC DAQ AC Power | M&S | 1 | system | 165002 | 214.5026 | racks control units; overall power safety and fire extinguishing; other sensors included into racks cost; this does not include fire suppressant circuit outside racks ; https://edms.cern.ch/document/2214268 |  |  |  | 128.7016 | 85.801 |  |  |  |  | I&I MS | 0 | y
Giovanna | 131.04.01.02 | Services Racks CUC | N/A | controls and safety + leaks monitor | M&S | 60 | unit | 4730 | 368.94 | racks control units; overall power safety and fire extinguishing; other sensors included into racks cost; this does not include fire suppressant circuit outside racks |  |  |  | 221.364 | 147.576 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.02 | Services Racks CUC | N/A | cable trays and supports in CUC | M&S | 120 | m | 60.925 | 9.5043 | 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215441 |  |  |  | 5.7026 | 3.8017 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.02 | UPS in CUC | N/A | UPS for all DAQ | M&S | 1 | unit | 370000 | 481 | 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215441 |  |  |  | 288.6 | 192.4 |  |  |  |  | I&I MS | 0 | y
|  | Cables/Fibers/Power-cables |  | 399.112 | [5 empty] | 1158.8616
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | fibers bundles APA on the detector roof | M&S | 150 | 15m ribbon | 102 | 19.89 | 12 fibres cords OM3 terminated MTP12. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215450 |  |  |  | 11.934 | 7.956 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | pach panels for fibers APA | M&S | 25 | patch panel | 242 | 7.865 | on detector racks. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215456 |  |  |  | 4.719 | 3.146 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | fibers cords to DAQ room | M&S | 27 | 200m ribbon | 7844 | 275.3244 | 12 fibres cords OM3 terminated MTP12. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215451 |  |  |  | 165.1946 | 110.1298 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | ethernet cablesfrom DAQ room - det racks | M&S | 78 | 200m ribbon | 545 | 55.263 | 2 fibres cords OM3 terminated MTP12. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215455 |  |  |  | 33.1578 | 22.1052 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | control cables | M&S | 3000 | m | 3.1 | 12.09 | include connectors. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215675 |  |  |  | 7.254 | 4.836 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | power cables on the detector roof | M&S | 480 | m | 167.4 | 104.4576 | 4x ~120m including power panels and rack wiring. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215454 |  |  |  | 62.6746 | 41.783 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | power cables to tranformers | M&S | 480 | m | 97.2 | 60.6528 | include connectors. 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215453 |  |  |  | 36.3917 | 24.2611 |  |  |  |  | I&I MS | 0 | y
Terri | 131.04.01.06 | Cables/Fibers/Power-cables | 1 | transformers for ground decoupling | M&S | 4 | transf | 8440 | 43.888 | 30% added for additional tools. See detailed information on https://edms.cern.ch/document/2215452 |  |  |  | 26.3328 | 17.5552 |  |  |  |  | I&I MS | 0 | y
Marzio | 131.04.01.07 | Cables/Fibers/labor | 1 | installation 2 FTE per 1 year | Labor | 2 | FTE | 99778 | 199.556 | install all cables and connectors needed in situ. Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 139.6892 | 59.8668 |  |  |  |  | SDSD labor | 0 | y
Marzio | 131.04.01.07 | Cables/Fibers/labor | 2 | installation; same as det1 | Labor | 2 | FTE | 99778 | 199.556 | install all cables and connectors needed in situ. Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. | [5 empty] | 139.6892 | 59.8668 |  |  | SDSD labor | 0 | y
Terri | 131.04.01.07 | Cables/Fibers/Power-cables | 2 | M&S same as det1 | M&S |  |  |  | 579.4308 | [6 empty] | 405.6016 | 173.8292 |  |  | I&I MS | 0 | y
|  | Storage/offices/varia |  | 10739.072 | [5 empty] | 676.39
Jim | 131.04.01.02 | Storage/offices/varia | N/A | tools sets mechanis, optics | M&S | 2 | tools | 21235 | 55.211 | Tools for use in storage and cavern. 30% added. See detailed information on https://edms.cern.ch/document/ 2218848 |  |  | 55.211 | [6 empty] | I&I MS | 0 | y
Jim | 131.04.01.02 | Storage/offices/varia | N/A | tools electronics | M&S | 2 | varia | 81415 | 211.679 | Tools for use in storage and cavern. 30% added. See detailed information on https://edms.cern.ch/document/ 2218849 |  |  | 105.8395 | 105.8395 | [5 empty] | I&I MS | 0 | y
Jim | 131.04.01.02 | Storage/offices/varia | N/A | consumables | M&S | 7 | material | 45000 | 409.5 | simple estimation |  |  | 58.5 | 58.5 | 58.5 | 58.5 | 58.5 | 58.5 | 58.5 | I&I MS | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | offices in trailors complex | M&S | 7 | trailor | 70000 | 490 | Surface office space: https://shop.fsindustries.com/product/ov820-4e-gr-quick-ship-modular-office/134294. 30% added. See detailed information on https://edms.cern.ch/document/ 2225283 |  |  | 490 | [6 empty] | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | logistic software | M&S | 1 | unit | 50000 | 65 | simple estimation |  |  | 65 | [6 empty] | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | storage area rent (t0-2 to t0+4) | M&S | 7 | rent | 1000000 | 7000 | 20$/y/ftq, 5000 mq |  |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | transport storage/shaft | M&S | 6 | 1 truck/year | 374400 | 2246.4 | 1000$/day, 6 days/week. See detailed information on https://edms.cern.ch/document/ 2218842. Direct procurement might be competitive. |  |  |  | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | 374.4 | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | Porta-Potty Service | M&S | 20 | units | 6788.5 | 135.77 | with service. See detailed information on https://edms.cern.ch/document/ 2218850 |  |  | 135.77 | [6 empty] | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | Hand Washing Stations | M&S | 12 | units | 796 | 9.552 | 30% added. See detailed information on https://edms.cern.ch/document/ 2218851 |  |  | 9.552 | [6 empty] | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | Janitorial Service | M&S | 7 | years | 46800 | 327.6 | See detailed information on https://edms.cern.ch/document/ 2218965 |  |  | 46.8 | 46.8 | 46.8 | 46.8 | 46.8 | 46.8 | 46.8 | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | Trash/Recycling Service | M&S | 7 | years | 23400 | 163.8 | See detailed information on https://edms.cern.ch/document/ 2218970 |  |  | 23.4 | 23.4 | 23.4 | 23.4 | 23.4 | 23.4 | 23.4 | SDSD M&S | 0 | y
Patrick | 131.04.01.02 | Storage/offices/varia | N/A | Cardboard baler | M&S | 1 | unit | 25000 | 32.5 | 30% added.See detailed information on https://edms.cern.ch/document/ 2218974 |  |  | 32.5 | [6 empty] | SDSD M&S | 0 | y
Marzio | 131.04.01.02 | Storage/offices/varia | N/A | Metrology material | M&S | 2 | unit | 103250 | 268.45 | lasers theodolites, reflectors, software. 30% added, waiting for an offer. See detailed information on https://edms.cern.ch/document/ 2221988 |  |  | 268.45 | [6 empty] | SDSD M&S | 0 | y
|  | Tech Labor |  | 10376.8704 | [5 empty] | 10106.6496
Patrick | 131.04.01.02 | Tech Labor | 1 | crane drivers caverns (1 FTE 6 years) | Labor | 6 | FTE/year | 99777.6 | 598.6656 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 99.7776 | 99.7776 | 99.7776 | 99.7776 | 99.7776 | 99.7776 | SDSD labor | 0 | n
Patrick | 131.04.01.02 | Tech Labor | 1 | crane drivers caverns (5 FTE 6 years) | Labor | 30 | FTE/year | 99777.6 | 2993.328 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 498.888 | 498.888 | 498.888 | 498.888 | 498.888 | 498.888 | SDSD labor | 0 | y
Patrick | 131.04.01.07 | Tech Labor | 1 | core tecs crew (1 FTE, 4 years) | Labor | 4 | FTE/year | 99777.6 | 399.1104 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 99.7776 | 99.7776 | 99.7776 | 99.7776 |  |  | SDSD labor | 0 | n
Patrick | 131.04.01.07 | Tech Labor | 1 | core tecs crew (9 FTE, 4 years) | Labor | 36 | FTE/year | 99777.6 | 3591.9936 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 897.9984 | 897.9984 | 897.9984 | 897.9984 |  |  | I&I labor | 0 | y
Patrick | 131.04.01.07 | Tech Labor | 1 | construction managers (3 FTE,4 years) | Labor | 12 | FTE/year | 121777.6 | 1461.3312 | Non local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. + lodging 22k/y. No Labs overheads added here. |  |  |  | 365.3328 | 365.3328 | 365.3328 | 365.3328 |  |  | I&I labor | 0 | y
Patrick | 131.04.01.02 | Tech Labor | 2 | same as det1 SDSD | Labor |  |  |  | 3991.104 | [6 empty] | 997.776 | 997.776 | 997.776 | 997.776 | SDSD labor | 0
Patrick | 131.04.01.07 | Tech Labor | 2 | same as det1 I&I | Labor |  |  |  | 5053.3248 | [6 empty] | 1263.3312 | 1263.3312 | 1263.3312 | 1263.3312 | I&I labor | 0
Patrick | 131.04.01.02 | Tech Labor | N/A | storage core tecs crew (3 FTE, 8 years) | Labor | 24 | FTE/year | 99777.6 | 2394.6624 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  | 299.3328 | 299.3328 | 299.3328 | 299.3328 | 299.3328 | 299.3328 | 299.3328 | 299.3328 | SDSD labor | 0 | y
|  | Support Labor |  | 13655.9808
Patrick | 131.04.01.02 | Support Labor | N/A | Electrician on call (1 FTE, 6years) | Labor | 6 | FTE/year | 99777.6 | 598.6656 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 99.7776 | 99.7776 | 99.7776 | 99.7776 | 99.7776 | 99.7776 | SDSD labor | 0 | n
Patrick | 131.04.01.02 | Support Labor | N/A | Electrician on call (2 FTE, 6years) | Labor | 12 | FTE/year | 99777.6 | 1197.3312 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 199.5552 | 199.5552 | 199.5552 | 199.5552 | 199.5552 | 199.5552 | SDSD labor | 0 | y
Patrick | 131.04.01.02 | Support Labor | N/A | Ventil./water/network on call (1 FTE, 6years) | Labor | 6 | FTE/year | 99777.6 | 598.6656 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 99.7776 | 99.7776 | 99.7776 | 99.7776 | 99.7776 | 99.7776 | SDSD labor | 0 | n
Patrick | 131.04.01.02 | Support Labor | N/A | Ventil./water/network on call (2 FTE, 6years) | Labor | 12 | FTE/year | 99777.6 | 1197.3312 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 199.5552 | 199.5552 | 199.5552 | 199.5552 | 199.5552 | 199.5552 | SDSD labor | 0 | y
Patrick | 131.04.01.02 | Support Labor | N/A | Surveyors (2 FTE, 6 years) | Labor | 12 | FTE/year | 90000 | 1080 | Local staff employee, specialists (100K$/y, 40h/week). Based on Fermilab rates for A-5 mid point. No Labs overheads added here. |  |  |  | 180 | 180 | 180 | 180 | 180 | 180 | SDSD labor | 0 | y
Patrick | 131.04.01.02 | Support Labor | N/A | Transport crews to cavern (12 FTE,6years) | Labor | 72 | FTE/year | 99777.6 | 7183.9872 | Local staff employee, specialists (31.98$/h, 60h/w). Based on Fermilab rates for H-7 pay range zone 3 max. No Labs overheads added here. |  |  |  | 1197.3312 | 1197.3312 | 1197.3312 | 1197.3312 | 1197.3312 | 1197.3312 | SDSD labor | 0 | y
Patrick | 131.04.01.02 | Support Labor | N/A | Safety coordination (3 FTE,6 years) | Labor | 18 | FTE/year | 100000 | 1800 | Local staff employee, specialists (100K$/y,40h/week). Based on Fermilab rates for A-6 mid point. No Labs overheads added here. |  |  |  | 300 | 300 | 300 | 300 | 300 | 300 | SDSD labor | 0 | y
total
|  |  |  | SDSD M&S |  |  | 24242.6757 |  | cranes, infrstructure, control rooms, transport tools, storage
|  |  |  | SDSD labor |  |  | 25419.7614 |  | cryostat top, internal cryo, cables, tech labor, support labor
|  |  |  | I&I M&S |  |  | 24830.6249 |  | cryostat top, internal cryo, DSS, computer racks, cables, instalaltion tools,..
|  |  |  | I&I labor |  |  | 10106.6496 |  | tech labor
|  |  |  | total [K$] |  |  | 84599.7116

## US accounting 2019
| Last update | 2019-10-09
0.078 | hoverhead contracts
0.018 | hoverhead on large contracts
1.48 | hoverhead labor staff
0.1 | contingency for staff
0.2 | contingency for contracts
0.09 | escaltion 3 years
0.12 | escalation 4 years | [10 empty] | M$S[K$] | 74000.5743 | 0 | 930.1263 | 7089.2835 | 15336.7707 | 14289.3648 | 14428.7497 | 9970.5262 | 8189.403 | 3766.35
0.15 | escalaton 5 years | [10 empty] | labor[K$] | 107488.7092 | 0 | 905.6613 | 905.6613 | 14633.1246 | 14331.237 | 22123.3881 | 21700.7452 | 16444.4458 | 16444.4458
0.085 | SD tax | [10 empty] | total [kS] | 181489.2835 | 0 | 1835.7876 | 7994.9448 | 29969.8953 | 28620.6018 | 36552.1378 | 31671.2714 | 24633.8488 | 20210.7958
| totals [k$] |  |  | 84599.7116 |  | 13367.3012 |  | 10151.9654 |  | 69199.0748 |  | 4171.2305 | 181489.2835
R WBS | System | Detector | item | total CORE[k$] | coef | contingency | coef | escalation | coef | overhead | coef | SD tax | total | t0-3 | t0-2 | t0-1 | t0 | t0+1 | t0+2 | t0+3 | t0+4 | t0+5 | Responsibility | CHECK | US project y/n
| Cryostat Top Infrastructure | 1811.3226 | 6888.1649 | [FY19]
131.04.01.06 | Cryostat Top infrastructure | 1 | SS vertical tubes (feed thrus) | 34.177 | 0.2 | 6.8354 | 0.12 | 4.1012 | 0.078 | 3.5189 | 0.085 | 2.905 | 51.5375 |  |  |  | 51.5375 | [5 empty] | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | SS tubes flanges (feed thrus) | 173.992 | 0.2 | 34.7984 | 0.12 | 20.879 | 0.078 | 17.9142 | 0.085 | 14.7893 | 262.373 |  |  |  | 262.373 | [5 empty] | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | manholes | 33.8 | 0.2 | 6.76 | 0.12 | 4.056 | 0.078 | 3.48 | 0.085 | 2.873 | 50.969 |  |  |  | 50.969 | [5 empty] | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | gate valves on instrumentation ports | 111.2592 | 0.2 | 22.2518 | 0.12 | 13.3511 | 0.078 | 11.4552 | 0.085 | 9.457 | 167.7744 |  |  |  | 167.7744 | [5 empty] | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | structural supports for feed thrus | 9.477 | 0.2 | 1.8954 | 0.12 | 1.1372 | 0.078 | 0.97575 | 0.085 | 0.80555 | 14.2909 |  |  |  | 14.2909 | [5 empty] | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | gas exhaust pipe | 55.9 | 0.2 | 11.18 | 0.12 | 6.708 | 0.078 | 5.7555 | 0.085 | 4.7515 | 84.295 |  |  |  | 50.577 | 33.718 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | exhaust valves | 102.0357 | 0.2 | 20.4071 | 0.12 | 12.2443 | 0.078 | 10.5056 | 0.085 | 8.673 | 153.8658 |  |  |  | 92.3195 | 61.5463 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | flexibles to valves | 37.908 | 0.2 | 7.5816 | 0.12 | 4.549 | 0.078 | 3.903 | 0.085 | 3.2222 | 57.1637 |  |  |  | 34.2982 | 22.8655 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | exhaust valves soft pipe | 4.9192 | 0.2 | 0.98384 | 0.12 | 0.5903 | 0.078 | 0.50648 | 0.085 | 0.41813 | 7.418 |  |  |  | 4.4508 | 2.9672 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | exhaust valves fanout | 13.39 | 0.2 | 2.678 | 0.12 | 1.6068 | 0.078 | 1.3786 | 0.085 | 1.1382 | 20.1916 |  |  |  | 12.115 | 8.0766 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | gas analysers | 99.5384 | 0.2 | 19.9077 | 0.12 | 11.9446 | 0.078 | 10.2485 | 0.085 | 8.4608 | 150.0999 |  |  |  | 90.06 | 60.04 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | O2 trace analysers | 102.076 | 0.2 | 20.4152 | 0.12 | 12.2491 | 0.078 | 10.5097 | 0.085 | 8.6765 | 153.9265 |  |  |  | 92.3559 | 61.5706 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | primary pumps | 7.02 | 0.2 | 1.404 | 0.12 | 0.8424 | 0.078 | 0.72278 | 0.085 | 0.5967 | 10.5859 |  |  |  | 6.3515 | 4.2344 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | turbo pumps | 23.4 | 0.2 | 4.68 | 0.12 | 2.808 | 0.078 | 2.4093 | 0.085 | 1.989 | 35.2863 |  |  |  | 21.1718 | 14.1145 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | He leak checkers | 91.325 | 0.2 | 18.265 | 0.12 | 10.959 | 0.078 | 9.4028 | 0.085 | 7.7626 | 137.7144 |  |  |  | 82.6287 | 55.0858 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | vacuum tools | 19.5 | 0.2 | 3.9 | 0.12 | 2.34 | 0.078 | 2.0077 | 0.085 | 1.6575 | 29.4052 |  |  |  | 17.6431 | 11.7621 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | lights under the mezzanines | 7.8 | 0.2 | 1.56 | 0.12 | 0.936 | 0.078 | 0.80309 | 0.085 | 0.663 | 11.7621 |  |  |  | 7.0573 | 4.7048 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | V (power) cable trays + supports | 39.13 | 0.2 | 7.826 | 0.12 | 4.6956 | 0.078 | 4.0288 | 0.085 | 3.3261 | 59.0065 |  |  |  | 35.4039 | 23.6026 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | signals cable trays + supports | 39.13 | 0.2 | 7.826 | 0.12 | 4.6956 | 0.078 | 4.0288 | 0.085 | 3.3261 | 59.0065 |  |  |  | 35.4039 | 23.6026 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | copper grounding for the cable trays | 89.44 | 0.2 | 17.888 | 0.12 | 10.7328 | 0.078 | 9.2087 | 0.085 | 7.6024 | 134.8719 |  |  |  | 80.9232 | 53.9488 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure labor | 1 | specialized welders team det1 | 299.3328 | 0.1 | 29.9333 | 0.12 | 35.9199 | 1.48 | 540.4753 | 0 | 0 | 905.6613 |  |  |  | 543.3968 | 362.2645 |  |  |  |  | SDSD Labor | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | walking floor | 62.634 | 0.2 | 12.5268 | 0.12 | 7.5161 | 0.078 | 6.4488 | 0.085 | 5.3239 | 94.4496 |  |  |  |  | 94.4496 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | cable tray from CUC to racks mezzanine | 61.88 | 0.2 | 12.376 | 0.12 | 7.4256 | 0.078 | 6.3712 | 0.085 | 5.2598 | 93.3126 |  |  |  |  | 93.3126 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | power racks on mezzanine | 225.3108 | 0.2 | 45.0622 | 0.12 | 27.0373 | 0.078 | 23.198 | 0.085 | 19.1514 | 339.7597 |  |  |  |  | 339.7597 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | racks internal power distribution | 30.8256 | 0.2 | 6.1651 | 0.12 | 3.6991 | 0.078 | 3.1738 | 0.085 | 2.6202 | 46.4838 |  |  |  |  | 27.8903 | 18.5935 |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | racks controls + safety | 425.88 | 0.2 | 85.176 | 0.12 | 51.1056 | 0.078 | 43.8486 | 0.085 | 36.1998 | 642.21 |  |  |  |  | 385.326 | 256.884 |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | cryo vertical access doors | 274.56 | 0.2 | 54.912 | 0.12 | 32.9472 | 0.078 | 28.2687 | 0.085 | 23.3376 | 414.0255 |  |  |  |  | 248.4153 | 165.6102 |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | miniracks + supports | 43.875 | 0.2 | 8.775 | 0.12 | 5.265 | 0.078 | 4.5174 | 0.085 | 3.7294 | 66.1617 |  |  |  |  | 39.697 | 26.4647 |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | Water cryo traps | 52 | 0.2 | 10.4 | 0.12 | 6.24 | 0.078 | 5.3539 | 0.085 | 4.42 | 78.4139 | [6 empty] | 78.4139 |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 1 | valves for the GN2 insulation control | 11.752 | 0.2 | 2.3504 | 0.12 | 1.4102 | 0.078 | 1.21 | 0.085 | 0.99892 | 17.7215 | [5 empty] | 17.7215 |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure | 2 | M&S det2 same as det1 | 2283.9349 | 0.2 | 456.787 | 0.12 | 274.0722 | 0.078 | 235.1539 | 0.085 | 194.1345 | 3444.0825 | [5 empty] | 1377.633 | 1377.633 | 688.8165 |  | I&I MS | 0 | y
131.04.01.06 | Cryostat Top infrastructure labor | 2 | specialised welders team det2 | 299.3328 | 0.1 | 29.9333 | 0.12 | 35.9199 | 1.48 | 540.4753 | 0 | 0 | 905.6613 | [5 empty] | 543.3968 | 362.2645 |  |  | SDSD Labor | 0 | y
| Int Cryogenics | 1177.3597 | 2398.6779
131.04.01.06 | Int Cryogenics | 1 | pipes + fixations | 795.3387 | 0.2 | 159.0677 | 0.12 | 95.4406 | 0.078 | 81.8881 | 0.085 | 67.6038 | 1199.3389 |  |  |  |  | 1199.3389 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Int Cryogenics labor | 1 | assembly work 3 FTE for 6 months | 194.5663 | 0.1 | 19.4566 | 0.12 | 23.348 | 1.48 | 351.3089 | 0 | 0 | 588.6799 | [5 empty] | 588.6799 |  |  |  | SDSD Labor | 0 | y
131.04.01.06 | Int Cryogenics | 2 | pipes + fixations | 795.3387 | 0.2 | 159.0677 | 0.12 | 95.4406 | 0.078 | 81.8881 | 0.085 | 67.6038 | 1199.3389 | [5 empty] | 1199.3389 |  |  |  | I&I MS | 0 | y
131.04.01.06 | Int Cryogenics labor | 2 | assembly work 3 FTE for 6 months | 194.5663 | 0.1 | 19.4566 | 0.12 | 23.348 | 1.48 | 351.3089 | 0 | 0 | 588.6799 | [6 empty] | 588.6799 |  |  | SDSD Labor | 0 | y
| DSS |  | 7604.3036
131.04.01.06 | DSS | 1 | SS rails | 152.4432 | 0.2 | 30.4886 | 0.12 | 18.2932 | 0.078 | 15.6956 | 0.085 | 12.9577 | 229.8782 |  |  | 68.9635 | 68.9635 | 91.9513 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | DSS | 1 | rail supports + feedthroughs | 1303.302 | 0.2 | 260.6604 | 0.12 | 156.3962 | 0.078 | 134.188 | 0.085 | 110.7807 | 1965.3273 |  |  | 589.5982 | 589.5982 | 393.0655 | 393.0655 |  |  |  | I&I MS | 0 | y
131.04.01.06 | DSS | 1 | SS APA,CPA supports to rails and shuttle system | 438.75 | 0.2 | 87.75 | 0.12 | 52.65 | 0.078 | 45.1737 | 0.085 | 37.2938 | 661.6174 |  |  | 198.4852 | 198.4852 | 264.647 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | DSS | 1 | Installation equipment | 410.4087 | 0.2 | 82.0817 | 0.12 | 49.249 | 0.078 | 42.2557 | 0.085 | 34.8847 | 618.8799 |  |  | 185.664 | 185.664 | 247.552 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | DSS | 1 | installation test equipment, QA, and shipping stuff | 216.4838 | 0.2 | 43.2968 | 0.12 | 25.9781 | 0.078 | 22.2892 | 0.085 | 18.4011 | 326.4489 |  |  | 97.9347 | 97.9347 | 130.5796 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | DSS | 2 | same as det 1 | 2521.3877 | 0.2 | 504.2775 | 0.12 | 302.5665 | 0.078 | 259.6021 | 0.085 | 214.318 | 3802.1518 |  |  |  | 1140.6455 | 1140.6455 | 760.4304 | 760.4304 |  |  | I&I MS | 0 | y
| Cranes | 3194.9752
131.04.01.03 | Cranes | 1 | bridge crane | 370.5 | 0.2 | 74.1 | 0.12 | 44.46 | 0.078 | 38.1467 | 0.085 | 31.4925 | 558.6992 |  | 167.6098 | 167.6098 | 223.4797 | [5 empty] | SDSD M&S | 0 | y
131.04.01.03 | Hoists | 1 | individual hoists | 390 | 0.2 | 78 | 0.12 | 46.8 | 0.078 | 40.1544 | 0.085 | 33.15 | 588.1044 |  | 176.4313 | 176.4313 | 235.2418 | [5 empty] | SDSD M&S | 0 | y
131.04.01.03 | Cranes | 1 | Power line (150m) | 59.67 | 0.2 | 11.934 | 0.12 | 7.1604 | 0.078 | 6.1436 | 0.085 | 5.072 | 89.98 |  | 26.994 | 26.994 | 35.992 | [5 empty] | SDSD M&S | 0 | y
131.04.01.03 | Cranes | 1 | Installation of cranes, hoist, power lines and 1rst inspection | 187.2 | 0.2 | 37.44 | 0.12 | 22.464 | 0.078 | 19.2741 | 0.085 | 15.912 | 282.2901 |  | 84.687 | 84.687 | 112.916 | [5 empty] | SDSD M&S | 0 | y
131.04.01.03 | Cranes | 1 | small material (slings, …) | 52 | 0.2 | 10.4 | 0.12 | 6.24 | 0.078 | 5.3539 | 0.085 | 4.42 | 78.4139 |  | 23.5242 | 23.5242 | 31.3656 | [5 empty] | SDSD M&S | 0 | y
131.04.01.03 | Cranes | 2 | same as det1 | 1059.37 | 0.2 | 211.874 | 0.12 | 127.1244 | 0.078 | 109.0727 | 0.085 | 90.0464 | 1597.4876 |  |  | 479.2463 | 479.2463 | 638.995 |  |  |  |  | SDSD M&S | 0 | y
| Mecanical structures | 13192.6363
131.04.01.06 | Infrastructure | 1 | detector mezzanine | 293.8 | 0.2 | 58.76 | 0.12 | 35.256 | 0.078 | 30.2496 | 0.085 | 24.973 | 443.0386 |  |  | 132.9116 | 132.9116 | 177.2155 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | main bridge | 197.1047 | 0.2 | 39.4209 | 0.12 | 23.6526 | 0.078 | 20.2939 | 0.085 | 16.7539 | 297.226 |  |  | 89.1678 | 89.1678 | 118.8904 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | hand rails | 18.2 | 0.2 | 3.64 | 0.12 | 2.184 | 0.078 | 1.8739 | 0.085 | 1.547 | 27.4449 |  |  | 8.2335 | 8.2335 | 10.9779 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | connection cryostat-bridge | 38.5944 | 0.2 | 7.7189 | 0.12 | 4.6313 | 0.078 | 3.9737 | 0.085 | 3.2805 | 58.1988 |  |  | 17.4596 | 17.4596 | 23.2795 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | stair to 4910 | 61.75 | 0.2 | 12.35 | 0.12 | 7.41 | 0.078 | 6.3578 | 0.085 | 5.2488 | 93.1165 |  |  | 27.935 | 27.935 | 37.2466 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | stairs to mezzanines | 18.2 | 0.2 | 3.64 | 0.12 | 2.184 | 0.078 | 1.8739 | 0.085 | 1.547 | 27.4449 |  |  | 8.2335 | 8.2335 | 10.9779 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | Unforeseen facility modifications | 260 | 0.2 | 52 | 0.12 | 31.2 | 0.078 | 26.7696 | 0.085 | 22.1 | 392.0696 |  |  | 98.0174 | 98.0174 | 98.0174 | 98.0174 |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | licence engineering services | 234 | 0.2 | 46.8 | 0.12 | 28.08 | 0.078 | 24.0926 | 0.085 | 19.89 | 352.8626 |  |  | 88.2157 | 88.2157 | 88.2157 | 88.2157 |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | Compensation for lost of time to work | 2392 | 0.2 | 478.4 | 0.12 | 287.04 | 0.078 | 246.2803 | 0.085 | 203.32 | 3607.0403 |  | 450.88 | 450.88 | 450.88 | 450.88 | 450.88 | 450.88 | 450.88 | 450.88 | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | Alimak procurement | 486.2832 | 0.2 | 97.2566 | 0.12 | 58.354 | 0.078 | 50.0677 | 0.085 | 41.3341 | 733.2956 |  |  | 183.3239 | 183.3239 | 183.3239 | 183.3239 |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | Condensation prevention system | 224.9 | 0.2 | 44.98 | 0.12 | 26.988 | 0.078 | 23.1557 | 0.085 | 19.1165 | 339.1402 |  |  | 101.7421 | 101.7421 | 135.6561 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 1 | Grouting below cryostat | 149.5 | 0.2 | 29.9 | 0.12 | 17.94 | 0.078 | 15.3925 | 0.085 | 12.7075 | 225.44 |  |  | 67.632 | 67.632 | 90.176 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Infrastructure | 2 | same as det1 | 4374.3323 | 0.2 | 874.8665 | 0.12 | 524.9199 | 0.078 | 450.3813 | 0.085 | 371.8182 | 6596.3181 | [5 empty] | 2638.5273 | 1978.8954 | 1978.8954 |  | SDSD M&S | 0 | y
| Control Rooms | 325.7194 | 805.3313
131.04.01.03 | Control Rooms | N/A | screens in cntrl | 19.24 | 0.2 | 3.848 | 0.12 | 2.3088 | 0.078 | 1.981 | 0.085 | 1.6354 | 29.0132 | [5 empty] | 14.5066 | 14.5066 |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | N/A | computers in cntrl | 52.3575 | 0.2 | 10.4715 | 0.12 | 6.2829 | 0.078 | 5.3907 | 0.085 | 4.4504 | 78.953 | [5 empty] | 39.4765 | 39.4765 |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | N/A | power distribution in cntrl | 4.55 | 0.2 | 0.91 | 0.12 | 0.546 | 0.078 | 0.46847 | 0.085 | 0.38675 | 6.8612 | [5 empty] | 3.4306 | 3.4306 |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | N/A | Net distribution in cavern/wifi | 394.05 | 0.2 | 78.81 | 0.12 | 47.286 | 0.078 | 40.5714 | 0.085 | 33.4943 | 594.2116 | [5 empty] | 297.1058 | 297.1058 |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | N/A | tables and chairs | 27 | 0.2 | 5.4 | 0.12 | 3.24 | 0.078 | 2.7799 | 0.085 | 2.295 | 40.7149 | [5 empty] | 20.3575 | 20.3575 |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | N/A | fire life safety/ barack | 11.856 | 0.2 | 2.3712 | 0.12 | 1.4227 | 0.078 | 1.2207 | 0.085 | 1.0078 | 17.8784 | [5 empty] | 8.9392 | 8.9392 |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | 1 | det 1 cryo room (cpu, screens, table) | 12.5 | 0.2 | 2.5 | 0.12 | 1.5 | 0.078 | 1.287 | 0.085 | 1.0625 | 18.8495 |  |  |  |  | 9.4247 | 9.4247 |  |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | 2 | det 2 cryo room (cpu, screens, table) | 12.5 | 0.2 | 2.5 | 0.12 | 1.5 | 0.078 | 1.287 | 0.085 | 1.0625 | 18.8495 |  |  |  |  | 9.4247 | 9.4247 |  |  |  | I&I MS | 0 | y
131.04.01.03 | Control Rooms | 1 | baracks cryo 1+ light + power + desks | 108 | 0.2 | 21.6 | 0.12 | 12.96 | 0.078 | 11.1197 | 0.085 | 9.18 | 162.8597 |  |  |  |  | 81.4298 | 81.4298 |  |  |  | SDSD M&S | 0 | y
131.04.01.03 | Control Rooms | 2 | baracks cryo 2+ light + power + desks | 108 | 0.2 | 21.6 | 0.12 | 12.96 | 0.078 | 11.1197 | 0.085 | 9.18 | 162.8597 | [5 empty] | 81.4298 | 81.4298 |  |  | SDSD M&S | 0 | y
| Transport Tools | 2795.5231
131.04.01.02 | Transport Tools | N/A | engines | 155.0029 | 0.2 | 31.0006 | 0.12 | 18.6003 | 0.078 | 15.9591 | 0.085 | 13.1752 | 233.7382 |  |  |  | 140.2429 | 93.4953 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.02 | Transport Tools | N/A | wagons | 140.4 | 0.2 | 28.08 | 0.12 | 16.848 | 0.078 | 14.4556 | 0.085 | 11.934 | 211.7176 |  |  |  | 127.0306 | 84.687 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.02 | Transport Tools | N/A | mobile crane at shaft botton | 94.9 | 0.2 | 18.98 | 0.12 | 11.388 | 0.078 | 9.7709 | 0.085 | 8.0665 | 143.1054 |  |  |  | 85.8632 | 57.2422 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.02 | Transport Tools | N/A | headframe transport tools telehandler rental | 187.2 | 0.2 | 37.44 | 0.12 | 22.464 | 0.078 | 19.2741 | 0.085 | 15.912 | 282.2901 |  |  |  | 169.3741 | 112.916 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.02 | Transport Tools | N/A | headframe transport tools forklift rental | 300.3 | 0.2 | 60.06 | 0.12 | 36.036 | 0.078 | 30.9189 | 0.085 | 25.5255 | 452.8404 |  |  |  | 271.7042 | 181.1362 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.02 | Transport Tools | N/A | headframe transport tools forklift purchase | 130 | 0.2 | 26 | 0.12 | 15.6 | 0.078 | 13.3848 | 0.085 | 11.05 | 196.0348 |  |  |  | 117.6209 | 78.4139 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.02 | Transport Tools | N/A | All terrain pallet jack for surface | 24.7 | 0.2 | 4.94 | 0.12 | 2.964 | 0.078 | 2.5431 | 0.085 | 2.0995 | 37.2466 |  |  |  | 11.174 | 11.174 | 7.4493 | 7.4493 |  |  | SDSD M&S | 0 | y
131.04.01.07 | Installation Tools | N/A | Cold box access lift | 100 | 0.2 | 20 | 0.12 | 12 | 0.078 | 10.296 | 0.085 | 8.5 | 150.796 |  |  |  | 90.4776 | 60.3184 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.06 | Installation Tools | N/A | ventilation system top man holes | 136.344 | 0.2 | 27.2688 | 0.12 | 16.3613 | 0.078 | 14.038 | 0.085 | 11.5892 | 205.6013 |  |  |  | 123.3608 | 82.2405 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.07 | Installation Tools | N/A | cold boxes | 468 | 0.2 | 93.6 | 0.12 | 56.16 | 0.078 | 48.1853 | 0.085 | 39.78 | 705.7253 |  |  |  | 423.4352 | 282.2901 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.07 | Installation Tools | N/A | N2 system for cold boxes | 67.6 | 0.2 | 13.52 | 0.12 | 8.112 | 0.078 | 6.9601 | 0.085 | 5.746 | 101.9381 |  |  |  | 61.1629 | 40.7752 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.07 | Installation Tools | N/A | CPA assembly tower/frame | 39 | 0.2 | 7.8 | 0.12 | 4.68 | 0.078 | 4.0154 | 0.085 | 3.315 | 58.8104 |  |  |  | 35.2863 | 23.5242 |  |  |  |  | SDSD M&S | 0 | y
131.04.01.07 | Installation Tools | N/A | APA cable installation infrastructure | 10.3974 | 0.2 | 2.0795 | 0.12 | 1.2477 | 0.078 | 1.0705 | 0.085 | 0.88378 | 15.6789 |  |  |  | 9.4073 | 6.2715 |  |  |  |  | SDSD M&S | 0 | y
| Installation Tools | 854.0403 | 14356.615
131.04.01.06 | Installation Tools | 1 | basic clean room structure (metallic str.) | 224.0901 | 0.2 | 44.818 | 0.12 | 26.8908 | 0.078 | 23.0723 | 0.085 | 19.0477 | 337.9189 |  |  |  | 202.7513 | 135.1676 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | basic clean room structure(walls) | 135.2 | 0.2 | 27.04 | 0.12 | 16.224 | 0.078 | 13.9202 | 0.085 | 11.492 | 203.8762 |  |  |  | 122.3257 | 81.5505 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | basic clean room structure(doors) | 10.14 | 0.2 | 2.028 | 0.12 | 1.2168 | 0.078 | 1.044 | 0.085 | 0.8619 | 15.2907 |  |  |  | 9.1744 | 6.1163 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | clean room infrastructure | 490.4393 | 0.2 | 98.0879 | 0.12 | 58.8527 | 0.078 | 50.4956 | 0.085 | 41.6873 | 739.5628 |  |  |  | 443.7377 | 295.8251 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | large platforms | 81.77 | 0.2 | 16.354 | 0.12 | 9.8124 | 0.078 | 8.419 | 0.085 | 6.9505 | 123.3059 |  |  |  | 73.9835 | 49.3224 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | personnel SAS outfitting | 52.998 | 0.2 | 10.5996 | 0.12 | 6.3598 | 0.078 | 5.4567 | 0.085 | 4.5048 | 79.9189 |  |  |  | 79.9189 | [5 empty] | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | internal bridge crane | 89.7 | 0.2 | 17.94 | 0.12 | 10.764 | 0.078 | 9.2355 | 0.085 | 7.6245 | 135.264 |  |  |  | 81.1584 | 54.1056 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | external rails (DSS type) + fixations | 22.685 | 0.2 | 4.537 | 0.12 | 2.7222 | 0.078 | 2.3356 | 0.085 | 1.9282 | 34.2081 |  |  |  | 20.5248 | 13.6832 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | Cold box access lift | 72.839 | 0.2 | 14.5678 | 0.12 | 8.7407 | 0.078 | 7.4995 | 0.085 | 6.1913 | 109.8383 |  |  |  | 109.8383 | [5 empty] | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | ventilation system top man holes | 54.34 | 0.2 | 10.868 | 0.12 | 6.5208 | 0.078 | 5.5948 | 0.085 | 4.6189 | 81.9425 |  |  |  | 81.9425 | [5 empty] | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | cold boxes | 690.3 | 0.2 | 138.06 | 0.12 | 82.836 | 0.078 | 71.0733 | 0.085 | 58.6755 | 1040.9448 |  |  |  | 624.5669 | 416.3779 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | N2 system for cold boxes | 1106 | 0.2 | 221.2 | 0.12 | 132.72 | 0.078 | 113.8738 | 0.085 | 94.01 | 1667.8038 |  |  |  | 1000.6823 | 667.1215 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | CPA assembly tower/frame | 52 | 0.2 | 10.4 | 0.12 | 6.24 | 0.078 | 5.3539 | 0.085 | 4.42 | 78.4139 |  |  |  | 47.0484 | 31.3656 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | APA cable installation infrastructure | 42.7882 | 0.2 | 8.5576 | 0.12 | 5.1346 | 0.078 | 4.4055 | 0.085 | 3.637 | 64.5229 |  |  |  | 38.7137 | 25.8092 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | cryostat lights+filters | 29.3241 | 0.2 | 5.8648 | 0.12 | 3.5189 | 0.078 | 3.0192 | 0.085 | 2.4925 | 44.2196 |  |  |  | 26.5317 | 17.6878 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | temporary power distribution | 34.8036 | 0.2 | 6.9607 | 0.12 | 4.1764 | 0.078 | 3.5834 | 0.085 | 2.9583 | 52.4824 |  |  |  | 31.4895 | 20.993 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | various mech. tools | 114.7042 | 0.2 | 22.9408 | 0.12 | 13.7645 | 0.078 | 11.8099 | 0.085 | 9.7499 | 172.9693 |  |  |  | 103.7816 | 69.1877 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | Cleanroom safety tools (PPE,ODH, fire, …) | 171.145 | 0.2 | 34.229 | 0.12 | 20.5374 | 0.078 | 17.6211 | 0.085 | 14.5473 | 258.0798 | [5 empty] | 180.6559 | 77.4239 |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | consumables, small items / 2 years 2 detectors | 405.976 | 0.2 | 81.1952 | 0.12 | 48.7171 | 0.078 | 41.7993 | 0.085 | 34.508 | 612.1956 | [5 empty] | 153.0489 | 153.0489 | 153.0489 | 153.0489 | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | clean room initial cleaning | 145.6 | 0.2 | 29.12 | 0.12 | 17.472 | 0.078 | 14.991 | 0.085 | 12.376 | 219.559 | [5 empty] | 109.7795 |  | 109.7795 |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | spare parts | 195 | 0.2 | 39 | 0.12 | 23.4 | 0.078 | 20.0772 | 0.085 | 16.575 | 294.0522 | [5 empty] | 205.8365 | 88.2157 |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | electrical diagnostics equipment | 205.193 | 0.2 | 41.0386 | 0.12 | 24.6232 | 0.078 | 21.1267 | 0.085 | 17.4414 | 309.4228 | [5 empty] | 216.596 | 92.8269 |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | installation storage equipment | 61.932 | 0.2 | 12.3864 | 0.12 | 7.4318 | 0.078 | 6.3765 | 0.085 | 5.2642 | 93.391 | [5 empty] | 65.3737 | 28.0173 |  |  | I&I MS | 0 | y
131.04.01.06 | Installation Tools | 1 | floor inside cryostat + supports | 265.0752 | 0.2 | 53.015 | 0.12 | 31.809 | 0.078 | 27.2921 | 0.085 | 22.5314 | 399.7228 |  |  |  |  | 279.806 | 119.9168 |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | scissor lifts rental (6 per 48 months) | 260.208 | 0.2 | 52.0416 | 0.12 | 31.225 | 0.078 | 26.791 | 0.085 | 22.1177 | 392.3833 |  |  |  | 98.0958 | 98.0958 | 98.0958 | 98.0958 |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | scaffolding rental/ (6 per 4 years) | 234 | 0.2 | 46.8 | 0.12 | 28.08 | 0.078 | 24.0926 | 0.085 | 19.89 | 352.8626 |  |  |  | 88.2157 | 88.2157 | 88.2157 | 88.2157 |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 1 | machine shop | 208 | 0.2 | 41.6 | 0.12 | 24.96 | 0.078 | 21.4157 | 0.085 | 17.68 | 313.6557 |  |  |  | 313.6557 | [5 empty] | SDSD M&S | 0 | y
131.04.01.06 | Installation Tools | 2 | same as det1 | 1414.8823 | 0.2 | 282.9765 | 0.12 | 169.7859 | 0.078 | 145.6763 | 0.085 | 120.265 | 2133.5859 | [5 empty] | 640.0758 | 640.0758 | 640.0758 | 213.3586 | I&I MS | 0 | y
131.04.01.07 | installation tools | 2 | same as det1 | 4041.3684 | 0.2 | 808.2737 | 0.12 | 484.9642 | 0.078 | 416.0993 | 0.085 | 343.5163 | 6094.2219 | [5 empty] | 1828.2666 | 1828.2666 | 1828.2666 | 609.4222 | I&I MS | 0 | y
131.04.01.07 | Installation Tools | 2 | reuse cold boxes, N2 | -1796.3 | 0.2 | -359.26 | 0.12 | -215.556 | 0.078 | -184.947 | 0.085 | -152.6855 | -2708.7485 | [5 empty] | -1625.2491 | -1083.4994 |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | N/A | Material Handling in cavern and transport from cavern to SAS | 470.664 | 0.2 | 94.1328 | 0.12 | 56.4797 | 0.078 | 48.4596 | 0.085 | 40.0064 | 709.7425 | [5 empty] | 709.7425 |  |  |  | I&I MS | 0 | y
131.04.01.07 | Installation Tools | N/A | lifts for photon integration | 43.9471 | 0.2 | 8.7894 | 0.12 | 5.2736 | 0.078 | 4.5248 | 0.085 | 3.7355 | 66.2704 | [5 empty] | 16.5676 | 16.5676 | 16.5676 | 16.5676 | I&I MS | 0 | y
131.04.01.07 | Installation Tools | N/A | electronics racks for testing | 97.7418 | 0.2 | 19.5484 | 0.12 | 11.729 | 0.078 | 10.0635 | 0.085 | 8.3081 | 147.3907 | [5 empty] | 147.3907 |  |  |  | I&I MS | 0 | y
131.04.01.02 | Installation Tools | N/A | Benches for eating area outside cleanroom | 35.1 | 0.2 | 7.02 | 0.12 | 4.212 | 0.078 | 3.6139 | 0.085 | 2.9835 | 52.9294 | [5 empty] | 52.9294 |  |  |  | SDSD M&S | 0 | y
131.04.01.07 | Installation Tools | N/A | Areal Lift | 173.4948 | 0.2 | 34.699 | 0.12 | 20.8194 | 0.078 | 17.863 | 0.085 | 14.7471 | 261.6231 |  |  | 261.6231 | [6 empty] | SDSD M&S | 0 | y
131.04.01.07 | Installation Tools | N/A | Lifts general service contract | 149.76 | 0.2 | 29.952 | 0.12 | 17.9712 | 0.078 | 15.4193 | 0.085 | 12.7296 | 225.8321 | [5 empty] | 56.458 | 56.458 | 56.458 | 56.458 | SDSD M&S | 0 | y
| Computer Racks CUC |  | 2623.0103
131.04.01.02 | Computer Racks CUC | N/A | water cooled racks | 634.296 | 0.2 | 126.8592 | 0.12 | 76.1155 | 0.078 | 65.3071 | 0.085 | 53.9152 | 956.493 |  |  |  | 239.1232 | 239.1232 | 239.1232 | 239.1232 |  |  | I&I MS | 0 | y
131.04.01.02 | Services Racks CUC | N/A | water distribution | 31.2 | 0.2 | 6.24 | 0.12 | 3.744 | 0.078 | 3.2124 | 0.085 | 2.652 | 47.0484 |  |  |  | 28.229 | 18.8193 |  |  |  |  | I&I MS | 0 | y
131.04.01.02 | Services Racks CUC | N/A | CUC DAQ AC Power | 214.5026 | 0.2 | 42.9005 | 0.12 | 25.7403 | 0.078 | 22.0852 | 0.085 | 18.2327 | 323.4613 |  |  |  | 194.0768 | 129.3845 |  |  |  |  | I&I MS | 0 | y
131.04.01.02 | Services Racks CUC | N/A | controls and safety + leaks monitor | 368.94 | 0.2 | 73.788 | 0.12 | 44.2728 | 0.078 | 37.9861 | 0.085 | 31.3599 | 556.3468 |  |  |  | 333.8081 | 222.5387 |  |  |  |  | I&I MS | 0 | y
131.04.01.02 | Services Racks CUC | N/A | cable trays and supports in CUC | 9.5043 | 0.2 | 1.9009 | 0.12 | 1.1405 | 0.078 | 0.97856 | 0.085 | 0.80787 | 14.3321 |  |  |  | 8.5993 | 5.7328 |  |  |  |  | I&I MS | 0 | y
131.04.01.02 | UPS in CUC | N/A | UPS for all DAQ | 481 | 0.2 | 96.2 | 0.12 | 57.72 | 0.078 | 49.5238 | 0.085 | 40.885 | 725.3288 |  |  |  | 435.1973 | 290.1315 |  |  |  |  | I&I MS | 0 | y
| Cables/Fibers/Power-cables | 1207.5533 | 1747.5169
131.04.01.06 | Cables/Fibers/Power-cables | 1 | fibers bundles APA on the detector roof | 19.89 | 0.2 | 3.978 | 0.12 | 2.3868 | 0.078 | 2.0479 | 0.085 | 1.6907 | 29.9933 |  |  |  | 17.996 | 11.9973 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cables/Fibers/Power-cables | 1 | pach panels for fibers APA | 7.865 | 0.2 | 1.573 | 0.12 | 0.9438 | 0.078 | 0.80978 | 0.085 | 0.66853 | 11.8601 |  |  |  | 7.1161 | 4.744 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cables/Fibers/Power-cables | 1 | fibers cords to DAQ room | 275.3244 | 0.2 | 55.0649 | 0.12 | 33.0389 | 0.078 | 28.3474 | 0.085 | 23.4026 | 415.1782 |  |  |  | 249.1069 | 166.0713 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cables/Fibers/Power-cables | 1 | ethernet cablesfrom DAQ room - det racks | 55.263 | 0.2 | 11.0526 | 0.12 | 6.6316 | 0.078 | 5.6899 | 0.085 | 4.6974 | 83.3344 |  |  |  | 50.0006 | 33.3338 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cables/Fibers/Power-cables | 1 | control cables | 12.09 | 0.2 | 2.418 | 0.12 | 1.4508 | 0.078 | 1.2448 | 0.085 | 1.0276 | 18.2312 |  |  |  | 10.9387 | 7.2925 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cables/Fibers/Power-cables | 1 | power cables on the detector roof | 104.4576 | 0.2 | 20.8915 | 0.12 | 12.5349 | 0.078 | 10.755 | 0.085 | 8.8789 | 157.5179 |  |  |  | 94.5107 | 63.0072 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cables/Fibers/Power-cables | 1 | power cables to tranformers | 60.6528 | 0.2 | 12.1306 | 0.12 | 7.2783 | 0.078 | 6.2448 | 0.085 | 5.1555 | 91.462 |  |  |  | 54.8772 | 36.5848 |  |  |  |  | I&I MS | 0 | y
131.04.01.06 | Cables/Fibers/Power-cables | 1 | transformers for ground decoupling | 43.888 | 0.2 | 8.7776 | 0.12 | 5.2666 | 0.078 | 4.5187 | 0.085 | 3.7305 | 66.1813 |  |  |  | 39.7088 | 26.4725 |  |  |  |  | I&I MS | 0 | y
131.04.01.07 | Cables/Fibers/labor | 1 | installation 2 FTE per 1 year | 199.556 | 0.1 | 19.9556 | 0.12 | 23.9467 | 1.48 | 360.3183 | 0 | 0 | 603.7766 |  |  |  | 362.266 | 241.5107 |  |  |  |  | SDSD labor | 0 | y
131.04.01.07 | Cables/Fibers/labor | 2 | installation; same as det1 | 199.556 | 0.1 | 19.9556 | 0.12 | 23.9467 | 1.48 | 360.3183 | 0 | 0 | 603.7766 | [5 empty] | 422.6436 | 181.133 |  |  | SDSD labor | 0 | y
131.04.01.07 | Cables/Fibers/Power-cables | 2 | M&S same as det1 | 579.4308 | 0.2 | 115.8862 | 0.12 | 69.5317 | 0.078 | 59.6582 | 0.085 | 49.2516 | 873.7585 | [5 empty] | 611.6309 | 262.1275 |  |  | I&I MS | 0 | y
| Storage/offices/varia | 16194.091 | 1019.9691
131.04.01.02 | Storage/offices/varia | N/A | tools sets mechanis, optics | 55.211 | 0.2 | 11.0422 | 0.12 | 6.6253 | 0.078 | 5.6845 | 0.085 | 4.6929 | 83.256 |  |  | 83.256 | [6 empty] | I&I MS | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | tools electronics | 211.679 | 0.2 | 42.3358 | 0.12 | 25.4015 | 0.078 | 21.7945 | 0.085 | 17.9927 | 319.2035 |  |  | 159.6017 | 159.6017 | [5 empty] | I&I MS | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | consumables | 409.5 | 0.2 | 81.9 | 0.12 | 49.14 | 0.078 | 42.1621 | 0.085 | 34.8075 | 617.5096 |  |  | 88.2157 | 88.2157 | 88.2157 | 88.2157 | 88.2157 | 88.2157 | 88.2157 | I&I MS | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | offices in trailors complex | 490 | 0.2 | 98 | 0.12 | 58.8 | 0.078 | 50.4504 | 0.085 | 41.65 | 738.9004 |  |  | 738.9004 | [6 empty] | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | logistic software | 65 | 0.2 | 13 | 0.12 | 7.8 | 0.078 | 6.6924 | 0.085 | 5.525 | 98.0174 |  |  | 98.0174 | [6 empty] | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | storage area rent (t0-2 to t0+4) | 7000 | 0.2 | 1400 | 0.12 | 840 | 0.078 | 720.72 | 0.085 | 595 | 10555.72 |  |  | 1507.96 | 1507.96 | 1507.96 | 1507.96 | 1507.96 | 1507.96 | 1507.96 | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | transport storage/shaft | 2246.4 | 0.2 | 449.28 | 0.12 | 269.568 | 0.078 | 231.2893 | 0.085 | 190.944 | 3387.4813 |  |  |  | 564.5802 | 564.5802 | 564.5802 | 564.5802 | 564.5802 | 564.5802 | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | Porta-Potty Service | 135.77 | 0.2 | 27.154 | 0.12 | 16.2924 | 0.078 | 13.9789 | 0.085 | 11.5405 | 204.7357 |  |  | 204.7357 | [6 empty] | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | Hand Washing Stations | 9.552 | 0.2 | 1.9104 | 0.12 | 1.1462 | 0.078 | 0.98347 | 0.085 | 0.81192 | 14.404 |  |  | 14.404 | [6 empty] | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | Janitorial Service | 327.6 | 0.2 | 65.52 | 0.12 | 39.312 | 0.078 | 33.7297 | 0.085 | 27.846 | 494.0077 |  |  | 70.5725 | 70.5725 | 70.5725 | 70.5725 | 70.5725 | 70.5725 | 70.5725 | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | Trash/Recycling Service | 163.8 | 0.2 | 32.76 | 0.12 | 19.656 | 0.078 | 16.8648 | 0.085 | 13.923 | 247.0038 |  |  | 35.2863 | 35.2863 | 35.2863 | 35.2863 | 35.2863 | 35.2863 | 35.2863 | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | Cardboard baler | 32.5 | 0.2 | 6.5 | 0.12 | 3.9 | 0.078 | 3.3462 | 0.085 | 2.7625 | 49.0087 |  |  | 49.0087 | [6 empty] | SDSD M&S | 0 | y
131.04.01.02 | Storage/offices/varia | N/A | Metrology material | 268.45 | 0.2 | 53.69 | 0.12 | 32.214 | 0.078 | 27.6396 | 0.085 | 22.8182 | 404.8119 |  |  | 404.8119 | [6 empty] | SDSD M&S | 0 | y
| Tech Labor | 31396.2591 | 30578.679
131.04.01.02 | Tech Labor | 1 | crane drivers caverns (1 FTE 6 years) | 598.6656 | 0.1 | 59.8666 | 0.12 | 71.8399 | 1.48 | 1080.9506 | 0 | 0 | 1811.3226 |  |  |  | 301.8871 | 301.8871 | 301.8871 | 301.8871 | 301.8871 | 301.8871 | SDSD labor | 0 | n
131.04.01.02 | Tech Labor | 1 | crane drivers caverns (5 FTE 6 years) | 2993.328 | 0.1 | 299.3328 | 0.12 | 359.1994 | 1.48 | 5404.753 | 0 | 0 | 9056.6132 |  |  |  | 1509.4355 | 1509.4355 | 1509.4355 | 1509.4355 | 1509.4355 | 1509.4355 | SDSD labor | 0 | y
131.04.01.07 | Tech Labor | 1 | core tecs crew (1 FTE, 4 years) | 399.1104 | 0.1 | 39.911 | 0.12 | 47.8932 | 1.48 | 720.6337 | 0 | 0 | 1207.5484 |  |  |  | 301.8871 | 301.8871 | 301.8871 | 301.8871 |  |  | SDSD labor | 0 | n
131.04.01.07 | Tech Labor | 1 | core tecs crew (9 FTE, 4 years) | 3591.9936 | 0.1 | 359.1994 | 0.12 | 431.0392 | 1.48 | 6485.7036 | 0 | 0 | 10867.9358 |  |  |  | 2716.984 | 2716.984 | 2716.984 | 2716.984 |  |  | I&I labor | 0 | y
131.04.01.07 | Tech Labor | 1 | construction managers (3 FTE,4 years) | 1461.3312 | 0.1 | 146.1331 | 0.12 | 175.3597 | 1.48 | 2638.5796 | 0 | 0 | 4421.4037 |  |  |  | 1105.3509 | 1105.3509 | 1105.3509 | 1105.3509 |  |  | I&I labor | 0 | y
131.04.01.02 | Tech Labor | 2 | same as det1 SDSD | 3991.104 | 0.1 | 399.1104 | 0.12 | 478.9325 |  | 7206.3374 | 0 | 0 | 12075.4843 | [5 empty] | 3018.8711 | 3018.8711 | 3018.8711 | 3018.8711 | SDSD labor | 0
131.04.01.07 | Tech Labor | 2 | same as det1 I&I | 5053.3248 | 0.1 | 505.3325 | 0.12 | 606.399 |  | 9124.2833 | 0 | 0 | 15289.3395 | [5 empty] | 3822.3349 | 3822.3349 | 3822.3349 | 3822.3349 | I&I labor | 0
131.04.01.02 | Tech Labor | N/A | storage core tecs crew (3 FTE, 8 years) | 2394.6624 | 0.1 | 239.4662 | 0.12 | 287.3595 | 1.48 | 4323.8024 | 0 | 0 | 7245.2906 |  | 905.6613 | 905.6613 | 905.6613 | 905.6613 | 905.6613 | 905.6613 | 905.6613 | 905.6613 | SDSD labor | 0 | y
0
| Support Labor | 41317.5355 | [22 empty] | 0
131.04.01.02 | Support Labor | N/A | Electrician on call (1 FTE, 6years) | 598.6656 | 0.1 | 59.8666 | 0.12 | 71.8399 | 1.48 | 1080.9506 | 0 | 0 | 1811.3226 |  |  |  | 301.8871 | 301.8871 | 301.8871 | 301.8871 | 301.8871 | 301.8871 | SDSD labor | 0 | n
131.04.01.02 | Support Labor | N/A | Electrician on call (2 FTE, 6years) | 1197.3312 | 0.1 | 119.7331 | 0.12 | 143.6797 | 1.48 | 2161.9012 | 0 | 0 | 3622.6453 |  |  |  | 603.7742 | 603.7742 | 603.7742 | 603.7742 | 603.7742 | 603.7742 | SDSD labor | 0 | y
131.04.01.02 | Support Labor | N/A | Ventil./water/network on call (1 FTE, 6years) | 598.6656 | 0.1 | 59.8666 | 0.12 | 71.8399 | 1.48 | 1080.9506 | 0 | 0 | 1811.3226 |  |  |  | 301.8871 | 301.8871 | 301.8871 | 301.8871 | 301.8871 | 301.8871 | SDSD labor | 0 | n
131.04.01.02 | Support Labor | N/A | Ventil./water/network on call (2 FTE, 6years) | 1197.3312 | 0.1 | 119.7331 | 0.12 | 143.6797 | 1.48 | 2161.9012 | 0 | 0 | 3622.6453 |  |  |  | 603.7742 | 603.7742 | 603.7742 | 603.7742 | 603.7742 | 603.7742 | SDSD labor | 0 | y
131.04.01.02 | Support Labor | N/A | Surveyors (2 FTE, 6 years) | 1080 | 0.1 | 108 | 0.12 | 129.6 | 1.48 | 1950.048 | 0 | 0 | 3267.648 |  |  |  | 544.608 | 544.608 | 544.608 | 544.608 | 544.608 | 544.608 | SDSD labor | 0 | y
131.04.01.02 | Support Labor | N/A | Transport crews to cavern (12 FTE,6years) | 7183.9872 | 0.1 | 718.3987 | 0.12 | 862.0785 | 1.48 | 12971.4073 | 0 | 0 | 21735.8717 |  |  |  | 3622.6453 | 3622.6453 | 3622.6453 | 3622.6453 | 3622.6453 | 3622.6453 | SDSD labor | 0 | y
131.04.01.02 | Support Labor | N/A | Safety coordination (3 FTE,6 years) | 1800 | 0.1 | 180 | 0.12 | 216 | 1.48 | 3250.08 | 0 | 0 | 5446.08 |  |  |  | 907.68 | 907.68 | 907.68 | 907.68 | 907.68 | 907.68 | SDSD labor | 0 | y
|  |  | SDSD M&S | 36556.9852 |  |  |  |  | cranes, infrstructure, control rooms, transport tools, storage
|  |  | SDSD labor | 72713.7946 |  |  |  |  | cryostat top, internal cryo, cables, tech labor, support labor
|  |  | I&I M&S | 37443.5891 |  |  |  |  | cryostat top, internal cryo, DSS, computer racks, cables, instalaltion tools,..
|  |  | I&I labor | 34774.9147 |  |  |  |  | tech labor
|  |  | total [K$] | 181489.2835

## JPO staff
JPO SDSD staff: not on project
| Name | Affiliation |  | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | Domestic | International | Annual Travel [$]
Position | [14 empty] | cost US /y [$] | cost US [$]
JPO | Integration Office (131.04.01):
JPO | Engineering Review | tba | FNAL |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 14250 |  | 14250
JPO | Review Coordinator Travel | Collaboration Scientists |  |  | X | X | X |  |  |  |  | 4 | 4 | 19000 | 0 | 19000
JPO | Detector Installation Coordinator | Bill Miller ($211k) | Minnesota |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 6000 |  | 6000
JPO | Deputy Detector Installation Coor. | James Stewart | BNL |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 6000 |  | 6000
JPO | Electrical Integration Technician | tba | FNAL |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 6000 |  | 6000
JPO | Chief engineer | Jack Fowler | FNAL |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 19000 | 270000 | 1909000
JPO | Chief design engineer | Justin Fritag | FNAL |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 19000 | 160000 | 1139000
JPO | SD Service Division (131.04.02):
SDSD | Division Head | Patrick Weber | SURF |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 |  |  | 0
SDSD | Deputy Division Head | Joe Pygott | SURF |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 1 |  |  | 0
SDSD | Far Site Logisitics Coordinator | Ladia Jacubek | SURF |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 |  |  | 0
SDSD | SDSD Administrative Support | Natasha Schweitzer | SURF |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 |  |  | 0
SDSD | chief crane driver/transport + deputy | tba | SURF |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 335000 | 4690000
SDSD | 24/7 electrician intervention | tba | SURF |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 295000 | 2065000
SDSD | 24/7 HVAC/net intervention | tba | SURF |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 295000 | 2065000
SDSD | core tec crew leader + deputy | tba | SURF |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 335000 | 4690000
sum |  |  |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 16 | 45 | 23 | 89250 |  | 16609250

## Sheet1
Facility Jack Dimitar | Detector Installation Justin | Detector Integration Kyle | Electrical | Cryogenic
Cryostat Top infrastructure SS vertical tubes (feed thrus) | Int Cryogenics pipes + fixations | Integrate APA | Computer Racks CUC water cooled racks
Cryostat Top infrastructure SS tubes flanges (feed thrus) | Installation equipment | Integrate HV system (CPA, FC, EW, HV probe) | Services Racks CUC water distribution
Cryostat Top infrastructure manholes | installation test equipment, QA, and shipping stuff | Integrate CE | Services Racks CUC CUC DAQ AC Power
Cryostat Top infrastructure gate valves on instrumentation ports | Infrastructure Alimak procurement | Integrate PD | Services Racks CUC controls and safety + leaks monitor
Cryostat Top infrastructure structural supports for feed thrus | Transport Tools engines | Integrate all connections to DSS beam from the detector elements for the final installed state | Services Racks CUC cable trays and supports in CUC
Cryostat Top infrastructure gas exhaust pipe | Transport Tools wagons | Integrate all detector services contained inside LAr volumn (both gas and liquid) including the support required for these services | UPS in CUC UPS for all DAQ
Cryostat Top infrastructure exhaust valves | Transport Tools mobile crane at shaft botton |  | Cables/Fibers/Power-cables fibers bundles APA on the detector roof
Cryostat Top infrastructure flexibles to valves | Transport Tools headframe transport tools telehandler rental |  | Cables/Fibers/Power-cables pach panels for fibers APA
Cryostat Top infrastructure exhaust valves soft pipe | Transport Tools headframe transport tools forklift rental |  | Cables/Fibers/Power-cables fibers cords to DAQ room
Cryostat Top infrastructure exhaust valves fanout | Transport Tools headframe transport tools forklift purchase |  | Cables/Fibers/Power-cables ethernet cablesfrom DAQ room - det racks
Cryostat Top infrastructure gas analysers | Transport Tools All terrain pallet jack for surface |  | Cables/Fibers/Power-cables control cables
Cryostat Top infrastructure O2 trace analysers | Transport Tools fixation material in shaft, guides |  | Cables/Fibers/Power-cables power cables on the detector roof
Cryostat Top infrastructure primary pumps | Transport Tools basic rigging equipment |  | Cables/Fibers/Power-cables power cables to tranformers
Cryostat Top infrastructure turbo pumps | Transport Tools 2 fork lifts underground electric, 6 years |  | Cables/Fibers/Power-cables transformers for ground decoupling
Cryostat Top infrastructure He leak checkers | Transport Tools 1 standup forklift
Cryostat Top infrastructure vacuum tools | Transport Tools Personnel Carriers
Cryostat Top infrastructure lights under the mezzanines | Transport Tools Pallet Jacks
Cryostat Top infrastructure V (power) cable trays + supports | Installation Tools basic clean room structure (metallic str.)
Cryostat Top infrastructure signals cable trays + supports | Installation Tools basic clean room structure(walls)
Cryostat Top infrastructure copper grounding for the cable trays | Installation Tools basic clean room structure(doors)
Cryostat Top infrastructure labor specialized welders team det1 | Installation Tools clean room infrastructure
Cryostat Top infrastructure walking floor | Installation Tools large platforms
Cryostat Top infrastructure cable tray from CUC to racks mezzanine | Installation Tools personnel SAS outfitting
Cryostat Top infrastructure power racks on mezzanine | Installation Tools internal bridge crane
Cryostat Top infrastructure racks internal power distribution | Installation Tools external rails (DSS type) + fixations
Cryostat Top infrastructure racks controls + safety | Installation Tools Cold box access lift
Cryostat Top infrastructure cryo vertical access doors | Installation Tools ventilation system top man holes
Cryostat Top infrastructure miniracks + supports | Installation Tools cold boxes
Cryostat Top infrastructure Water cryo traps | Installation Tools N2 system for cold boxes
Cryostat Top infrastructure valves for the GN2 insulation control | Installation Tools CPA assembly tower/frame
Cryostat Top infrastructure M&S det2 same as det1 | Installation Tools APA cable installation infrastructure
Cryostat Top infrastructure labor specialised welders team det2 | Installation Tools cryostat lights+filters
DSS SS rails | Installation Tools temporary power distribution
DSS rail supports + feedthroughs | Installation Tools various mech. tools
DSS SS APA,CPA supports to rails and shuttle system | Installation Tools Cleanroom safety tools (PPE,ODH, fire, …)
DSS Installation equipment | Installation Tools consumables, small items / 2 years 2 detectors
DSS installation test equipment, QA, and shipping stuff | Installation Tools clean room initial cleaning
Cranes bridge crane | Installation Tools spare parts
Hoists individual hoists | Installation Tools electrical diagnostics equipment
Cranes Power line (150m) | Installation Tools installation storage equipment
Cranes Installation of cranes, hoist, power lines and 1rst inspection | Installation Tools floor inside cryostat + supports
Cranes small material (slings, …) | Installation Tools scissor lifts rental (6 per 48 months)
Infrastructure detector mezzanine | Installation Tools scaffolding rental/ (6 per 4 years)
Infrastructure main bridge | Installation Tools machine shop
Infrastructure hand rails | Installation Tools Material Handling in cavern and transport from cavern to SAS
Infrastructure connection cryostat-bridge | Installation Tools lifts for photon integration
Infrastructure stair to 4910 | Installation Tools electronics racks for testing
Infrastructure stairs to mezzanines | Installation Tools Benches for eating area outside cleanroom
Infrastructure Unforeseen facility modifications | Installation Tools Areal Lift
Infrastructure Condensation prevention system | Installation Tools Lifts general service contract
Infrastructure Grouting below cryostat
Control Rooms screens in cntrl
Control Rooms computers in cntrl
Control Rooms power distribution in cntrl
Control Rooms Net distribution in cavern/wifi
Control Rooms tables and chairs
Control Rooms fire life safety/ barack
Control Rooms det 1 cryo room (cpu, screens, table)
Control Rooms det 2 cryo room (cpu, screens, table)
Control Rooms baracks cryo 1+ light + power + desks
Control Rooms baracks cryo 2+ light + power + desks