## Slide 1: Engineering Integration meetings CERN Nov 18-20
Meeting info in
https://edms.cern.ch/project/CERN-0000202860
https://edms.cern.ch/document/2269160/1

## Slide 2: CERN meeting Nov 18
18 November 2019, 0830 - 1500
Participants: Jack, Eric, Marzio, Dimitar, Justin, Kyle, Steve, Jolie
Please review EDMS 2269157 before meeting
Engineering coordinators: Facility, Detector, Installation
  1. Define interactions, roles & responsibilities (Jack, Justin, Kyle & Dimitar). Includes design oversight, review oversight, attention to resource needs & usage
  2. Define responsibilities for each all Integration elements; use Marzio's detailed cost sheet to assign design coverage for all items. Ensure no scope gaps.
  3. Agree to functional implementation: meetings, interactions, outreach to other key team members, goal is to begin with Wednesday 9a CT FS Interface meeting time slot
2020 activities in preparation for DOE CD-2
Planning for ProtoDUNE II
Involvement of FD engineering, ESH & QA, DAQ
Meeting agenda for Feb 2020 workshop

## Slide 3: CERN meeting Nov 19
19 November 2019, 0830 - 1200
Participants: Dimitar, Kyle, Justin, Jack, designers as needed
Engineering Planning
Determine model formats from all sources, their deliverables and coordinate systems
Interface documentation – text or drawing or both
Establish control/critical dimensions
DUNE interface drawings
Assignment to Justin, Kyle: Bring list of models (inputs); determine translation strategy - all
Assignment to all : have all interface/control/envelope drawings available for review by team
Attach or upload document to https://edms.cern.ch/project/CERN-0000202906

## Slide 4: CERN meeting Nov 20
20 November 2019 0830 - 1200
Participants: Steve, Jack, Marzio, Jolie, Eric
Review Office Planning
Review revised design review document EDMS 2173197
How to execute process; clarify oversight “review office” roles & responsibilities EDMS documents 2093094, 2173000, 2216079, CERN-0000195184
Guidelines for reviewees to be included in the document (documentation required, deliverables, charge, etc)
Upcoming planned reviews & coverage (design phase clarification)
Role of compliance office (& timing for involvement)
Role of FD engineers
Role of ESH, QA

## Slide 5: CERN meeting Nov 20 cont
20 November 2019 1330 - 1500
Participants: Steve, Jack, Olga, Marzio, Jolie, Eric
Safety and Compliance Integrated Project office
Clarify guidance for design review preparation
Please review the documents below before attending
  Structural analysis guideline – Olga EDMS 2172998
  Farshid’s document – status? who owns this now? EDMS 2142687
  Electrical document – Terri EDMS 2159583
Goals
  Notification list for reviews
  Consolidate & centralize information (what are/aren’t we using (obsolete what we’re not using))
  Integrate these items into the JPO review document

## Slide 6: Goals for today
Discuss plans for engineering oversight for post CF work at FS
Agree on responsibilities for engineering coordinators and consortia technical leads
Agree on distinct project engineering roles: detector, installation and facility
Agree on scope for each of the 3 parts
Agree on next actions

## Slide 7: Integration engineering coordinators
Interface coordinators – detector (Zeug), installation (Freitag), facility (Fowler, Mladenov) infrastructure
Responsibilities
  Oversight of the successful planning of deliverables of the elements in their purview to the FS
  Oversight of the design of elements in their working group. Includes assisting in the preparation for design reviews.
  Oversight of all interfaces between elements within their working group and adjacent elements
  Oversight and approval of drawings in their working group
  Creation of documents or drawings to establish and control interfaces
  Lead change efforts that may affect critical interfaces

## Slide 8: Consortia technical leads
Design lead engineers – CE, APA, HV, PD, DAQ, Cryogenics, Cryostat, Cold boxes, Electrical, Installation, CISC
Responsibilities
  Interaction with the engineering coordinators to successfully provide consortia deliverables to the FS
  Oversight or monitor of all design of elements within the consortia
  Manage personnel available to accomplish designs within consortia
  Review designs of adjacent elements that may effect their elements
  Creation of documents or drawings for design of elements, analysis required. They should ultimately have approval responsibilities.
  Lead design change efforts within the consortia
  Negotiate with other technical leads to define interface boundaries

## Slide 9: Detector engineering coordinator
Engineering lead – K Zeug
This contains elements of the APA, PD, HV, CE consortia.
Interface with APA, PD, HV, CE, CISC consortia to integrate detector elements and define the envelopes.
This includes all detector elements in the final installed state, detector services inside the LAr volume and anything that physically connects to the flange on the warm side that supports APA, PD, HV, CE operation. The DSS is an exception to the above rule, as the interface is instead at the connection point on the DSS beam.
Independent verification that detector mechanical designs from individual consortia are consistent with ICDs
Make recommendations on interference resolution
Components that touch Ar (liquid or gas) excluding DSS, Cryo and membrane.

## Slide 10: Installation engineering coordinator
Engineering lead – J Freitag
All detector I&I elements to be installed and the associated infrastructure.
This also includes working with logistics, detector, cryogenics and cryostat to manage interfaces for all components from surface to 4850 station at bottom of Ross shaft and to the detector caverns and CUC. Custom tooling and packaging required for material movement
Integration and infrastructure needed for the cleanroom, all installation work stations/platforms, custom tooling, custom fixtures, conveyances and cold boxes.
Infrastructure required and movement of detector elements inside the cryostat to their final position, includes trolleys, access equipment, false floor.
Ash River planning

## Slide 11: Facility engineering coordinators
Engineering leads – D Mladenov/J Fowler
This contains coordination of all other elements. Interfaces outside of the TPC detector and installation cleanroom.
Includes all mezzanines, racks, cable trays, vent piping, position and alignment of flanges, barracks, bridge and connections
Will manage the interfaces between the internal cryostat, cryogenics and DSS.
Interfaces with the external facility and CF.
Determines the position of the detector inside the cryostat.
Overall integration of all elements

## Slide 12: Detector scope
Engineering lead – K Zeug and consortia engineers
Custom material handling devices beyond what is planned by SDSD (carts and wagons)
Custom lifting tooling (beyond standard slings and tooling)
Cable management inside the cryostat
Cable management during installation (cold box test, for doublet)
Components that touch Ar (liquid or gas) excluding DSS, cryogenic piping and cryostat membrane
Material containers for transport from factory to SD to 4850
Integration of items from LBNF/DUNE subsystems inside the cryostat (eg cryogenic piping and likely CISC and Cal).

## Slide 13: Installation scope
Engineering lead – J Freitag
Cleanroom (includes inside the cryostat), work platforms, air filtration, SAS, lighting, electrical distribution, compressed air
Conveyances, hoists and cranes inside cleanroom
Connection from DSS to installation infrastructure
Access equipment and work floors
Structures inside cleanroom to support I&I
Material needed for detector movement on rails
Clean room life safety and egress
Custom lifting tooling (beyond standard slings and tooling)
Cold box setup and operations (with cryogenics)
Cold box test plans (physics and test plan with consortia) Underground coordinators?

## Slide 14: Facility scope
Engineering leads – D Mladenov/J Fowler
Cold boxes
Barracks and layout (life safety, power and cooling)
DSS
Structures needed on cryostat and mezzanines to support I&I
Flange height, support and alignment
Cable tray layout and support
Vent piping layout with cryogenics
Rack layout but not rack builds
Tolerancing and stack up should be covered somewhere?
Alignment, survey and …….. (Commissioning?)

## Slide 15: Next Actions
Agreement on path forward
Established mailing list
Initiate engineers meeting weekly
Utilize separate meeting for engineer <> stakeholder interactions
Communicate structure and plan to stakeholders (2-4 February) or before
Leverage ProtoDUNE-II as a test case for this engineer <> stakeholder interactions (roles, deliverables)
Identify milestones to track interactions, deliverables

## Slide 16: Cryogenic design oversight and planning
Engineering lead – D Montanari
Cryogenic equipment and instrumentation
Cryogenic system for coldboxes
Internal cryogenic cooldown piping
Internal cryogenic recirculation piping
Cryostat valves, pumps and protective structures
Piping to the caverns and support

## Slide 17: Electrical design oversight and planning
Engineering lead – T Shaw
Detector and AC power distribution
Detector grounding
Rack builds (with the DAQ)
Rack safety systems
Cable and fiber routing and lengths
Cable management from detector flanges to racks
ESD planning
SSDD (with DAQ)
Computing and cyberinfrastructure

## Slide 18: Back ups

## Slide 19: LBNF-DUNE-FS-Integration-Engineering
Establish an ongoing forum to manage the FS integration, interfaces and planning between LBNF-DUNE-Integration
We will create a new distribution list (next bullet) for Thursday integration meeting. (9CT, 10 ET, 1600 CERN), Does this time work or should we reschedule? Do we need a weekly coordination meeting with small group (Zeug, Freitag, Mladenov, Fowler, …..)?
K Zeug, J Freitag, D Mladenov, M Zhao, M Verzocchi, B Yu, V Guarino, D Warner, D Wenman, A Marchionni, B Miller, J Stewart, L Jakubec, T Shaw, D Montanari, J Fowler, S Kettell, E James, J Macier, M Nessi, P Weber, J Mateyack, D Newhart, G Lehman, A Thea, G Gallo
CISC and Cal will be addressed as their systems become more advanced. How to integrate CISC and Cal will be assigned later?

## Slide 20: Design and Interface contacts
Design responsibilities*
  CE Mechanical Eng – M Zhao Tech Lead – M Verzocchi
  HV Mechanical Eng – V Guarino Tech Lead – B Yu
  PD Eng – D Warner Tech Lead – D Warner
  APA Mechanical Eng – D Wenman Tech Lead – A Marchionni
  DAQ – G Lehman Tech Lead – A Thea
  CISC and Cal Eng - ?
  Electrical – T Shaw
  Mechanical – G Gallo
  Cryogenics – D Montanari
  Cryostat and cold boxes – D Mladenov
  Cleanroom and I&I – J Freitag Tech Leads – B Miller J Stewart
Interface responsibilities*
  Installation – J Freitag Tech Leads – B Miller J Stewart
  Detector Integration – K Zeug
  Electrical – T Shaw
  Mechanical – G Gallo
  Cryogenics – D Montanari
  Cryostat – D Mladenov
  All others – J Fowler/D Mladenov
J Fowler/D Mladenov – Overall integration of all models
*Responsibilities:
Each lead is expected to coordinate efforts within their team to ensure progress and quantify status
Ensure adequate resource planning

## Slide 21
LBNF/DUNE Integration
Engineering
Systems Engineers
Configuration Manager
Document Control
Designers
DUNE TC
Project Engineers
Designers
Cryogenics
Project Engineer
Engineers
Designers
Cryostat
Project Engineer
Engineers
Designers
Conventional Facilities
Project Engineers
A&E firms
Consortia
Engineers
Tech Leads
Designers
Facility Support & Services
Logistics support
Core Technical Team
FS Installation
Project Engineers
Tech Leads
Designers
FD
Production
FS Integration Engineering
Facility
FS Installation
Detector

## Slide 22
FS Installation
LBNF/DUNE Systems Engineering
Systems Engineers
Configuration Manager
Document Control
Designers
DUNE TC
Project Engineers
Consortia Tech Leads
Designers
Cryogenics
Project Engineer
Engineers
Designers
Cryostat
Project Engineer
Engineers
Designers
Conventional Facilities
Project Engineers
A&E firms
Consortia
Engineers
Tech Leads
Designers
Facility Support & Services
Project Engineers
Designers
FS Installation
Project Engineers
Tech Leads
Designers
FD
Production
Weber Pygott Jakubec
Site services
Marchionni Verzocchi Yu Warner Guarino Wenman Zhao
James
Kettell Shaw Zeug
Freitag
Miller Stewart
Montanari
Adamowski Haaf
Mladenov
Lacarelle Seleskaya
Pelletier
Willhite
CF team
Fowler Mladenov Dhanaraj Freitag Macier Lacarelle Seleskaya Parchet Zeug, Data Mgr.
Mateyack
Newhart
FS Integration Engineering
Facility
Detector

## Slide 23: Other details
Sample biweekly meeting agenda
  Design teams status reports
    Progress toward deliverables (i.e., Ash River test, load test at SURF, models on EDMS, etc)
    Resource planning
    Interfaces with other teams
  Interface teams status reports
    ..
    Update on interface drawings
  Other reports: Logistics, others?
Meeting frequency: 2x / month

## Slide 24: CERN meeting Nov 18
Proposed participants: Jack Fowler, Marzio Nessi, Eric James, Dimitar Mladenov, Justin Freitag, Kyle Zeug, Steve Kettell, Jolie Macier, Olga Beltramello
Day 1 – Jack and Jolie to coordinate
Review design scope responsibilities assigned for detector, installation, facility. Identify scope gaps
Prioritize and assign responsibilities and resources
Develop design plan with resources including procurements and scheduling. What is needed at CD-2/3? (April Oct 2020)
ProtoDUNE II in EHN1
Day 2 – Dimitar, Justin, Kyle
Determine model formats from all sources, their deliverables and coordinate systems
Interface documentation – text or drawing or both
Establish control/critical dimensions
Day 3 – Jack
Design and analysis documentation – Steve
Safety files, documentation and compliance office coordination - Olga
Design reviews – Jack, Steve, Olga, Marzio
EDMS coordination
Visit ProtoDUNE – need to coordinate
Other items
Agenda Feb meeting
Interviews : EDMS and Safety compliance