## Slide 1: Slow Extraction Working Group
Draft notes

## Slide 2: Working group
Vladimir Nagaslaev
Vander Meulen
George Deinlein
Brian Drendel
Steve Werkema
Jerry Annala
Aakaash Narayanan

## Slide 3: Interfaces
Infrastructure WG
  Aperture improvements
  Vacuum improvements
  Instrumentation options
Installations
8 GeV Transport
Radiation and Loss Control
  Later stage
Mu2e off-project  further upgrades?
  Beam profilometer at the ESS
  Ceramic pipes for tune quads
  Air core quads
  Regulation system
Beam Studies
RF?

## Slide 4: Issues
[All interfaces]
Production delays
  ESS
  Regulation

## Slide 5: Plan of Actions
Meetings bi-weekly, or in person with each interface
Machine studies - on opportunity, chances to schedule? Not discussed with George D.
Installation Met and discussed with Jim B.
Infrastructure Talking with Dave V. on occasions
Programming: start talking to who?
Guidance:
  End of October: present the plan, group list
  Starting November 1 - monthly reports [WBS, milestones, labor resources for the WG, justification if more than 6 months needed, ref to documentation]
  January 31: Preliminary plan
  March 2020: Full report

## Slide 6: Milestones
Installations:
  Septa HV supplies installed
  Septa cabling complete
  Shutdown 2020 installations complete
  FC-40 circulation system complete
  Spill Regulation system installed
  Electrostatic Septa installed
Beam studies:
  General studies complete
  Dedicated studies complete
Application programming
  Items #n complete
Instrumentation systems (each) ready for integration
Spill Regulation system is ready for integration
Slow Extraction systems integration complete
Slow Extraction commissioning start
Slow Extraction commissioning complete

## Slide 7: WBS-I

## Slide 8: WBS-II

## Slide 9: WBS-III