## Slide 1
APA Workshop UK Factory
STFC Daresbury Laboratory
22nd January 2020

## Slide 2
Overview
Factory layout
Progress on the Factory
Safety system
APA component status
APA production schedule

## Slide 3
Daresbury Laboratory DUNE Factory
Inner hall site of the SRS accelerator identified as factory location
Purpose built factory room
Factory to have 4 winding machines, 10 process carts
Separate shipping area in renovated plant room
Dedicated swing arm pillar cranes for each winding machine

## Slide 4
Daresbury Laboratory DUNE Factory Layout

## Slide 5
Storage area for bare APA frames + large equipment.
APA frames loaded into process carts here.
Entrance into preparation area.
Pre Processing Area – Comb bases & mesh panel fitting
Pre Processing Area

## Slide 6
Emergency Exit
Small part assembly / general work area.
comb base and mesh panel fitting.
Small part / jig storage.
Prep area
210m^2
Access to
Winding
area
‘A’Frame
Ganrty
Crane
Pre Processing Area - cont

## Slide 7
Winder - 1
Winder - 2
Winder - 3
Winder - 4
Emergency Exit
Parking for completed APA’s waiting for transfer to shipping area.
Door position shown incorrectly
Winder area 638m^2
Plenty of wall space for off line prep work
Factory Area Layout

## Slide 8
Lifting zone to platform.
Fixed platform
Overhead crane to cover this area.
Post processing / packing & shipping area. 237m^2
HIAB Truck for loading and shipping APA’s
Packing crate (size of existing PSL crate).
Packing & Shipping Area

## Slide 9
Factory Review Jan 2020
Crane installation & commissioning - Complete
Factory room build - Complete
Factory Room Services
  Electrical services being installed includes all lighting, power and network systems…..expected completion end Jan 2020.
  Heating and ventilation system filtered to class 100,000 ordered…..installation Feb 2020.
Shipping room refurbishment well advanced
  Floor remedial work ongoing then electrical power distribution boards will be installed
  Lighting installed
  Heating and ventilation order placed
Platform
  Installed - Complete
Factory Progress

## Slide 10
Plan to use updated existing winding machine in current position for development work and building of APA’s to meet schedule
Winding machine bases and pillars (3 off) – Delivered
Spines and bearing/shaft systems – Delivered
XYZ drives including spare z drives – expected delivery Jan 2020
Cable trays - Delivered
Factory Progress – Winding Machines

## Slide 11
6 linear bearings,top centre & bottom
Bishop Wisecarver XY&Z drive stages
Winding Machines
Component Procurement in Progress

## Slide 12
Development work being carried out on current winding machine.
Laser curtains in place
Fencing and access doors with breakout switches installed
Emergency off pull wire installed
Control system drgs complete
Commission control system in progress
Safety System for Winding Machine

## Slide 13
Safety System for Winding Machine
Laser light curtain
Interlock door for rear access
Laser light curtain
Emergency interlocked pull wire
DC motor winder head tests in progress

## Slide 14
Frames
3 frames ordered 2 from UK supplier 1 from PSL
Tender process for production required
Electronic Boards
60% Electronics review took place PSL November
Production delayed……sample boards will be supplied by PSL for winder commissioning
Suppliers need to be identified
Combs & Comb Bases
Suppliers identified
  Order placed for comb bases,
  Order placed for sample combs
APA Component Status

## Slide 15
Winder Heads (active tension control) – 4off
1 existing…. Commissioned
4 currently being manufactured at University of Liverpool
Mesh – 10 rolls - Delivered
  Currently manufacturing 40 mesh panels for 2 APA’s – expected delivery December 2019
  Tender process for production is currently ongoing in UK
APA Component Status

## Slide 16
Process Carts – 10 off
2 carts exist
Aluminium extrusion bases for 8 carts ordered
Support arms, gearboxes and bearing shafts ordered …….design review with PSL
Shipping Crates
Design review Jan 2020….Liverpool
Tender process for production required
APA Component Status

## Slide 17: APA Production
Production of APAs for Detector #1
  US-APA production (76 APAs): Jan 4, 2021 – Dec 7, 2023
  UK-APA production (76 APAs): Jul 6, 2020 – Nov 6, 2023
APA Production/year
Production Site | 2020 | 2021 | 2022 | 2023
Daresbury | 6 | 24 | 26 | 20
Yale |  | 10 | 13 | 7
Chicago |  | 10 | 13 | 7
PSL |  | 3 | 7 | 6
TOT | 6 | 47 | 59 | 40
Need to cold test 10% of APA production
Need to investigate options for local storage if early shipping to SD is not possible

## Slide 18
Factory to be manned and winding machines operated by Technician Staff from:-
Manchester, Liverpool, Sheffield, Lancaster & Daresbury
APA Production

## Slide 19
Thank you