## Slide 1
Vincent Roger
15 January 2020
Design of HB650 Proto CM - Fermilab meeting

## Slide 2: PDR
All presentations are in Indico:
https://indico.fnal.gov/event/22509/
Preliminary report of the reviewers
1. Technical Scope
a. Are all design & performance specifications and requirements reviewed, and at the level
of maturity commensurate with a PDR?
RESPONSE: Yes, specifications and requirements have been reviewed appropriately and
are consistent with the project’s definition of PDR level.
b. Have all the major interfaces been identified and incorporated into the design?
RESPONSE: Yes, interfaces have been identified and reviewed; however, particular
diligence will be necessary to manage the interfaces both at FNAL and with the partners
as the design matures.
c. Are the development of CAD and drawing packages sufficiently mature for preliminary
design stage?
RESPONSE: Yes, however several of the sub-packages require additional analysis and
model completion to be consistent with PDR requirements.
d. Are there any unmanaged items that could affect safety, quality, cost, schedule, or
performance?
RESPONSE: No

## Slide 3: PDR
2. Design Management
a. Is the design team organized and staffed to successfully complete the project?
RESPONSE: Yes, the design team is developed and staffed appropriately to complete the
project. As mentioned, diligence in managing the deliverables both at FNAL and from the
partners is key to the project success.
b. Have all the major risks been identified and managed?
RESPONSE: Yes, the design FMEA and risk register were presented
c. Are appropriate ESH, QA, and QC steps being implemented?
RESPONSE: Yes, ESH, QA, and QC are appropriately developed and implemented.
d. Is the cost and schedule reasonable to achieve the planned scope?
RESPONSE: Yes
3. Is the cryomodule design sufficiently mature to meet the standard for a PDR
(~50% complete), and on track for completion of Final Design (>90% complete) by June 2020?
RESPONSE: Yes, the review committee recognizes that this is a technically driven
schedule and funding profile can change schedule.

## Slide 4: PDR Recommendations
1. Analyze interface between strongback and vacuum vessel to determine if adjustability of the internal vacuum vessel rails is required.
2. Analyze stresses in strongback with cool-down following loss of insulating vacuum.
3. Using simulation, confirm the impact of the cavity and 5K thermal intercept cooldown sequence on the support post.
4. Analyze and review the cool-down manifold (Line H) and capillary tubes for fast cool-down pressure drops and for uniform flow into helium vessels.
5. Check 2-phase flow design for liquid droplet separation. For example, you might need a larger distance between inlet and pumping line or metal mesh (Mott Corp.) so as not to pump liquid entrained in vapor.
6. Complete the vibration modal study on the strongback and coldmass system.
7. Complete vibration analysis to ensure mechanical integrity during shipping and handling for the FPC components prior to placing orders as it may impact shipping and handling approach for the CM.
8 (coupler related)
9. Develop a detailed transportation plan (that is reflected in the project schedule) that includes component testing, transportation frame verification and shipping approach for at least long distance portions but consider also on-site transportation and handling. Complete the shipping configuration specification prior to the CM FDR as it might impact design choices related to the CM.
10. In determining the preferred lift points for transportation, determine whether the cryomodule design lift points are consistent with this additional weight and weight distribution. Address the risks to the cryomodule of impact on any part of the transportation frame when it’s lifted or set down.

## Slide 5: FDR - June 2020 or earlier
Main activities on going:
  The string assembly, tooling and procedure [Y. Orlov]
  The rails and tooling with regards to the assembly process [V. Poloubotko]
  The transportation analysis [S. Cheban, J. Helsper]
  The cryomodule design [V. Roger, Y. Orlov]
    Piping
    The vacuum vessel design and analysis
    The thermal shield design and analysis [G. Smith]
    Cavity support design and analysis [N. Nigam, J. Helsper]
Future activities:
  Implement input from partners
    Strongback + interface with the vacuum vessel, transport frame, heat exchanger
  HBCAM [S. Zorzetti]
  Alignment strategy
  Valve sizing and pressure drops [B. Squires]
  P&ID and instrumentation list [B. Squires]
  ICD, ISD, TRS , FRS … [B. Squires]
  Assembly procedure
  Procurement plan
  QA-QC plan
  Final magnetic calculation and magnetic hygiene plan [I. Terechkine, Y. Xie]

## Slide 6: Unit
Everything in metric
Models, drawings, notes, hardware, standard parts, …
121.0146PD – HB650 CM STRING design (cleanroom assembly related)
121.0262PD – HB650 CM design (outside cleanroom assembly related)
Task code