## Slide 1
Steve Holmes
DOE ICE
February 5, 2020
PIP-II CD-2 vs CD-1 Cost Comparisons
(PIP-II-doc-3069)

## Slide 2: What are we comparing?
CD-1 Budget at Completion
  Based on Cost Book from the CD-1 IPR (PIP-II-doc-229)
  Starts Oct 1, 2017
  Base-year FY2016 dollars
  Add actuals from Jan 2016 – Sep 30, 2017
  Cost Book and actuals mapped onto the CD-2 WBS
  Modified to incorporate the UK in-kind contribution – not in the Cost Book but described in a supplementary document (PIP-II-doc-1212)
CD-2 Budget at Completion
  Based on Cost Book for the CD-2 IPR (PIP-II-doc-1176)
  Through BCRP0144
  Base year FY2018 dollars
  Includes actuals from Jan 2016 – Jan 31, 2019

## Slide 3: CD-2 – CD-1 Comparisons
Budget at Completion
  At L3 of the CD-2 WBS
  Hours, direct M&S (base-year dollars), fully-burdened/escalated dollars
    CD-1 Direct M&S adjusted upward by 4% to account for different base years (difference tables only).
    No attempt to unravel overhead or escalation rates
    Overhead rates are similar since new project rates not yet adopted
Total Project Cost
  At L3 of the CD-2 WBS
  Start with BACs
  Add Contingency (Estimate Uncertainty + Risk)
  Subtract anticipated reduction in CD-2 overheads
  Corresponds to the EAC presented at the IPR

## Slide 4: CD-1 Estimate (BAC)
 |  | CD-1 BAC |  |  | 
WBS |  | Hours | Direct M&S | Cost | FTE
121 | PIP-II Project | 1,675,665 | $217,901,346 | $530,030,924 | 947.8
121.01 | PROJECT MANAGEMENT | 297,821 | $4,775,482 | $55,060,422 | 168.5
121.02 | SRF and CRYO SYSTEMS | 528,368 | $41,801,600 | $129,086,754 | 298.9
121.03 | ACCELERATOR SYSTEMS | 350,294 | $28,216,693 | $88,652,486 | 198.1
121.04 | LINAC INSTALLATION and COMMISSIONING | 375,646 | $18,324,479 | $76,545,251 | 212.5
121.05 | ACCELERATOR COMPLEX UPGRADES | 87,546 | $18,791,206 | $38,203,521 | 49.5
121.06 | CONVENTIONAL FACILITIES | 35,990 | $105,991,885 | $142,482,489 | 20.4

## Slide 5: CD-2 Estimate (BAC)
 |  | CD-2 BAC |  |  | 
WBS |  | Hours | Direct M&S | Cost | FTE
121 | PIP-II Project | 2,368,382 | $275,751,505 | $696,817,897 | 1,339.6
121.01 | PROJECT MANAGEMENT | 375,616 | $9,675,710 | $77,013,471 | 212.5
121.02 | SRF and CRYO SYSTEMS | 651,915 | $46,820,508 | $153,904,615 | 368.7
121.03 | ACCELERATOR SYSTEMS | 433,136 | $39,584,985 | $110,118,971 | 245.0
121.04 | LINAC INSTALLATION and COMMISSIONING | 579,984 | $29,022,640 | $124,130,010 | 328.0
121.05 | ACCELERATOR COMPLEX UPGRADES | 256,992 | $21,981,616 | $64,869,426 | 145.4
121.06 | CONVENTIONAL FACILITIES | 70,740 | $128,666,046 | $166,781,404 | 40.0

## Slide 6: CD-2 – CD-1 Estimate (BAC)
 |  | CD-2 – CD-1 BAC |  |  | 
WBS |  | D Hours | D Direct M&S | D Cost | DFTE
121 | PIP-II Project | 692,716 | $49,440,378 | $166,786,973 | 391.8
121.01 | PROJECT MANAGEMENT | 77,795 | $4,739,647 | $21,953,049 | 44.0
121.02 | SRF and CRYO SYSTEMS | 123,547 | $3,505,737 | $24,817,861 | 69.9
121.03 | ACCELERATOR SYSTEMS | 82,841 | $10,257,520 | $21,466,485 | 46.9
121.04 | LINAC INSTALLATION and COMMISSIONING | 204,338 | $10,040,391 | $47,584,758 | 115.6
121.05 | ACCELERATOR COMPLEX UPGRADES | 169,447 | $2,439,419 | $26,665,905 | 95.8
121.06 | CONVENTIONAL FACILITIES | 34,749 | $18,457,663 | $24,298,915 | 19.7

## Slide 7: Commentary
The CD-2 BAC is about 31% higher than at CD-1
  Labor hours are up by 41%
  M&S is up by 23% (after adjusting for base-year difference)
Biggest increases are in Linac Installation & Commissioning and Accelerator Upgrades
  Most (~75%) of the LI&C increase comes from labor estimate increases
  Essentially all (~96%) of the AU increase is from inherited AIPs and scope transfers
Note: There are several significant transfers of scope between L2s that are not accounted for in the CD-1 WBS mapping.
  Net effect is moving ~$14M of costs from Accelerator Systems to Accelerator Upgrades and Conventional Facilities

## Slide 8: Commentary
There are also scope adjustments from CD-1 to CD-2
  Added and removed scope
  New in-kind contributions and assumed in-kind contributions going away
And significant adjustments to Project Management costs across all L2s
  Expanded management team
  Additional level-of-effort as CD-4 moved six months (later) between the CD-1 and CD-2 estimates
Notes: Add some of the description of drivers:
Requirements changes
Management growth
Estimate evolution
risk reduction
Contingency/EU+risk
Why is EU higher at CD-2 than CD-1?

## Slide 9: Scope Adjustments
 |  | Scope Adjustments |  | 
WBS |  | Hours | Direct M&S | Cost
121 | PIP-II Project | 107,749 | $(1,193,440) | $16,899,122
121.01 | PROJECT MANAGEMENT | 0 | $0 | $0
121.02 | SRF and CRYO SYSTEMS | (16,426) | $(6,020,323) | $(10,372,372)
121.03 | ACCELERATOR SYSTEMS | 37,219 | $4,234,992 | $11,274,435
121.04 | LINAC INSTALLATION and COMMISSIONING | 7,080 | $0 | $1,770,000
121.05 | ACCELERATOR COMPLEX UPGRADES | 79,875 | $3,886,891 | $18,510,559
121.06 | CONVENTIONAL FACILITIES | 0 | $(3,295,000) | $(4,283,500)

## Slide 10: Commentary
The net scope adjustment is about $16.9M
Net added scope amounts to about $41.7M
  Prototype SSR1, SSR2, LB650, HB650
  LB650 reconfiguration and reduced CM RF tests (credit)
  EPICS implementation
  Booster, RR, MI inherited AIPs
  CF off-project GPPs (credit)
  CF upgrades to support CW operations
  Enclosure and gallery length to support 1 GeV
Net in-kind changes amount to about $24.8M
  SSR1, SSR2 components
  Cryogenic Distribution System
  Reduced LLRF no longer in-kind (debit)
  Reduced BPM and BLM in-kind (debit)

## Slide 11: Scope Adjustment Details
 |  | CD-2 – CD-1 Scope Modifications |  | 
WBS | Scope | Hours | Direct M&S | Cost
121 | PIP-II | 107,749 | ($1,193,440) | $16,899,122
121.2 | Prototype Cryomodules | 97,716 | $8,033,634 | $25,589,704
 | SSR1,2 in-kind contributions | (78,030) | ($12,036,088) | ($27,741,487)
 | LB650 reduced testing | (32,143) | $325,766 | ($4,558,669)
 | CDS in-kind contribution | (3,969) | ($2,343,635) | ($3,661,921)
121.3 | No LLRF in-kind contributions | 15,468 | $1,910,469 | $4,881,150
 | EPICS implementation | 17,207 | $1,539,364 | $4,668,258
 | Reduced BPM, BLM in-kind contributions | 4,544 | $785,159 | $1,725,027
121.4 | Booster Physics Studies | 7,080 | $0 | $1,770,000
121.5 | Booster Upgrades from AIP | 56,755 | $3,837,501 | $13,827,291
 | MI gamma-t jump | 23,120 | $49,390 | $4,683,268
121.06 | Electrical utilities to GPP | 0 | ($9,700,000) | ($12,610,000)
 | Mechanical upgrades for CW operations | 0 | $2,620,000 | $3,406,000
 | Increased tunnel and gallery length | 0 | $3,785,000 | $4,920,500

## Slide 12: Project Management Increases
 |  | CD-2 – CD-1 Project Management Growth |  |  | 
WBS |  | Hours | Direct M&S | Cost | FTE
121 | PIP-II Project | 133,682 | $5,680,452 | $34,710,053 | 75.6
121.01 | PROJECT MANAGEMENT | 77,795 | $4,739,647 | $21,953,049 | 44.0
121.02 | SRF and CRYO SYSTEMS | 29,530 | $608,598 | $7,279,389 | 16.7
121.03 | ACCELERATOR SYSTEMS | (703) | $(620) | $(955,874) | (0.4)
121.04 | LINAC INSTALLATION and COMMISSIONING | 11,728 | $94,703 | $2,786,485 | 6.6
121.05 | ACCELERATOR COMPLEX UPGRADES | 9,639 | $25,984 | $2,263,100 | 5.5
121.06 | CONVENTIONAL FACILITIES | 5,694 | $212,140 | $1,383,905 | 3.2

## Slide 13: Commentary
The Project Management increase is about $34.7M
Levels-of-effort and durations both change between the CD-1 and CD-2 estimates
Total increase of ~76 FTE
  ~61 FTE (about 7 FTE/year) are attributable to growth in the size of the management team
    Growth generally motivated by enhancing the management structure to provide coordination and oversight of a larger number of international partners
    Also: enhanced procurement & project controls support
  ~15 FTE are attributable to the additional six months to CD-4 in the CD-2 schedule.

## Slide 14: CD-2 – CD-1 Summary (BAC)
 |  | CD-2 – CD-1 BAC |  |  |  | 
WBS |  | CD-1 | CD-2 | D Cost | D Scope | D PM
121 | PIP-II Project | $530,030,924 | $696,817,897 | $166,786,973 | $16,899,122 | $34,710,053
121.01 | PROJECT MANAGEMENT | $55,060,422 | $77,013,471 | $21,953,049 | $0 | $21,953,049
121.02 | SRF and CRYO SYSTEMS | $129,086,754 | $153,904,615 | $24,817,861 | $(10,372,372) | $7,279,389
121.03 | ACCELERATOR SYSTEMS | $88,652,486 | $110,118,971 | $21,466,485 | $11,274,435 | ($955,874)
121.04 | LINAC INSTALL and COMMISSION | $76,545,251 | $124,130,010 | $47,584,758 | $1,770,000 | $2,786,485
121.05 | ACCELERATOR COMPLEX UPGRADES | $38,203,521 | $64,869,426 | $26,665,905 | $18,510,559 | $2,263,100
121.06 | CONVENTIONAL FACILITIES | $142,482,489 | $166,781,404 | $24,298,915 | $(4,283,500) | $1,383,905

## Slide 15: CD-2 – CD-1 Summary (TPC)
 |  | CD-2 – CD-1 TPC |  |  |  | 
WBS |  | CD-1 | CD-2 | D Cost | D Scope | D PM
121 | PIP-II Project (BAC) | $530,030,924 | $696,817,897 | $166,786,973 | $16,899,122 | $34,710,053
 | CONTINGENCY | $190,671,578 | $235,746,301 | $45,074,723 | $6,287,097 | $23,830,036
 | % CONT on ETC | 38% | 40% | - | - | -
 | OVHD Reduction | $0 | $(44,556,377) | $(44,556,377) | $(1,188,270) | ($3,000,120)
 | PIP-II Project (TPC) | $720,702,502 | $888,007,821 | $167,305,319 | $21,997,948 | $55,539,969

## Slide 16: Summary (1/2)
TPC grew by about $167M (23%) between CD-1 and CD-2 after taking credit for the proposed overhead reduction ($45M).
  Nearly half ($78M) comes from changes in scope ($22M) and project management ($56M).
Overall contingency grew by $45M.
  As a fraction of (ETC) contingency grew from 38% at CD-1 to 40% at CD-2.
  Largely reflects coordination of additional international partners
Cost growth in labor and M&S is in the ratio of about 3:2

## Slide 17: Summary (2/2)
Largest cost growth in absolute terms (62%) is in Linac Installation & Commissioning.
  Largely due to increases in labor estimates resulting from moving from parametric to bottoms-up estimates of labor-intensive activities.
A comparably large relative cost growth (70%) is found in Accelerator Upgrades.
  Scope modifications from the inclusion of what was intended to be in AIPs at CD-1 and scope transfers from other Level 2 elements account for nearly the entire increase.

## Slide 18: Backups

## Slide 19: Characterization of Cost Increase
Chart: Sources of Cost Growth
| Management Team Growth | Extended CD-4 | On/off-project transfers | Risk Reduction | Requirements changes | Estimate evolution
 | 29713132.4278 | 4996920.4211 | 7670559.3 | 21031035 | 12994758.2 | 115177799.0656