## Slide 1
S. Dixon, L2 Manager
DOE CD-2/3a ICE Review
February 4-7, 2020
WBS 121.06.02 -Site Preparation

## Slide 2: About Me
PIP-II Level 2 Manager for Conventional Facilities
Relevant Experience
  Licensed Architect;
  Project Management Professional (PMP);
  LEED Accredited Professional;
  27+ years at Fermilab;
  NOvA Project L2 Manager for Site and Buildings;
    2014 CD-4
    2015 U.S. DOE Secretary’s Award for Excellence
  General Plant Project Manager for 17+ years
    Short Baseline Neutrino (SBN) Near Detector Building;
    Short Baseline Neutrino (SBN) Far Detector Building;
    Experimental Operations Center;

## Slide 3: Agenda
Project Organization
Scope
Documents

## Slide 4: Project Organization
Architect/Engineer Team
Gensler (architecture), IMEG (mechanical, electrical, plumbing)
TGRWA (structural),CMT (civil), Jensen Hughes (life safety), Syska Hennessy (commissioning), Burns and McDonnell (landscaping)
WBS 121.06
Conventional Facilities
S. Dixon
System Manager
WBS 121.06.02
Site Preparation
R. Wielgos
WBS 121.06.03
Cryogenics Plant Building
(S. Dixon)
WBS 121.06.06
Booster Connection
E. Alcaraz
WBS 121.06.05
Linac Complex
E. Alcaraz
WBS 121.06.04
Utility Plant
E. Alcaraz
WBS 121.06.01
Project Management
S. Dixon

## Slide 5: Scope/Deliverables
WBS 121.06.02 Site Preparation [1]
WBS 121.06.02.01 – Project Management and Coordination
WBS 121.06.02.02 – Detailed and Final Design
WBS 121.06.02.03 – Site Clearing
WBS 121.06.02.04 – Site Work
WBS 121.06.02.05 – Site Restoration & Landscaping
[1] See WBS Dictionary in PIP-II-doc-599 for complete description

## Slide 6: Scope and Deliverables
Site Preparation (WBS 121.06.02)
  Site Clearing
  Site Work
  Site Restoration and Landscaping

## Slide 7: Technical Progress to Date – Site Clearing
WBS 121.06.02.03 – Site Clearing
Design completed in October 2018
Construction:
  Authorized in October 2018 [1]
  Construction began in March 2019
  Construction complete in July 2019
Authorization for PIP-II Project Related Site Clearing Work Prior to CD-2/3
[1] See PIP-II-doc-2524 for Authorization
July 2019

## Slide 8: Technical Progress to Date – Site Work
WBS 121.06.02.04 – Site Work
Designed as a separate construction package includes:
  Roadway base
  AZero pond rework (road crossings, retaining wall, deepening)
  Storm drainage
  Landscaping outside of ring road
Design completed in January 2019
Part of the CD-3a request

## Slide 9: Technical Progress to Date – Site Work
WBS 121.06.02.04 – Site Work [1]
[1] See PIP-II-doc-2521 for complete document set
Pond Crossings
AZero Pond Rework
Road Base
Rough Grading
Landscaping Outside Road
Storm Drainage
Sheet Pile Wall

## Slide 10: Technical Progress to Date – Site Restoration
WBS 121.06.02.05 – Site Restoration and Landscaping
Designed as a separate construction package includes:
  Final road coarse
  Finish grading and topsoil
  Linac Pond
  Landscaping
  Roadway lighting
Design completed in April 2019
Part of the CD-3a request

## Slide 11: Technical Progress to Date – Site Restoration
WBS 121.06.02.05 – Site Restoration and Landscaping [1]
[1] See PIP-II-doc-3163 for complete document set
Entry Plaza
Linac Pond
Roadway Lighting
Landscaping Inside Road
Landscaping

## Slide 12: Documents
PIP-II-doc-2492 - Functional Requirements Specification
PIP-II-doc-2492 – Technical Requirements Specification
PIP-II-doc-2524 – Site Clearing Construction Documents
PIP-II-doc-2521 – Site Work Construction Documents
PIP-II-doc-3163 – Site Restoration Construction Documents

## Slide 13: End