## Slide 1
S. Dixon, L2 Manager
DOE CD-2/3a ICE Review
February 4-7, 2020
WBS 121.06.03 –Cryogenics Plant Building

## Slide 2: About Me
PIP-II Level 2 Manager for Conventional Facilities
Relevant Experience
  Licensed Architect;
  Project Management Professional (PMP);
  LEED Accredited Professional;
  27+ years at Fermilab;
  NOvA Project L2 Manager for Site and Buildings;
    2014 CD-4
    2015 U.S. DOE Secretary’s Award for Excellence
  General Plant Project Manager for 17+ years
    Short Baseline Neutrino (SBN) Near Detector Building;
    Short Baseline Neutrino (SBN) Far Detector Building;
    Experimental Operations Center;

## Slide 3: Agenda
Project Organization
Scope
Documents

## Slide 4: Project Organization
Architect/Engineer Team
Gensler (architecture), IMEG (mechanical, electrical, plumbing)
TGRWA (structural),CMT (civil), Jensen Hughes (life safety), Syska Hennessy (commissioning), Burns and McDonnell (landscaping)
WBS 121.06
Conventional Facilities
S. Dixon
System Manager
WBS 121.06.02
Site Preparation
R. Wielgos
WBS 121.06.03
Cryogenics Plant Building
(S. Dixon)
WBS 121.06.06
Booster Connection
E. Alcaraz
WBS 121.06.05
Linac Complex
E. Alcaraz
WBS 121.06.04
Utility Plant
E. Alcaraz
WBS 121.06.01
Project Management
S. Dixon

## Slide 5: Scope and Deliverables
WBS 121.06.03 Cryogenics Plant Building[1]
Procurement and management for all contracted labor, materials, tools, equipment, and services needed for the construction of the Cryogenics Plant Building work scope. It describes the labor resources, materials and services necessary for management, organization, planning, oversight and engineering, design, inspection and administration (EDIA).
[1] See WBS Dictionary in PIP-II-doc-599 for complete description

## Slide 6: Scope and Deliverables
Charge #1
WBS 121.06.03 Cryogenics Plant Building
WBS 121.06.03.01 – Project Management and Coordination
WBS 121.06.03.02 – Detailed and Final Design
WBS 121.06.03.03 – Construction On Site
View Looking Southwest

## Slide 7: Scope and Deliverables
Cryogenics Plant Building (WBS 121.06.03)
Utility Plant (WBS 121.06.04)

## Slide 8: Technical Progress to Date
WBS 121.06.03
Technical Requirements phase starting in May 2018
Completed Industrial Cooling Water Quality Testing [1]
Value Engineering resulted in a combined building with the Utility Plant functions
Final Design started in January 2019
Design completed in July 2019 [2]
[1] See PIP-II-doc-155
[2] See PIP-II-doc-1660

## Slide 9: Technical Progress to Date
WBS 121.06.03 Construction Documents[1]
[1] See PIP-II-doc-1660 for complete document set
Temporary Access
Road
Sedimentation
Pond
Cryogenics Plant Building

## Slide 10: Technical Progress to Date
Warm Compressor Station
Cold Box Station
Tech Bay

## Slide 11: Technical Progress to Date
Helium
Storage
Tanks
Mechanical Bays

## Slide 12: Technical Progress to Date

## Slide 13: Technical Progress to Date – Reviews
Completed
Requirements and Specifications Review in November 2018
40% Technical Requirements Review in November 2018
60% Design Review in March 2019
90% Design Review in May 2019
Procurement Readiness Review in August 2019

## Slide 14: Schedule

## Slide 15: Documents
PIP-II-doc-2492 - Functional Requirements Specification
PIP-II-doc-2492 – Technical Requirements Specification
PIP-II-doc-1660 – Cryogenics Plant Building Construction Documents

## Slide 16: End