## Slide 1
S. Dixon, L2 Manager
DOE CD-2/3a ICE Review
February 4-7, 2020
WBS 121.06 - Conventional Facilities
Overview and Process

## Slide 2: About Me
PIP-II Level 2 Manager for Conventional Facilities
Relevant Experience
  Licensed Architect;
  Project Management Professional (PMP);
  LEED Accredited Professional;
  27+ years at Fermilab;
  NOvA Project L2 Manager for Site and Buildings;
    2014 CD-4
    2015 U.S. DOE Secretary’s Award for Excellence
  General Plant Project Manager for 17+ years
    Short Baseline Neutrino (SBN) Near Detector Building;
    Short Baseline Neutrino (SBN) Far Detector Building;
    Experimental Operations Center;

## Slide 3: Agenda
Project Organization
Scope
Schedule
Risks
Basis of Estimate Development Process
Cost and Schedule Update

## Slide 4: Project Organization
Architect/Engineer Team
Gensler (architecture), IMEG (mechanical, electrical, plumbing)
TGRWA (structural),CMT (civil), Jensen Hughes (life safety), Syska Hennessy (commissioning), Burns and McDonnell (landscaping)
WBS 121.06
Conventional Facilities
S. Dixon
System Manager
WBS 121.06.02
Site Preparation
R. Wielgos
WBS 121.06.03
Cryogenics Plant Building
(S. Dixon)
WBS 121.06.06
Booster Connection
E. Alcaraz
WBS 121.06.05
Linac Complex
E. Alcaraz
WBS 121.06.04
Utility Plant
E. Alcaraz
WBS 121.06.01
Project Management
S. Dixon

## Slide 5: Scope and Deliverables
Conventional Facilities includes the design, procurement and construction of the utilities, roads, structures, enclosures and buildings to support the installation, assembly and operation of the technical components. [1]
WBS
  121.06.01 – Project Management and Coordination
  121.06.02 – Site Preparation – CD-3a Request
  121.06.03 – Cryogenics Plant Building - CD-3a Request 121.06.04 – Utility Plant
  121.06.05 – Linac Complex (88,600 square feet)
  121.06.06 – Booster Connection (7,800 square feet)
[1] See WBS Dictionary in PIP-II-doc-599 for complete description

## Slide 6: Scope and Deliverables
Cryogenics Plant Building (WBS 121.06.03)
Utility Plant (WBS 121.06.04)
Linac Complex (WBS 121.06.05)
  High Bay Building
  Linac Tunnel
  Linac Gallery
  Beam Transfer Line
Booster Connection (WBS 121.06.06)
Site Preparation (WBS 121.06.02)
  Site Clearing
  Site Work
  Site Restoration and Landscaping

## Slide 7: Schedule
CD-3a Requests

## Slide 8: Risks and Risk Mitigation
Type | Quantity
High | 1
Medium | 4
Low | 8
Opportunity | 2
[1] – Risk Management Plan can be found in PIP-II-doc-163
[2] – Construction Escalation Strategy can be found in PIP-II-doc-1299
Following the procedures contained in the PIP-II Risk Management Plan [1]
15 currently managed risks
Managed through the Risk Register
Top Five Risks
RI-ID | Title
RT-121-06-001 | CnvF: Changes in subproject requirements affect Conventional Facilities
RT-121-06-042 | CnvF: Construction activities impact the Booster
RT-121-06-043 | CnvF: Construction subcontractor performance
RT-121-06-010 | CnvF: Interfaces between subprojects and conventional construction
RT-121-06-011 | CnvF: Time for long lead time items is longer than expected
Construction Escalation Strategy Updated in December 2020 [2]

## Slide 9: Risks – Conventional Facilities Risks
From PIP-II-doc-3271

## Slide 10: Risks – Top 30 Cost Risks
Histogram does not include standing army and escalation burn rate costs.
These are computed collectively for the whole project using the PRA MC.
From PIP-II-doc-3271

## Slide 11: Risks – Top 30 Schedule Risk Impacts
From PIP-II-doc-3271
Note: only some risks delay the project finish (if they are on or near the critical path).
Aggregate schedule risk is assessed using the PRA MC model.

## Slide 12: Basis of Estimate Development
Process

## Slide 13: Cost Estimate Process
Documentation can be found at PIP-II-doc-333
Initial Tasking for A/E Team
Conceptual Design drawings and Estimate Assumptions developed with input from stakeholders
Drawings from PIP-II-doc-1155
the construction cost estimate should be prepared in accordance with DOE’s Cost Estimating Guide (G413.3-21) and GAO Cost Estimating and Assessment Guide (GOA-09-3SP) as well as current industry best practices. For the purposes of this tasking the preliminary cost estimate should assume a 10%-40% project definition based on the conceptual design documentation and therefore a Class 3 estimate classification as defined by DOE G 413.3-21

## Slide 14: Cost Estimate Process
Documentation can be found at PIP-II-doc-333
Original estimate completed in May 2017;
Broken down by work package;
Updated in April 2018

## Slide 15: Schedule Estimate Process
Documentation can be found at PIP-II-doc-581
Initial Tasking for A/E Team
Conceptual Design drawings and Estimate Assumptions developed with input from stakeholders
Drawings from PIP-II-doc-1155
The preliminary construction schedule should instead focus on the completion of major milestones (eg: excavation complete, foundation complete, building shell complete, beneficial occupancy, etc.) within the overall schedule to provide a reasonable prediction of one possible construction scenario. This schedule information will be included in the PIP-II resource loaded schedule as a planning package that will be updated with further information and details as they become available.

## Slide 16: Schedule Estimate Process
Documentation can be found at PIP-II-doc-581 and in each Basis of Estimate file
Considered Planning Packages;
Technically driven schedules;
Focused on interface milestones
Durations modified based on scope adjustments

## Slide 17: Basis of Estimate Form Example
Typical Basis of Estimate form
Assumptions
Supporting Documents

## Slide 18: Basis of Estimate Form Example
Typical Basis of Estimate form
Base Estimate(PIP-II-doc-333)
ED&I Costs
(PIP-II-doc-327)
Scope Adjustments to Base Estimate
Construction Estimate = Base Estimate + Scope Adjustments

## Slide 19: Basis of Estimate Form Example
Typical Basis of Estimate form
Construction Subcontract Procurement Durations
(PIP-II-doc-321)
Construction Subcontract Durations
(PIP-II-doc-581)
Estimate Uncertainty
(PIP-II-doc-345)

## Slide 20: Basis of Estimate List

## Slide 21: Cost and Schedule
Design Team
  Selection required cost/schedule estimator;
  Gensler team includes Turner Construction Company;
Overall Cost/Schedule Estimate
  One of the first design team tasks;
  Initially done based on conceptual design developed in house;
  Periodic updates (see next slide).
Construction Packages
  Design phase request for proposal includes:
    Design to construction cost target;
    Updated cost estimate at 60%, 90% and 100% deliverables.

## Slide 22: Cost and Schedule Update
Timeline
  2017 - Original cost/schedule estimate based on conceptual design
  2018 – Updated cost estimate based on value engineering workshop
  March-October 2019 – Updated design of Linac Complex based on latest requirements
  November 2019 to March 2020: Updated cost/schedule estimate (reconciliation in progress)

## Slide 23: Cost and Schedule Update
Cost/schedule update by the A/E started after the completion of design update for Linac Complex and Booster Connection.
Includes estimator on Design Team (Turner) and external independent estimator (Cumming)
The reconciled cost/schedule estimate will be used as the basis for the construction cost target during design phase.

## Slide 24: Cost and Schedule Update
Site Preparation (121.06.02) and Cryogenics Plant Building (121.06.03) not included in table above
Reconciliation Required: Still require discussions about scope
PRELIMINARY

## Slide 25: Cost and Schedule Update
Site Preparation (121.06.02) and Cryogenics Plant Building (121.06.03) not included in table above
Reconciliation Required: Still require discussions about production rate from Turner
PRELIMINARY

## Slide 26: End