## Slide 1: 3.9 GHz FPC Warm end Installation at SLAC
Ken Premo/Chuck Grimm
LCLS-II 3.9 GHz Cryomodule Transportation Review
13 February 2020

## Slide 2: Installation of 3.9GHz FPC Warm Ends at SLAC
Process and procedures
  Process will follow 3.9 GHz warm end installation used at FNAL
  Special hard copy traveler will be developed, similar to F1.3-07
  Sign offs on hard copy will be scanned as record of installation in Vector
  FMEA will be developed before work starts
Tooling
  Existing tooling design will be utilized
  All tools used for installation will be shipped from FNAL to SLAC prior to installation
Packaging of components
  Warm end components will be packaged for shipment after removal from tested cryomodule
    Serialize coupler positions
  Warm end components will utilize the same configuration as shipped from vendor
    Components will be bagged and purged with N2
    Same shipping restraints as used with delivery from vendor

## Slide 3: Installation of FPC Warm Ends at SLAC
Experienced FNAL personnel will do the installation work
  Personnel with hands on experience on coupler installation
    Sixteen 3.9 GHz warm end installations have been successfully completed on F3.9-01 and F3.9-02
    Many 1.3 GHz warm end installations have been done
Ergonomics
  Ideally the CM will be at a height that is best for warm coupler installation, but we can work with whatever is expected
  SLAC to provide information on expected CM height
    Initial correspondence is SLAC is flexible on height, but may be lower than we normally install couplers
SLAC support needed
  Leak check support (machine and operator)
  Soft wall clean room
  Logistics support (badging/training etc.)
  Similar support as used for F1.3-07 warm end installation

## Slide 4: Installation of FPC Warm Ends at SLAC
Components removed for transport, components remaining for transport
FPC Mounting Brackets
Coupler Pumping Line
Ion Pumps
Under Vacuum
Blank-off Flanges Added

## Slide 5: Installation of FPC Warm Ends at SLAC
Coupler transport support flange replaces warm FPC

## Slide 6: Installation of FPC Warm Ends at SLAC
Coupler transport support flange replaces warm FPC
Same as for FLASH transport
Rubber Bumper
Coupler Shipping Flange
Closed Cell
Foam
Wood Spacer

## Slide 7: Summary
3.9 GHz CMs will be shipped with warm couplers removed
  This uses the same technique utilized for the successful transport of the FLASH 3.9 GHz CM transport to DESY (2009)
  Minimizes concern associated with possible transportation loads
  This configuration was successfully tested on the shaker table
  This configuration was also successfully tested on the Illinois road tests when we had a cavity in position one
Reinstallation of warm couplers at SLAC
  Trained and experienced Fermilab staff will do the work
    Performed similar work for F1.3-07
  Work will be done under the control of a specific traveler
    In accordance with FMEA
  Existing tooling will be used
  All tools used for installation will be shipped from FNAL to SLAC prior to installation
  Do not see any issues with performing this work at SLAC