## Slide 1: Summary of 3.9 GHz Transportation Readiness
Brian Hartsell
LCLS-II 3.9 GHz Cryomodule Transportation Review
13 February 2020

## Slide 2: Summary
Due to the project’s risk tolerance, we are taking the most conservative approach we can to mitigate risk.
  Build on proven LCLS-II 1.3 GHz and 3.9 GHz FLASH transports and incorporating their best practices and lessons learned.
  Followed processes to help identify further areas to study.
    Completed a “fresh look” series of reviews on the 3.9 GHz cryomodule design driven by input from experts and simulations.
    Performed rigorous analysis to identify and quantify risk areas.
  Followed a systematic approach to verify transport performs to expectations.
    Incremental dummy load road testing
    Incremental shaker table testing
  The shipping configuration has been tested extensively.

## Slide 3: Transportation plan
3.9 GHz CM transportation plan borrows heavily from the successful 1.3 GHz transportation and the successful 3.9 GHz FLASH CM transportation to DESY (2009).
  Utilized techniques from FLASH: cold mass stabilization, warm FPC removed and replaced with stabilizer, foam inserted between shields and vacuum vessel.
  Equipment, processes, technicians, and drivers are carried over from LCLS-II 1.3 GHz.
The plan calls for a set of road tests before shipping to SLAC in the same manner as the dummy load.
  First – short, low speed test around Fermilab site
  Next – short, high speed test around Fermilab site
  Then – longer ~50mi test out to DeKalb and back
  Finally – ship to SLAC
After each test the data will be analyzed to look for anomalies or areas of concern

## Slide 4: Summary
Expect to ship F3.9-01 at the end of March.
We believe we are ready to begin testing with live 3.9 GHz cryomodules and prove out a plan to ship to SLAC.
4