## Slide 1
Status & Plans
Eric James
FD Technical Board Meeting
February 20, 2020

## Slide 2: Calendar
Far Site I & I Review at FNAL (February 27)
LBNF/DUNE Risk Workshop at FNAL (March 2-4)
LBNC Meeting at FNAL (March 4-6)
Cold Electronics Systems Review at BNL (March 10-11)
RRB Meeting at FNAL (April 2-3)
LBNF/DUNE Director’s Review at FNAL (April 28 – May 1)
Calibration/CI Workshop at CERN (May 7-9)
DSS Review at CERN (May 11-12)
HV System Review at CERN (May 13-14)
Collaboration Meeting at SURF (May 18-22)
PD System Review at FNAL (May 27-28)
APA Shipping Box Review (May/June)
APA Final Design Review (June/July)
DOE IPR at FNAL (July 14-17)
LBNC Meeting at FNAL (July 15-17)

## Slide 3: Interface Documents
Kyle & Terri made some good progress at collaboration meeting on updates to consortia-consortia interface documents
As a next step, they have created a schedule for finalizing updated documents over the next nine weeks (see following slide)
Just to remind everyone, we are targeting having updated interface documents/drawings in EDMS prior to April 17 (and signed interface documents/drawings in EDMS by July 3rd)

## Slide 4: Schedule

## Slide 5: Other Interface Documents
In addition to the consortia-consortia interface documents, we believe these others are also necessary
  DSS – Consortia Interface Documents (signed by Dimitar/Marzio)
  Facilities – Consortia Interface Documents (signed by Filippo/Marzio)
  Installation – Consortia Interface Documents (signed by Jim/Marzio)
Jack Fowler is taking the lead on drafting a generic DSS interface document covering all consortia (we will decide later if this needs to be split up into separate documents)
Updates to facilities-consortia and installation-consortia interface documents will get underway after the upcoming FS Installation and Integration Review on February 27th

## Slide 6: Structural Analysis Notes
Current focus is on producing and reviewing notes covering the APA Shipping Box and HV system
Next highest priority is initiating work on DSS note
Need to understand if any sort of notes are required for Photon Detectors or Cold Electronics
As a reminder, notes need to be finalized 4-6 weeks in advance of planned subsystem reviews to allow time for feedback from compliance office review of note
Notes produced in support of Ash River work will also need to be reviewed in advance of actual activities
Giuseppe serves as the consortia point-of-contact for all matters related to structural analysis notes

## Slide 7: Schedule Development
Ash River/ProtoDUNE-II schedule entered into P6 (see next slide)
Need to incorporate correct links with consortia activities
Working with DAQ consortia to implement a high-level schedule for their activities in P6 this week
The schedule to be used for upcoming Director’s review will be frozen at end of next week
Will continue to work longer-term on incorporating information from consortia cost estimates into P6 activities as a mechanism for extracting annual cost and labor profiles for NCG

## Slide 8: ProtoDUNE-II / Ash River Schedule

## Slide 9: Key Integration Activities
ProtoDUNE-I SP – Operations through April 2020
  Xenon-doping tests
  Pulsed neutron source tests
  Exploring above-nominal HV settings
ProtoDUNE-I DP – Operations through 2020
  Continuing studies to understand detector performance
ICEBERG / EHN1 Cold Box
  System testing of ASIC options
  First baseline data collected in ICEBERG this week
Ash River Prototyping
  ProtoDUNE-II installation tests (phase I) – April to June
  ProtoDUNE-II installation tests (phase II) – July to August

## Slide 10: Key Integration Activities (cont.)
Finalize designs for placement of temperature sensors on APAs over next few weeks
  Requires input from APA, PD, and CE consortia
Cold testing of temperature sensors (and PD infrastructure) on APA frames – currently targeting mid-March at PSL
Creation of full CAD model for ProtoDUNE-II
  Development of scheme/tooling for hanging APAs upside-down
  Development of CAD model for ProtoDUNE-II TPC (connected to ProtoDUNE DSS) – Requires input from APA and HV consortia
  Development of global CAD model for ProtoDUNE-II detector within EHN1 cryostat – Requires input from all consortia
Calibration and Cryogenic Instrumentation workshop at CERN from May 7-9

## Slide 11: LBNC Meeting
Next LBNC meeting is March 4-6 at FNAL
First day is plenary with overview talks on SP, DP technology and SP, DP ProtoDUNE data analysis
Some breakout sessions on the morning of March 5th in the morning currently being advertised as DP, SP Electronics, and SP Installation
I do not believe that in-person attendance is critical except for those giving presentations (the consortia leadership teams are welcome to attend)
Zoom connections should be available (for the breakout sessions in particular)