## Slide 1: Cost & Schedule
Kevin L. Duel
Primary Vacuum Preliminary Design Review
March 10, 2020

## Slide 2: M&S Cost
WBS Total | WBS Description
$205,605 | Pumps
$236,906 | Beam Tubes
$63,189 | Valves/Gauges
$153,967 | Vacuum Instrumentation & Controls
$13,622 | Baking/Cleaning Equipment
$199,282 | Ceramic Beam Tubes Procurement
$105,538 | Ceramic Beam Tubes Fabrication
$978,108 | Total for non-labor M&S
Subcontracted crew labor expressed as M&S | 
$78,970 | Cable installation crew - electrical crew
$22,080 | Compressed air and N2 system installation - pipeftter crew
$4,216 | Lambertson bake electrical installation - electrical crew
$51,840 | Beam tube installation - welder
$157,106 | Total for labor M&S
Increase of ~$125k by going with outside vendor
Savings of ~$116k in FNAL labor and welding
Some increase due to EVAC flanges between dipoles

## Slide 3: Primary Beamline
Primary Beamline layout of magnets and vacuum
Kickers
Lambertsons
MI Wall Penetration
Temporary Shield Wall (not shown)
Target Hall Wall
Main Injector

## Slide 4: Beamline Schedule Summary
Beamline Checkout Period
FY29
FY28
FY27
FY26
FY24
FY23
FY22
FY21
FY20
FY19
FY30
FY31
FY25
Extraction Enclosure (Long Shut Down)
Magnets
Production Horns A, B, C
Target Shield Pile
Disassemble MI Components
Conventional Construction
Install New / Re-install Existing Components
Beamline Final Design
Target Complex
Install Target Shield Pile/ Battlement/Cooing Panel Install
Mechanical and Electrical Rough-in
Install Horn A, B, C and initial Power-up/ Leak Check chase
Absorber Component Installation
Decay Pipe Upstream Window, Muon System - Install
Mechanical and Electrical Rough-in
Remote Handling Installation & Commissioning
Target Complex Authorization for Use and Possession
Beamline Preliminary Design
TC –Final Design – Remote Handling
DP&AC Final Design – Hadron Monitor
SI Final Design – interlocks
Procurement/ Assembly
Material Purchase Constraint
Material Purchase Constraint
Authorization for Use and Possession
Near Site Critical Path
Main injector – Second Shutdown Begins
A B C
Decay and Absorber Complex Authorization for Use and Possession
Primary Beam Enclosure
Upstream of Shield Wall
Downstream of Shield Wall
Beamline Complete
DOE and Non-DOE Activity
PB Final Design - Instrumentation
Target Complex
Absorber Complex
Decay and Absorber Complex

## Slide 5: Design Schedule
Preliminary design ramped up around March 2019
March 2020 – June 2020
  Dipole Beam Tube Design and Specification Updates
    150 hrs eng, 80 drafting
  Final Design of Turbocart
    120 hrs eng, 160 drafting
  Final design of beam tube, ion pump, and gate valve stands
    92 hrs engineering, 160 drafting

## Slide 6: Design Schedule
June 2020 – September 2020
  Final design of beam tubes and connections
    190 hrs engineering, 260 drafting
  Develop cleaning, handling, & certification procedures
    80 hrs engineering, 40 technician
September 2020 – December 2020
  Final design of instrumentation & controls
    190 hrs engineering, 200 drafting
  Finalization of cleaning, handling & certification procedures
    40 hrs engineering, 20 technician

## Slide 7: Design Schedule
December 2020 – February 2021
  Final vacuum installation drawings
    75 hrs engineering, 120 drafting
March 2021
  Final Design Review
December 2022 – January 2023
  Final revisions to beam tubes for BPM final design
    50 hrs engineering, 80 drafting
~ 1 year of final design activities

## Slide 8: Design Schedule Kicker Beam Tubes
Now through May 2020
  SEY testing of kicker beam tubes
    12 hrs engineering, 22 engineering physicist
May 2020 – June 2020
  Update kicker beam tube flanges and bellows design
    80 hrs engineering, 80 hrs drafting

## Slide 9: Procurement Schedule
October 2025 – October 2026
  Turbocarts
  Ion pumps
  Beam tube assemblies
  Instrumentation
  Compressed air & nitrogen
October 2026 – January 2027
  Component vacuum certification

## Slide 10: Procurement Schedule Kicker Beam Tube*
July 2024 – June 2025
  Cut, lap, and braze
July 2025 – January 2026
  Apply resistance coating (Aerodag)
    Includes baking, leak checking, inspection, etc
January 2026 – June 2026
  Custom bellows welding
July 2026
  Production kicker assembly (Magnets BOE)
*Marked for early procurement – will start earlier than shown

## Slide 11: Installation Schedule
February 2027
  Install cabling, compressed air, nitrogen upstream of shield wall & MI
March 2027 – May 2027
  Install beam tubes upstream of shield wall & MI
  Install ion pumps, valves, gauges upstream of shield wall & MI
December 2027
  Install cabling, compressed air, nitrogen downstream of shield wall
July 2028 – August 2028
  Install beam tubes downstream of shield wall
  Install ion pumps, valves, gauges downstream of shield wall