## Slide 1: Magnet Fabrication Travelers, Non-Conformities and Resolution
Katherine Ray – LBNL (QA)
Mike Solis – LBNL (Procurement Technical Contact)
March 12, 2020 – MQXFA05 Structure and Loading Review

## Slide 2: Overview
State of the Magnet Fabrication Travelers
Non-Conformances on MQXFA05

## Slide 3: Magnet Fabrication Travelers Overview
# | Title | Revision | ID
1 | Coil Acceptance WI | A | SU-1011-5294
2 | Yoke Pre-Stack WI | B | SU-1008-8072
3 | Yoke Half Stack WI | C | SU-1009-7829
4 | Shell Instrumentation WI | D | SU-1009-3745
5 | Shell-Yoke Assy WI | B | SU-1008-2169
6 | Loadpad Pre-Stack WI | B | SU-1008-8075
7 | Dressed Coil WI | E | SU-1008-8073
8 | Pad-Collar Assy WI | A | SU-1010-1610
9 | Coil Pack Subassy WI | B | SU-1008-8074
10 | Magnet Electrical QA at LBNL | C | SU-1010-1903
11 | Magnetic Measurements | A | SU-1010-2018
12 | Integration and Loading WI (based on 2 other WI, both @ Rev B) | B | SU-1011-5637
13 | Axial Rods Instrumented WI | C | SU-1008-8069
14 | Splice Box WI | B | SU-1008-8067
15 | Magnet Shipping WI | A | SU-1011-3284

## Slide 4: Magnet Fabrication Travelers Overview
# | Title | Revision | ID
1 | Coil Acceptance WI | A | SU-1011-5294
2 | Yoke Pre-Stack WI | B | SU-1008-8072
3 | Yoke Half Stack WI | C | SU-1009-7829
4 | Shell Instrumentation WI | D | SU-1009-3745
5 | Shell-Yoke Assy WI | B | SU-1008-2169
6 | Loadpad Pre-Stack WI | B | SU-1008-8075
7 | Dressed Coil WI | E | SU-1008-8073
8 | Pad-Collar Assy WI | A | SU-1010-1610
9 | Coil Pack Subassy WI | B | SU-1008-8074
10 | Magnet Electrical QA at LBNL | C | SU-1010-1903
11 | Magnetic Measurements | A | SU-1010-2018
12 | Integration and Loading WI (based on 2 other WI, both @ Rev B) | B | SU-1011-5637
13 | Axial Rods Instrumented WI | C | SU-1008-8069
14 | Splice Box WI | B | SU-1008-8067
15 | Magnet Shipping WI | A | SU-1011-3284
We continue to update the travelers based on lessons learned
All travelers were used and signed off for MQXFA04

## Slide 5: Change Records
We are tracking Non-Conformances, Deviations and Engineering Changes in one spreadsheet
These are currently communicated to Fermilab L2 on a monthly basis

## Slide 6: MQXFA05 Change Records
The NCRs on A05 thus far include:
  (#24) Minor collar dimension issues
  (#43) Minor collar dimension issues
  (#44) Shell thread damage
  (#68) Sharp edges on wiring skirts, skirts made of 5052 Al
  (#69) Cable support had hole in wrong location
  (#80) Dents in Master Keys
  (#83) ~60 yoke bushings were undersized

## Slide 7: MQXFA05 Change Records Details
  (#24) Minor collar dimension issues
  (#43) Minor collar dimension issues
  “Profile 0.03 at the 45° plane of the 25 or 45 mm scan” out of tolerance by 0.0002mm to 0.0047mm in 9 locations. We believe all are due them scanning over the engraved serial number (ACCEPT AS IS)
  (#44) Shell thread damage
  One M6 holes has 2-3 threads damaged (ACCEPT AS IS)
  (#68) Sharp edges on wiring skirts, skirts made of 5052 Al
  Need to discuss if 5052 Al is okay
  (#69) Cable support had hole in wrong location
  Vendor is sending new parts
  (#83) ~60 yoke bushings were undersized
  Undersized bushings did not fit over yoke tie-rod and were replaced. Decision about reworking or rejecting undersized bushings has not been made yet.

## Slide 8: MQXFA05 Change Records Details
  (#80) Dents in Master Keys
  Largest dent was 3.5mm long and .13mm deep
  Two more dents,
  1.8mm long dent on 45 deg surface
  Smaller dent over bladder