## Slide 1: Overview and Status of ALS-U Project Vacuum Systems
Sol Omolayo
April 15th, 2024

## Slide 2: Outline
ALS-U Project Overview
ALS-U Vacuum System Scope and Status
NEG Coating Development Status

## Slide 3: Advanced Light Source Upgrade at LBNL
Dark time
(SR Install)
2026
2016
Project Launch
Conceptual Design
2018
Preliminary Design
2021
2022
Final Design
Accumulator Ring
(AR)
Storage Ring
(SR)
AR Install
2023

## Slide 4: ALS-U Project: Motivation – Lower Emittance & Higher Brightness
ALS-U: nine-bend achromat with reverse bends
ALS today : triple-bend achromat
Large increase in coherent fraction due to lower emittance and smaller b-functions
71
Storage Ring Parameters | Value
Electron energy | 2.0 GeV
Average current | 500mA
Bunch Length (FWHM) | 110 ps
Total lifetime | >0.5h
Circumference | 196.510 m
ALS 1994
ALS-U 2028

## Slide 5: Enabling new science frontiers
Infrared
Hard
Tender
Soft
VUV
40 beamlines
2,100+ users/year
950+ pubs/year
20% in high-impact journals
Quantum Materials Research & Discovery
Multiscale Structure & Dynamics
Chemical Transformations
Earth, Environment & Biological Systems
Instrumentation Science

## Slide 6: ALS-U Vacuum System Scope
Design, procurement and assembly of vacuum systems and components for the AR, BTA, SR, ATS and STA
Dynamic Pressures
  AR < 1e-8 Torr
  BTA, ATS, STA < 5e-8Torr
  SR <5e-9 Torr
STA
Booster
BTA
ATS
SR
AR
BTA – Booster to Accumulator ring
ATS - Accumulator to Storage Ring
STA - Storage Ring to Accumulator Ring

## Slide 7: AR Assembly and Installation
Modular
Pre-assembly
Installation
Commissioning
Component QA
Component
Pre-assembly
84 Arc Modules
12 Straights

## Slide 8: AR Vacuum System On-site Assembly and Production
Raft Vacuum Production
Dipole Production
Bakeout controller
Assembly Table
4 x Raft 4s
Vacuum
Diagnostics
S&A
Pre-staging
Stress relieving and Inspection
Leak check and cleaning
Prep NEG coating
NEG coating
NEG Inspection
Liftoff
Pre-staging
Leak checking and pre-assembly
Assemble
BPM measurement
Alignment
Leak check
Prep for bakeout
Bakeout – 4days
Prep for removal
Go-no-go gauge

## Slide 9: AR Vacuum System On-site Assembly and Production
Portable CMM dedicated to vacuum use
BPM Performance Tuning using Vacuum Flanges
High Density Vacuum Module Storage

## Slide 10: AR Sector Vacuum Layout
4 x In-line Ion Pump
7 x RF Bellows
Dipole Chamber
Standard Straights
Multipole Chamber Assemblies
6 x BPMs
9 x NEG Cartridges
Beam Direction
Raft#1
Raft#2
Raft#3
Raft#4
3 x Vacuum Assembly Types
Multipole Chamber Assembly
Dipole Chamber Assembly
Standard Straight Assembly
Vacuum Only
Vacuum + Magnets

## Slide 11: ALS-U AR Vacuum System Production
AR Vacuum systems in numbers
  1,152 vacuum components on AR (excl vacuum supports & electrical), 95% delivered
  494 awards (66>$10k) totaling $10M
  AR vacuum volume 384 liters.
  AR vacuum pumping 24k l/s H2, 10k l/s CO
  AR vacuum has 8,640 fasteners (excl vacuum supports)
Major outstanding item is AR dipole chamber
  2 parallel production paths (vendor, in-house)
  2 x first article received one from each production path
  4 production chambers expected this month
AR Dipole Production (Vendor)
AR Dipole Design
Tube forming
EDM machining
Cu/SS Tig welding
Ebeam welding
NEG Coating
ALS-U Project | OLAV-VI Workshop| April 16th 2024

## Slide 12: Storage Ring Sector Layout – Sector 5
Beamline 5.0
Frontend 5.0
Sector Gate Valve
Storage Ring
Vacuum
Beamline
Vacuum
Frontend 5.3
Frontend 5.4 - IR
Frontend Gate
Valve
Sector Gate Valve
Future 5.1 Frontend
Stop
Clearing Magnets
Photon Transport Line
ID Crotch
Typical:
Pole to Pole = 89mm
Yoke to Yoke = 128mm
Coil to Coil = 77mm
Access
First frontend gate valve

## Slide 13: Key SR Vacuum Design Features Summary
In-situ bakeout and NEG activation with possibility of Neon venting
Combination of distributed and discrete absorbers
Modular design that conforms to magnet raft layout for ease of pre-assembly and installation
60% NEG coating
Discrete pumping with ion pumps and NEG cartridge pumps in SR arcs.
Limited NEG coatings in straights and PTL.

## Slide 14: Vacuum chamber apertures
ALS-U Project | OLAV-VI Workshop| April 16th 2024
13mm
100mm
100mm
13mm
20mm
10mm
29mm
5mm
13mm
7mm
13mm
7mm
High Field Magnet Chamber
1 Arc Sector
900mm

## Slide 15
Vacuum Chamber Designs & Procurement
Broad array of vacuum chambers and components
Majority of the chambers are NEG coated
Stainless Steel Chamber
Keyhole & HHL Chamber
Crotch Chambers
VC01
VC16
VC02
VC03
VC05
VC08
VC11
VC15
VC10
VC04
VC12
Beam Egress Chamber
VC06 and VC09
VC07
VC13
RF Bellows

## Slide 16: With 1000Ah conditioning, the total average lifetime is expected to be 0.9h (‘post-LOCO’ corrected lattices)
Gas-pressures for 1000Ah, 100Ah, and 10Ah conditioning …
… and corresponding “post-LOCO” elastic-collision vacuum life
 | 1000Ah | 100Ah | 10Ah
elastic | 9.4 | 2.4 | 0.68
inelastic | 74.7 | 20.7 | 6.2
total vacuum | 8.3 | 2.2 | 0.61
total** | 0.9 | 0.68 | 0.38
Beam partial and total average lifetime* (h): break-down by conditioning
* Post-Loco DA assumed
** 1h Touschek lifetime assumed (not crediting overstretching)
ALS-U Project | OLAV-VI Workshop| April 16th 2024

## Slide 17: SR Vacuum Prototyping
3D Printed CuCrZr
After post machining
VC-02 ID Egress Chamber
H-Bend Chamber
H-Bend Copper chamber NEG coating trials
Conventional Machined
3D Printed CuCrZr

## Slide 18: SR Integrated Prototyping
Integrated SR Raft Mockup
SR Magnets – Vacuum Integrated Prototype
Magnet – vacuum assembly and alignment sequence, in-situ vacuum bakeout and NEG activation
Magnet cabling and LCW routing, raft assembly sequence, general cabling and controls integration

## Slide 19: NEG Coating Development Objective
Demonstrate current NEG coating technology is applicable to ALS-U relevant chambers
Explore/develop industry and research capability and partnerships – SOLEIL, STFC, ESRF, SAES, FMB
Develop in-house NEG coating capability
SIRIUS
MAX-IV
CERN, 2000s
MAX-IV, SIRIUS, 2010s
ALS-U, SOLEIL, 2020s
10mm
20mm
60mm
ALS-U, 2020s
6mm

## Slide 20: ALS-U NEG Coating Systems
2m long X 300mm wide NEG coating rig
4m long narrow NEG coating rig
NEG coating for large complex chambers
PM Assembly

## Slide 21: Pumping performance
Sample | H2 Sticking Coeff. | CO Sticking Coeff. | CO Capacity
CERN Benchmark | 0.007 | 0.7 | 8e-14 [molecules/cm]
LBL 6 mm | 0.007 | 0.03 | Comparable to CERN
LBL 9 mm | 0.007 | 0.25 | Comparable to CERN
Vendor1 6 mm | 0.0025 | 0.003 | low
Vendor1 9 mm | 0.0065 | 0.015 | low
ESRF 6 mm | 0.003 | 0.004 | low
ESRF 9 mm | 0.005 | 0.01 | low
Vendor2 10 mm | 0.005 | 0.0015 | poor
Factor that impact pumping performance
Substrate temperature
Cathode voltage
Plasma power or deposition rate
Initial base pressure
Coating pressure
Tube ID
NEG wire contamination content
Moving magnets vs full length solenoid
Gas purity
DC power vs pulsed-DC power
NEG wire degassing
Substrate roughness
Findings
9mm samples consistently performs better than 6mm – aspect ration rules out
In-house coated sample out performs those sourced externally
Vendor and other labs struggle with coating 6mm. Some declined
Vendor1 9mm
Vendor1 6mm
ALS-U Project | OLAV-VI Workshop| April 16th 2024

## Slide 22: Pumping comparison at SOLEIL
CERN-TS-2006-001(MME); Ti-Zr-V non-evaporable getter films: from development to large scale production for the Large Hadron Collider.
ALS-U Project | OLAV-VI Workshop| April 16th 2024

## Slide 23: PSD Measurement at SOLEIL

## Slide 24: SEM Analysis of NEG film morphology
SEM samples
Ti,Z,V
T = 100oc
T = 120oc
A.Anders, A structure zone diagram including plasma-based deposition and ion etching, Thin Solid Films, 2009
ALS-U Project | OLAV-VI Workshop| April 16th 2024

## Slide 25: Thank you