## Slide 1: Magnet-Vacuum Module Assembly of the APS-Upgrade Storage Ring Vacuum System
April 17th, 2024
Nicholas Bechtold
Module Assembly CAM
Mechanical Engineering and Design Group

## Slide 2: Outline
APS-Upgrade Overview
Facilities for Inventory Storage and Assembly
Scope
Inventory Management
Work Planning and Control
Timeline

## Slide 3: APS-U high level requirements
40 sectors (each sector consists of 5 modules)
Beam Energy = 6 GeV
Beam Current: > 200 mA
Max. single bunch current: > 4.2 mA
Circumference: 1103.608 meters

## Slide 4: Facilities for assembly and inventory storage
100,000 sq ft warehouse

## Slide 5: Modules in storage
https://youtu.be/LltYSncc0JI?list=PL994D8197DEEFCC59

## Slide 6: Assembly bays
5 bays for large modules
4 bays for QMQ Bridges

## Slide 7: Scope
Incoming inspection of parts from suppliers
Mount and align magnets
Install and align vacuum chambers
Leak check vacuum chambers
Bake-out wiring
Magnet Re-assembly
Hipot and Hydrostatic testing
Sector Mockup

## Slide 8: Mount and align magnets
Bottle jacks used to position girder
Magnets mounted in location
Survey and alignment determine shim pack for each magnet

## Slide 9: Split magnets
Flange bolts, rough locating pins, and taper dowel pins are used to locate top half of magnet
Custom tooling was used, but soft pins lead to issues
All taper pins replaced with custom hardened pins

## Slide 10: Split magnets
Swivel hooks, shackles and overhead cranes used to split magnets
Top half of magnets set on cribbing to avoid damaging mating surfaces

## Slide 11: install vacuum chambers
Space between adjacent magnets is limited
Chain clamps used to save space - need to be retorqued as they relax over time
Annealed gaskets used
Leak check
Survey and Alignment

## Slide 12: preassemblies
Keyhole chamber trio
  Space limited, bottom bolts inaccessible in-situ due to magnets
  Custom assembly and lifting fixture (next slide)

## Slide 13: Custom tooling and fixtures
Chamber trio assembly and lifting fixture
Made from 3D print and off-the-shelf materials as much as possible
80/20 cut to length by Argonne shops with fairly tight tolerances to ensure flat assembly

## Slide 14: QMQ Chambers
Assembled and leak checked prior to being installed in module.
Spreader bar used for dipoles and dipole chambers

## Slide 15: FODO Cross
Preassembled cross

## Slide 16: 3D Printed fixtures
BPM Bellows setting – 3 types, nominal, minimum bellows length and maximum bellows length
Chamber height
Measuring chamber roll – water chamber and heater not same thickness
Parts of fixtures to limit machined components

## Slide 17: Reassemble magnets
Tight tolerances – pole tips and chambers
Roll control during assembly important

## Slide 18: Split magnet and install vacuum chambers
Video of Q5 pole gap to chamber

## Slide 19: Inventory management
All materials entered in the Component Database
CDB items have QR Code applied
All storage/assembly locations also have QR Code

## Slide 20: Component database
Scanned QR code brings you to inventory page
  Status
  Location
  Housing
Notes: Each tab on the right is expandable to see more information

## Slide 21
Notes: Associated eTravelers and components installed on the module

## Slide 22: Etravelers
Document and track any/all work performed
QA and process steps
Discrepancy reporting
Data collected during work
Signed off by responsible engineer

## Slide 23: Inter-group handoffs
Trello - Quick Status
Checklist and Automation
Email notifications
Exports can be used for reporting
eTraveler feedback

## Slide 24: Checklist and Automation
Each checkbox correlates to work performed on module – labels for which group is responsible
Checked box triggers automation to move card into correct list and send email notification to the group performing next task

## Slide 25: Work planning and control
All work is covered under a Work Control Document (WCD)
  Establishes scope of work
  Limits of scope
  Planned start and end dates of work
  Documenting tasks to be performed under the scope of work
  Location work is to be performed
  Training required to perform work covered under WCD
Assembly WCD

## Slide 26: Sector Mockup
Used to practice QMQ install
Inter-module vacuum connections
Bakeout wiring connections between modules

## Slide 27: Moving modules - QMQs
Move in any direction
Can be raised and lowered

## Slide 28: QMQ Cart issues
Move in any direction
Can be raised and lowered
Wire routing caused pinching, lead to intermittent responding to commands
Ground flatness – drive wheels need to contact ground

## Slide 29: Assembly progress over time
Chart: 
| 44931 | 44938 | 44945 | 44952 | 44959 | 44966 | 44973 | 44980 | 44987 | 44994 | 45001 | 45008 | 45015 | 45022 | 45029 | 45036 | 45043 | 45050 | 45057 | 45064 | 45071 | 45078 | 45085 | 45092 | 45099 | 45106 | 45113 | 45120 | 45127 | 45134 | 45141 | 45148 | 45155 | 45162 | 45169 | 45176 | 45183 | 45190 | 45197 | 45204 | 45211 | 45218 | 45225 | 45232 | 45239 | 45246 | 45253 | 45260 | 45267
Modules Completed | 0 | 8 | 16 | 24 | 26 | 29 | 30 | 37 | 42 | 48 | 55 | 63 | 71 | 80 | 88 | 95 | 105 | 111 | 118 | 125 | 133 | 136 | 142 | 150 | 157 | 162 | 164 | 167 | 171 | 175 | 176 | 177 | 177 | 178 | 179 | 181 | 183 | 184 | 185 | 186 | 186 | 187 | 187 | 191 | 192 | 196 | 199 | 201 | 203

## Slide 30: Timeline
Fall 2021
Moved into offsite warehouse
Jan. 2022
Magnet-Vacuum module assembly starts
*vacuum deliveries on critical path, all magnets mounted and aligned
Jan 2023
First module completed
Dec. 2023
Final production module completed
Apr 2023
Storage Ring enters Dark Time
Vacuum component availability became a schedule driver

## Slide 31: Lessons learned
Scope:
Establish handoffs between working groups and processes
Explicitly state who is responsible for each necessary task so gaps can be identified
Documentation
We improved our processes as we progressed
Documentation needs to be updated to reflect refinement.
Repetitive Tasks
Can lead to complacency
Identify trends – small mistakes can be a precursor to larger issues

## Slide 32: Questions