## Slide 1: Neutrino Beamline Horn A Preliminary Design Review
Cory Crowley
24 April 2020
Review Summary

## Slide 2: Outline
Summary of Charge Questions
Reference Presentations / Review Materials
Final Design Plans
Testing Plans
Horn A Schedule

## Slide 3: Charge -- 1 of 2
Does the preliminary design meet the requirements of the optimized beamline parameters?
Is the design maturity presented for the Horn A conductors, stripline, interfaces, and ancillary systems at a level appropriate for the Preliminary Design Phase, as guided by the LBNF / DUNE Review Plan?
    Based on acceptable progress for Preliminary Design as 50 to 70%, with 100% equal to “completion of Preliminary Design phase”.
    Are areas where components are awaiting forthcoming development well understood?
    Final Design will be drawing-intensive in comparison to the first two phases of design.
Have suitable engineering analyses been performed and documented, and reviewed/peer reviewed and approved, where applicable?
Does the anticipated design life meet experimental requirements of 1E8 pulses or 2 years of operation prior to failure?
Have the ES&H issues been identified and analyzed appropriately?
Have the Fermilab Engineering Manual standards been applied to the design?

## Slide 4: Charge -- 2 of 2
Have potential design, manufacturing, and installation risks and challenges been identified within the Horn A WBS, and has it been adequately planned to address these during the final design?
Are difficult design features and possible prototyping issues identified? es the preliminary design meet the requirements of the optimized beamline parameters?
Is the level of integration with other LBNF beamline entities appropriate for this stage of the work? I.E. Are interfaces and collaborative design inputs being managed appropriately?
    A major Horn A system interface is the integrated target, which is being designed and built by RAL. Have all integration activities pertaining to the mating of these components been identified?
    Are there any outstanding design considerations for the integrated target which have not been identified by the design teams?.
Select Horn A components are currently undergoing estimation review through the Project Estimator. This includes the submission of sample packages to outside vendors for spot-checking of current values. With this in mind, a cursory check of the cost and schedule are desired:
    To verify top level cost estimates for prototype and production horn fabrication & testing.
    To question sufficiency of design resources with known complexity of certain features, such as stripline ceramics design, stripline welding, & conductor welding

## Slide 5: Reference Presentations / Review Material
All presentations & review material are permanently stored in DUNE-Doc-18562.
  Will add review comments and daily answers to questions.
  Design team responses to reviewer input will be posted when received.

## Slide 6: Final Design Plans
Get final approval from BIWG for horn components as modeled.
  Laura Fields / Zarko Pavlovic official email, memo, or equivalent.
Complete last FEA run on conductor assembly with final loading conditions applied. Pursue efforts to thin D.S. transition flange & keep S.F. above 2.
Complete last FEA run on stripline assembly with all known loading conditions applied, pending successful mechanical test of stripline bolt group & electrical test of resistance to corona inception & arcing.
Finish modeling on ancillary systems:
  Brackets, hardware, updates from review.
  Check over sizing & tolerances.
  Begin fixturing design for welding, water lines, stripline chamfers, etc…

## Slide 7: Final Design Plans Cont.
Provide a final integration model to RAL that serves as agreed upon reference going forward for fabrication.
Need both sides to “sign-off”: email, memo, or equivalent documentation.
Finish all inputs on parameters & specifications worksheet. Work with integration managers to get interfacing WBS/technical lead approvals prior to fabrication release.
  Targetry, RAW, Civil, Target Chase/Shielding, Power Supply, Remote Handling, Modeling.
Drawing Packages
  Most drawings are generated for Horn A piece parts.
  Need high level drawings (weldments, main assemblies, system layouts).
  Significant time on final tolerancing & component listings for purchase.

## Slide 8: Testing Plans
Friction stir weld vendor testing ongoing and results expected in May. Will help confirm:
  Weld efficiency.
  Weld shrinkage (feeds into drawing package material allowances).
  Flatness / quality / finish etc…
  Drawing package decision (bolt layer 5 at middle or stick with 1 piece finished weldment.
Stripline bus prototype.
  All parts expected in May. Need to work out assembly & testing timeline with AD/TSD + AD/EE-Support.
  Check ceramic interface, confirm sensitivity of bolt threads through center.
A full-scale Horn A prototype will be built & tested at MI-8 facility.
Testing activities above have implications for all horn designs.

## Slide 9: Horn A Schedule
Horn A has ~10 months left before we are ready to build (Feb. 2021).
Schedule allowance for fabrication is ~2.25 years (May 2023).
  Factors speeding up build time:
    Only 2 inner conductor welds, with identical NuMI weld preps.
    No outer conductor welding: bid out port fabrication, weld, & assemble.
    Simplified cooling loops for stripline flange.
  ~1.5 years schedule float if test stand not advanced.
  Off critical path by few months because of this delay. Would rather have more total schedule float to implement possible Horn B & C changes sooner.
Test stand timeframe for prototype is 8 months.
  Covers installation, vibration measurements, magnetic field measurement, post test inspection, prototype target installation trials + additional pulse testing of integrated target & horn assembly.
Production horn build starts 2025 after prototype testing complete.

## Slide 10: Summary
Design model is advanced, but much back-end work to do:
  Primarily assembly & high level drawings, final analysis runs, part revisions & creation of ancillary structures.
  Must develop additional procedures & fixturing prior to fabrication readiness review.
Risks exist but are being mitigated. Will have better feeling after tests complete and detailed design firms up.
Horn A represents bulk of engineering & design load to WBS. Horns B & C will use ~75% of design concepts from Horn A.
Schedule is funding limited based on test stand availability. Efforts ongoing to speed up design & take advantage of engineering resources available now.
Horn A design schedule and costs are currently on-track.

## Slide 11: Summary
            Thank you for your time!
            Questions?