## Slide 1
Status & Plans
Eric James
FD Technical Board Meeting
April 9, 2020

## Slide 2: Activity Updates
Xenon-doping of ProtoDUNE-SP has resumed and detector is being monitored remotely via minimal DAQ configuration
Some limited, ProtoDUNE-DP CRP testing that can be performed done remotely is being resumed this week
Prototyping work has continued at Ash River taking advantage of the minimal operations team in place
  EW Field Cage modules were assembled last week

## Slide 3: Targeted Events
RRB Meeting on April 2
LBNF/DUNE Director’s Review during week of May 18th
DOE IPR on July 14-17

## Slide 4: RRB Meeting
Remote RRB meeting took place on April 2 (last week)
The meeting was well-attended by the funding agency representatives
Current plan for baselining the US project was presented and discussed
Next meeting is planned for October 8-9
  This would be the final meeting prior to US project baselining, and we will be targeting initial approval of the DUNE MOU
  NCG reviews will need to be completed in advance of this

## Slide 5: LBNF/DUNE Director’s Review
Project (P6) schedule has been re-opened to incorporate changes reflecting the current plan for baselining
As part of this process, Gina and I are working with the DAQ and CALCI consortia to incorporate initial schedules for their systems
This schedule will be re-frozen for the upcoming review on the time scale of late next week
Materials for the review will need to be posted by ~ May 4

## Slide 6: DOE IPR
Project (P6) schedule for this review will be frozen at the end of May (~7 weeks)
All materials need to be posted by June 30 (~11 weeks)
Targeting full set of resource-loaded international detector activities in P6 schedule by end of May
Targeting complete sets (all four types) of signed interface documents in EDMS
Targeting completion of HV system, Photon Detector, APA Shipping Box, and DSS reviews on this time scale
Targeting completion of CALCI and Background Mitigation workshops

## Slide 7: Interface Documents
Currently targeting four sets of interface documents:
  Consortia-to-consortia (Kyle & Terri)
  Consortia-to-installation (Jim)
  Consortia-to-DSS (Jack)
  Consortia-to-facilities (TBD)
Deadline for initial posted drafts of those in red is end of next week (April 17)

## Slide 8: Interface Documents
Additional goals for July IPR:
  Finalization of consortia-to-DSS and consortia-to-facilities documents
  Appropriate sign-offs for all EDMS interface documents

## Slide 9: Schedule
With the re-opening of the P6 schedule for the upcoming Director’s Review, Gina and I are back to working on incorporating full, high-level sets of non-DOE activities for each system
Goal is to then resource-load these activities from consortia cost spreadsheets so that we can obtain annual labor and M&S profiles requested by NCG
Targeting providing these materials to the NCG by early May so that they can provide initial review feedback on the time scale of the July IPR

## Slide 10: Technical Reviews
Final Preliminary Cold Electronics has been ongoing (remotely) over the past several weeks – expecting closeout next week
Working with Review Office to schedule additional reviews needed prior to July IPR (see next slide)

## Slide 11: Proposed Review Schedule
System | Structural Analysis Note Ready | Note Review Complete | Review Target
HV System | Notes posted on April 3 | Early May | Mid-May
APA Frame & Shipping Box | Targeting April 24 | Late May | Early June
Photon Detection | TBD | TBD | Late June
DSS | Late May | Early July | Mid-July

## Slide 12: Requirements
Steve has been working with consortia to define what is needed in terms of requirements for upcoming reviews
  High-level requirements (28 for SP Far Detector) held by the DUNE Executive Board
  Lower-level consortia requirements held by DUNE Technical Board (APA-6, HV-2, CE-8, PDS-16, DAQ-8, CALCI-17, and Installation-6)
  Consortia-held interface, installation, production, and shipping requirements (based on controlled interface documents and consortia QA/QC plans)

## Slide 13: Requirements
First two categories (as defined in TDR) are now captured in EDMS (EDMS-0000195183) and DOORS (LBNF/DUNE Project Tool)
  Consortia should bring proposed changes to Technical Board
Last category should be captured in spreadsheets for upcoming design reviews (goal is to distill information contained within interface documents and QA/QC plan to guide review team)
More in Steve’s presentation

## Slide 14: QA/QC Plan
Kevin and Jim are in the final stages of producing a template (based on the already completed APA Preliminary Design Review) for what a consortium QA/QC document should look like at the time of a Preliminary Design Review
There will be a presentation on this at the next Technical Board Meeting

## Slide 15: CALCI Scope Workshop
Workshop is meant to play an important role in clarifying the baseline scope of far detector calibration and cryogenic instrumentation systems (needed for July IPR)
Workshop will be held remotely over a three week period beginning May 11th
Charge has been posted to DUNE DocDB 17985
In final stages of forming review committee

## Slide 16: Background Mitigation Workshop
We also need to have a follow-up workshop on background mitigation strategies for the underground caverns
  There is a specific previous review recommendation on this topic that we need to respond to at the July IPR
Working to see if we might be able to squeeze this in before July IPR – would most likely have to be held at the last minute (in early July)