## Risk Elements
Engineering Risk Assessment
Project: | PIP II 25KW Absorber
Lead Engineer: | Nnamdi Agbo
Reviewed By:
Date: | 2021-05-18
Score
Technology |  | 2 - Low to Medium Risk | 2
This defines the degree of technical complexity the Lead Engineer or engineering team will face in executing the project.
1 The project will use off-the-shelf technology.
3 Engineers will purchase and modify off-the-shelf technology.
5 The project will require the development of new technology.
Environmental Impact |  | 3 - Medium Risk | 3
This defines the potential level of environmental impact.
1 There will be no environmental impact.
3 The project may have some environmental impact but will not require an environmental assessment, as determined by FESHM.
5 The project will require an environmental impact statement.
Vendor Issues |  | 2 - Low to Medium Risk | 2
This defines the degree of complexity to be expected with vendors. Complicating factors may include long-lead-time items and issues with vendor qualification and reliability.
1 Vendors could cause minor issues.
3 Vendors could cause manageable complications.
5 Vendor issues could result in significant schedule delays or cost overruns or could otherwise jeopardize the successful completion of the project.
Resource Availability |  | 3 - Medium Risk | 3
This defines the availability of internal and external resources to plan and execute the project.
1 Resources will be readily available.
3 Resources could be somewhat restricted.
5 The difficulty of obtaining resources puts the project schedule at high risk.
Quality Requirements |  | 3 - Medium Risk | 3
This determines the effort required to achieve the quality level the customer assigns to the final product.
1 The quality requirements can be met easily with existing infrastructure.
3 The quality requirements are challenging but can be met with existing infrastructure.
5 The quality requirements are beyond the capability of existing infrastructure.
Safety |  | 2 - Low to Medium Risk | 2
This defines the safety issues the project team will encounter while completing the project.
1 The project will require standard safety considerations.
3 The project will require increased diligence due to its location, the configuration of the product or the type of work required. This includes work requiring review according to FESHM.
5 The project will require very restrictive safety considerations. This includes work requiring review and personnel safety systems.
Manufacturing Complexity |  | 2 - Low to Medium Risk | 2
This defines the degree of complexity to be expected when combining the elements of technology, operations and schedule in product manufacturing.
1 The manufacturing processes will be routine.
3 The project will require an existing technology that the manufacturer has not previously used.
5 The project will require new or complex manufacturing methods.
Transportation and Rigging Complexity |  | 2 - Low to Medium Risk | 2
This defines the expected complexity of transporting and rigging major components of the project.
1 The transportation and rigging processes will be routine.
3 The project will require some analysis to ensure safe transportation or rigging.
5 The project will require analysis and testing validation to ensure safe transportation or rigging.
Schedule |  | 2 - Low to Medium Risk | 2
This defines how much time the Lead Engineer or engineering team will have to complete the schedule.
1 Time will be unlimited.
3 The schedule will be somewhat constrained.
5 The subproject will be on the overall project critical path and has no schedule contingency.
Interfaces |  | 3 - Medium Risk | 3
This defines the risk associated with the complexity of integrating multiple subprojects.
1 One department at Fermilab will be involved with a standalone project.
3 Project success depends upon contributions from multiple departments at Fermilab.
5 Project success depends upon contributions from multiple institutions.
Experience/Capability |  | 2 - Low to Medium Risk | 2
This defines the level of experience and capability project team members will have.
1 Only experts will participate.
3 A blend of experts and inexperienced personnel will participate.
5 Only inexperienced personnel will participate.
Regulatory Requirements |  | 3 - Medium Risk | 3
This identifies the degree to which oversight by governmental or other regulatory agencies will impact the project.
1 Regulatory agencies will have minor to no involvement.
3 The Department of Energy, DOE, will have direct regulatory involvement.
5 DOE, as well as state or federal government, will have regulatory involvement.
Project Funding |  | 3 - Medium Risk | 3
This defines the availability and approval status of project planning and execution funds.
1 A single source within Fermilab will fund the project.
3 A source outside of Fermilab will fund the project.
5 Multiple sources outside of Fermilab will fund the project.
Project Reporting Requirements |  | 3 - Medium Risk | 3
This indicates the level of reporting to the senior management the project requires.
1 Reports to senior management about the project will not be required.
3 The project will require quarterly performance reports.
5 The project will be highly visible. Top management or outside agencies will schedule visits and issue monthly performance reports.
Public Impact |  | 1 - Low Risk | 1
This indicates how much the project will affect the public or public opinion.
1 The public will not be affected.
3 The public may be somewhat affected and should be informed with news releases.
5 The project may have an impact on the public. The public should be involved through public forums and may participate in advisory councils.
Project Cost |  | 4 - Medium to High Risk | 4
This defines how much the project is projected to cost.
1 The project will be within the department operating budget.
3 The project will require divisional budget planning.
5 The project will require laboratory or DOE budget tracking and reporting.

## Risk Summary
Engineering Risk Assessment
Project: |  | PIP II 25KW Absorber
Lead Engineer: |  | Nnamdi Agbo
Reviewed By: |  | 0
Date: |  | 2021-05-18
Chapter |  |  | Engineering Risk Element | [7 empty] | High
|  |  | A | B | C | D | E | F | G | H | Risk |  | Subtotal |  | Assessment
1 | Requirements and Specifications |  | Engineering Risk Element A: 2; Engineering Risk Element B: 3; Engineering Risk Element F: 2; Engineering Risk Element H: 2; High Risk: ≥ | 12 | 9 | 0 | Standard Risk
3 | Requirements and Specification Review |  | 2 | 3 |  | 3 | 3 | 2 |  | 2 | ≥ | 18 | 15 | 0 | Standard Risk
4 | System Design |  | 2 | 3 | 2 |  | 3 | 2 | 2 | 2 | ≥ | 21 | 16 | 0 | Standard Risk
5 | Engineering Design Review |  | 2 | 3 | 2 |  | 3 | 2 | 2 | 2 | ≥ | 21 | 16 | 0 | Standard Risk
6 | Procurement and Implementation |  |  | 3 |  | 3 | 3 | 2 | 2 | 2 | ≥ | 18 | 15 | 0 | Standard Risk
7 | Testing and Validation |  | 2 |  |  |  | 3 | 2 | 2 | 2 | ≥ | 15 | 11 | 0 | Standard Risk
8 | Release to Operations |  | Engineering Risk Element F: 2; High Risk: ≥ | 4 | 2 | 0 | Standard Risk
9 | Final Documentation |  | Engineering Risk Element B: 3; Engineering Risk Element F: 2; High Risk: ≥ | 7 | 5 | 0 | Standard Risk
|  |  | Project Risk Element | [7 empty] | High
|  |  | I | J | K | L | M | N | O | P | Risk |  | Subtotal |  | Assessment
|  |  | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 4 | ≥ | 25 | 21 | 0 | Standard Risk
Engineering Risk Elements |  |  | Project Risk Element P: Project Risk Elements
A | Technology |  | Project Risk Element P: I; High Risk: Schedule
B | Environmental Impact |  | Project Risk Element P: J; High Risk: Interfaces
C | Vendor Issues |  | Project Risk Element P: K; High Risk: Experience / Capability
D | Resource Availability |  | Project Risk Element P: L; High Risk: Regulatory Requirements
E | Quality Requirements |  | Project Risk Element P: M; High Risk: Project Funding
F | Safety |  | Project Risk Element P: N; High Risk: Project Reporting Requirements
G | Manufacturing Complexity |  | Project Risk Element P: O; High Risk: Public Impact
H | Transportation and Rigging Complexity |  | Project Risk Element P: P; High Risk: Project Cost

## Lists
Values |  | Chapters |  | Engineering Risk Element
1 | 1 - Low Risk | 1 | Requirements and Specifications | A | Technology
2 | 2 - Low to Medium Risk | 2 | Engineering Risk Assessment | B | Environmental Impact
3 | 3 - Medium Risk | 3 | Requirements and Specification Review | C | Vendor Issues
4 | 4 - Medium to High Risk | 4 | System Design | D | Resource Availability
5 | 5 - High Risk | 5 | Engineering Design Review | E | Quality Requirements
|  | 6 | Procurement and Implementation | F | Safety
| Assessment | 7 | Testing and Validation | G | Manufacturing Complexity
| Standard Risk | 8 | Release to Operations | H | Transportation and Rigging Complexity
| High Risk | 9 | Final Documentation
Project Risk Element
|  |  |  | I | Schedule
|  |  |  | J | Interfaces
|  |  |  | K | Experience / Capability
|  |  |  | L | Regulatory Requirements
|  |  |  | M | Project Funding
|  |  |  | N | Project Reporting Requirements
|  |  |  | O | Public Impact
|  |  |  | P | Project Cost