## Slide 1
AccU-BTL Installation
WBS 121.05.03
Denton Morris, L3 - BTL Installation
BTLBA Collimators FDR Review
October 4, 2022

## Slide 2: Outline
Introduction and Scope
Interfaces and Interferences
Installation Readiness Review Process
Installation Activities

## Slide 3: Introduction and Scope
  Denton Morris
  WBS 121.05.03
  BTL Installation L3
  Scope:
  Installation of all components downstream of the Linac low particulate vacuum
    beam valve, up to and including the Booster injection girder.
    Magnets, stands, beam pipe, instrumentation, cables, hoses, absorbers and collimators among other items.

## Slide 4: Interfaces
  BTL components, including the collimators, interface to Conventional Facilities, Building Utilities, Installation, Vacuum, Controls etc. (Contained in Interface Control Document)
  Interface issues identified:
  Machine side cable trays intersect collimator
  Due to collimators the aisle side cable trays encroach into “Keep Clear” volume
  LCW headers interfere with collimator
  LCW Make-up/Return lines interfere with collimator
  LVDT/drive system encroaches into “Keep Clear” volume

## Slide 5: Installation interferences

## Slide 6: Installation interferences
Absorber RAW make-up and F37
LCW tie in lines needed to be moved
further downstream.

## Slide 7: Installation
  Installation process begins with an Installation Readiness Review
  The IRR is part of the Validation and Verification process prior to accepting components for installation into the BTL.
  Gives the system L3s the opportunity to demonstrate that the components are as expected by the Project, meeting all fundamental and technical requirements, have passed QC, are properly documented using a traveler system, are configured in an agreed upon manner for installation and have all the necessary installation documentation.

## Slide 8: Validation and Verification Process
Configuration
QC
Travelers
FRS/TRS
PDR/FDR
Installation
Readiness
Review
Installation
Activities
Configuration
QC
Travelers
ORC
ARR
Documentation

## Slide 9: Installation Activities
  Following Hand-off of enclosure:
  Metrology stake-out
  Stand Installation w/ Metrology
  Collimator assembly on stand w/Metrology
  Cable pulls – motors, LVDTs, limit switches, thermocouples
  Terminate cables
  Vacuum connections
  Leak Check
  Motion control, LVDT, limit switch check-out
  Thermocouple test
  Close out QC
  Update Travelers
  Prepare for ORC

## Slide 10: Installation
The installation process will be similar to other systems we have installed:
MI-8 (Two pairs of collimators)
MI-30 (One primary and four secondary collimators)
RR-62 (One primary and two secondary collimators (Pictured to the right))