## Sheet1
PIP-II Review Response
| Review Title: | PIP-II 40 kW 650 MHz RF Distribution for PIP2IT PDR
| Review Date: | 2020-05-28
| Teamcenter ED#: | ED0012163
| System Manager (or Designee): | James Steimel
| Recommendation | Response | Action Item | Schedule to Complete Action | Responsible Party
1 | Antennas are problematic in a personal safety system for non-ionizing radiation. The distribution system needs to consider a parallel method for protecting against non-ionizing radiation, such as a low pressure interlock in the distribution system | We have changed the design of distribution system to include gas barriers. The sections that are isolated can be pressurized and monitored if gaps occur. | Change design | 2020-08-18 | Ding Sun
2 | For the FDR the circulator needs to have a detailed specification that includes test plans and vendor expectations. a. water temperature/variance b. water path circulator to load c. isolation over power band d. load design | a. We have added PIP2IT inlet water temperature 82 F – 84 F in our specification. b. We plan to use separate cooling water for circulator body and load. We plan to buy circulator and load separately. This option will enable us to insert a directional coupler between circulator and termination load for diagnosis. c. We have added “at any power level, under all the specified operation conditions” to the sentences specifying isolation, insertion loss and return loss. d. We plan to buy water cooled load (coaxial or waveguide) rated for 125 kW from commercial companies. e. We are drafting a test plan and will attach it to the specification for FDR. We will discuss the high power test plan with vendors. | Revise specification | 2020-08-18 | Ding Sun
3 | For the PIP-2IT test stand consider installing a coaxial dual directional coupler after the SSA combiner. | Yes, we have revised our design and added a 6-1/8” coaxial dual directional coupler after the SSA combiner to each distribution line. | Revise design | 2020-08-18 | Ding Sun
4 | Consider a bottoms up review of the labor plan after you have developed thorough installation and test plans for the system and components. | Yes, we will estimate labor and time needed for each step of installation and test plans for the system and components after those plans are completed. This estimate will be reviewed by engineers and technicians for their feedback and will be revised afterwards. | Review plans | 2020-12-31 | Team
5 | (comments) Directional coupler: Specify that it is pressure capable | We will add this request into specification sent to vendors. | Add specification | 2020-08-18 | Ding Sun
6 | (comment) Suggest having a first article test for the circulator before releasing production units | Yes, we will follow this suggestion and write this requirement in purchase contract (will consult with procurement department). | Perform high power test | 2021-06-30 | Ding Sun
7 | (comment) Acquisition Plan: Vendor on site or not? | We will clarify with vendors about their presence during high power test and this will be written in the contract. (some vendors may not want to be present in Fermilab’s high power test). | Communication with vendors | 2020-09-30 | Ding Sun
8 | (comments)The standing waves and the distribution scattering parameters need to be well understood (especially in the area between the 6 1/8” transition and the cavity coupler). | We will perform RF simulation in the area between Waveguide-Coax transition and cavity coupler. | Perform simulation | 2020-12-30 | Ding Sun
9
10
11
12
13