## Slide 1
PIP2IT 650 MHz RF Distribution Final Design Review Budget & Schedule
Jim Steimel
PIP2IT 650 MHz RF Distribution FDR
August 25, 2020

## Slide 2: Outline
Schedule interfaces and logic
Cost estimates: Labor & M&S
M&S Acquisition Plan
Quality Assurance
Safety by Design

## Slide 3: Schedule – Interface with Amplifiers
650 MHz RF Amplifiers will be provided by our DAE partners at RRCAT (Indore).
RRCAT personnel are constructing an amplifier in house for delivery to Fermilab in Oct 2020.
We don’t have a commitment date for the other five, but it will not likely be before March 2022.
We may need to test the first, HB650 cryomodule before we have the full set of amplifiers.
The current plan is to construct the RF distribution for one amplifier and test the first cryomodule one cavity at a time.
Will probably not trigger procurement of the rest of the transmission line until we get firmer commitment on final amplifier delivery.

## Slide 4: Schedule – Logic to Install
1st Amplifer Tested
RF Dist PDR
RF Dist FDR
Circulator Procurement & QA
RF Dist Procurement – 1 Cavity
Install RF Dist – 1 Cavity

## Slide 5: Schedule Dates
Preliminary Design Review Complete - June 8, 2020
Final Design Review Complete – Sept 2, 2020
Requisition Approved for Circulators – Nov 5, 2020
Requisition Approved for RF Dist 1 Cav – Dec 9, 2020
Testing of 1st 650MHz Amplifier Complete – May 28, 2021
Start QA Testing of Circulators – July 14, 2021
Start Installation of RF Distribution 1 Cav – Aug 16, 2021
Start Tests of HPRF System for 1 Cav – Sept 26, 2021
System ready for cryomodule tests – Nov 8, 2021
This schedule currently gives us >70 days of float to be ready to test the HB650 cryomodule.

## Slide 6: Cost Estimate - Labor
Basis of estimate for the PIP2IT 650MHz RF distribution can be found in PIP-II docdb #1848.
Labor estimates based on work required to perform design, procurement, testing, and installation of RF distribution for PIP2IT and STC.
Total Design effort budget – 390 hours
Circulator procurement and QA – 130 hours
RF Distribution procurement and QA – 65 hours
Installation for 1 cavity – 200 hours
Alignment effort – 200 hours
  This is not in the current basis of estimate.

## Slide 7: M&S Cost Estimate – Transmission Line
Basis of estimate for the PIP2IT 650MHz RF distribution can be found in PIP-II docdb #1848.
The cost estimates for the transmission lines and directional couplers (~$430k) are based on the cost of the components used in the STC 650MHz RF distribution upgrade that was commissioned in February.
  Current BOE assumes100’ of transmission line, 7 – elbows/bends, and one flex section or bellows per cavity.
  The final design includes ~11 – elbows/bends, 3 – flex sections, 2 – directional couplers, and 4 – waveguide to coax transitions.
  The design will also involve a few extra pieces of transmission line for 1st HB650 cryomodule test with 1 amp.

## Slide 8: M&S Cost Estimate – Circulator & Load
The basis of estimate for the circulator is from requests for information from multiple vendors.
The estimate is based on quantities required to supply the PIP-II accelerator and does not include NRE.
It is likely that smaller quantities for PIP-II will include NRE as an extra cost.
We would like to order circulators from two different vendors.
  Promote competition in quality
  Establish multiple sources for final PIP-II procurement
NRE costs for two vendors could increase total cost budgeted for circulators between $30k-$50k.
Cost of water-cooled loads is based on recent catalog prices.

## Slide 9: Acquisition Plan
Current proposal is to procure circulators from multiple vendors to reduce procurement risk going forward for PIP-II quantities.
Domestic vendors don’t have high power RF amplifiers for testing. High power testing likely to be performed at FNAL by FNAL engineers.
Contract needs to be structured to include retuning of circulators after initial, high power testing.
  Unless circulator vendor includes auto-tune mechanism.
RF transmission line components are off-the-shelf and will be ordered as needed.
  A formal acquisition plan is not needed.

## Slide 10: Quality Assurance Plan
Circulator QA will first include a low power test using a network analyzer to verify measurements performed on the vendor site.
Tests will be performed on the circulator to confirm the network analyzer measurements at high power. This will include measurements where the circulator output is terminated in a matched load and a variable length short.
Directional couplers will also be tested at low power using a network analyzer to verify specifications and calibrate.
The remainder of the RF distribution will only require visual inspection prior to installation.

## Slide 11: Safety by Design
One of the hazards associated with the RF distribution is exposure to RF fields.
  Exposure to open transmission lines mitigated though LOTO administrative controls.
  Exposure to RF leakage in closed systems mitigated through interlocks in RFPI system. Antenna detects high RF fields and trips amplifiers.
The circulator and some of the transmission line components are heavy and will be mounted overhead.
  Structure design will conform to FESHM 5100 standards and get reviewed by qualified mechanical safety engineer.
  Lifting plans will be developed in compliance with FESHM 10200. Critical lifts will be identified before installation.