## IoLaser
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
ProtoDUNE: UV laser, box, optical bench asembly, associated instruments | 2 | LANL | S. Gollapinni | 110000 | DUNE US project | Approved | CERN
ProtoDUNE: Periscope structure (inc. 2 mirrors, optical tubes, linear/rotary seals) | 2 | LANL | S. Gollapinni | 180000 | DUNE US project | Approved | CERN
ProtoDUNE: Custom flanges for ports (inc. electrical insulation) | 2 | LIP | J. Maneira | 7000 | Portugal | Approved | LANL
ProtoDUNE: Electronics board for instrumentation control and DAQ communication | 1 | LIP | J. Maneira | 5000 | Portugal | Approved | LANL
ProtoDUNE: Rack for laser PS, electronics board, control PC, network | 2 | LANL | S. Gollapinni | 50000 | DUNE US project | Approved | CERN
DUNE FD1: UV laser, box, optical bench assembly, associated instruments | 9 | LANL | S. Gollapinni | 500000 | LANL LDRD, DUNE US project | Aspirational | SURF
DUNE FD1: Periscope structure (inc. 2 mirrors, optical tubes) | 12 | LANL | S. Gollapinni | 1200000 | LANL LDRD, DUNE US project | Aspirational | SURF
DUNE FD1: Custom flanges for ports (inc. electrical insulation) | 12 | LIP | J. Maneira | 42000 | Portugal | Aspirational | LANL
DUNE FD1: Electronics board for instrumentation control and DAQ communication | 5 | LIP | J. Maneira | 25000 | Portugal | Aspirational | LANL
DUNE FD1: Rack for laser PS, electronics board, control PC, network | 9 | LANL | S. Gollapinni | 250000 | LANL LDRD, DUNE US project | Aspirational | SURF
2017000
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (2 FTE.yr), engineer (0.7 FTE.yr), technician (0.5 FTE.yr) |  | LIP | J. Maneira |  | Portugal | Approved
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (2 FTE.yr), engineer (0.5 FTE.yr), technician (1 FTE.yr) |  | LIP | J. Maneira |  | Portugal | Aspirational
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (3 FTE.yr), postdocs (4 FTE.yr), grad student (3 FTE.yr), engineer (2.1 FTE.yr), technician (1 FTE.yr) |  | LANL | S. Gollapinni
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (3 FTE.yr), postdocs (4 FTE.yr), grad student (3 FTE.yr), engineer (2.1 FTE.yr), technician (1 FTE.yr) |  | LANL | S. Gollapinni |  | LDRD, Base grant, US DOE project
Development of instrumentation interface and scan automation software |  | LIP | J. Maneira |  | Portugal | Approved
Development of DAQ-side data reduction software |  | York ? | C. David? |  |  | Aspirational

## IoLaser (Alternative)
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding
ProtoDUNE: UV laser, box, optical bench asembly, associated instruments | 1 |  |  | 55000 |  | Aspirational
ProtoDUNE: Periscope structure (inc. 2 mirrors, optical tubes, linear/rotary seals) | 1 |  |  | 90000 |  | Aspirational
ProtoDUNE: Custom flanges for ports (inc. electrical insulation) | 1 | LIP | J. Maneira | 3500 | Portugal | Approved
ProtoDUNE: Rack for laser PS, electronics board, control PC, network | 1 |  |  | 25000 |  | Aspirational
DUNE FD1: UV laser, box, optical bench assembly, associated instruments | 4 |  |  |  |  | Aspirational
DUNE FD1: Periscope structure (inc. 2 mirrors, optical tubes) | 4 |  |  | 400000 |  | Aspirational
DUNE FD1: Custom flanges for ports (inc. electrical insulation) | 4 | LIP | J. Maneira | 14000 | Portugal | Aspirational
DUNE FD1: Electronics board for instrumentation control and DAQ communication | 1 | LIP | J. Maneira | 5000 | Portugal | Aspirational
DUNE FD1: Rack for laser PS, electronics board, control PC, network | 4 |  |  | 100000 |  | Aspirational
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (0.5 FTE.yr), engineer (0.3 FTE.yr), technician (0.3 FTE.yr) |  | LIP | J. Maneira |  | Portugal | Approved
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (1 FTE.yr), engineer (0.5 FTE.yr), technician (0.5 FTE.yr) |  | LIP | J. Maneira |  | Portugal | Aspirational

## PELaser
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to: | Comments
ProtoDUNE: Adaptation of laser box for fiber injection | 1 | Hawaii | J. Maricic | 2000 | DUNE U.S. Project | Proposal under review | CERN
ProtoDUNE: Adaptation of laser box for fiber injection | 1 | Iowa | J. Nachtman |  |  | Aspirational | CERN
ProtoDUNE: Warm+cold fibers (inc. patch panel, multiplexer) | 6 | Hawaii | J. Maricic | 6000 | DUNE U.S. Project | Proposal under review | CERN
ProtoDUNE: Targets on CPA + holders on APA | 2 | Hawaii | J. Maricic | 2000 | DUNE U.S. Project | Proposal under review | CERN
DUNE FD1: Adaptation of laser box for fiber injection | 9 | Hawaii | J. Maricic | 18000 | DUNE U.S. Project | Aspirational | SURF
DUNE FD1: Warm+cold fibers (inc. patch panel, multiplexers) | 72 | Hawaii | J. Maricic | 30000 | DUNE U.S. Project | Aspirational | SURF
DUNE FD1: Targets on CPA + holders on APA | 24 | Hawaii | J. Maricic | 8000 | DUNE U.S. Project | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE : Person-power for hardware design, production, commissioning: faculty (1/3 FTE.yr), postdocs (0.3 FTE.yr), grad students (0.5 FTE.yr), engineer (1/12 FTE.yr), technician (0.3 FTE.yr) |  | Hawaii | J. Maricic |  | DOE IF Base | Approved
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (1/3 FTE.yr), postdocs (0.5 FTE.yr), grad students (0.5 FTE.yr), engineer (1/12 FTE.yr), technician (0.7 FTE.yr) |  | Hawaii | J. Maricic |  | DOE IF Base | Approved
Tests of fiber transmission and cathode efficiency |  | Hawaii | J. Maricic |  | DOE IF Base | Approved
Development of analysis software |  | Hawaii | J. Maricic |  | DOE IF Base | Aspirational

## LBLS
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
ProtoDUNE: Pads with 10 PIN diodes and cables | 2 | Hawaii | J. Maricic | 2000 | DUNE U.S. Project | approved | CERN
ProtoDUNE: LBLS Pad DAQ interface | 2 | Hawaii | J. Maricic | 3000 | DUNE U.S. Project | approved | CERN
ProtoDUNE: Mirror LBLS prototypes | 4 | LIP | J. Maneira | 3000 | Portugal | approved | CERN
DUNE FD1: Pads with 10 PIN diodes and cables | 32 | Hawaii | J. Maricic | 20000 | DUNE U.S. Project | Aspirational | SURF
DUNE FD1: LBLS Pad DAQ interface | 32 | Hawaii | J. Maricic | 15000 | DUNE U.S. Project | Aspirational | SURF
DUNE FD1: LBLS mirror pads | 32 | LIP | J. Maneira | 24000 | Portugal | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE : Person-power for PIN diode pads hardware design, production, commissioning: faculty (1/3 FTE.yr), postdocs (0.3 FTE.yr), grad students (0.5 FTE.yr), engineer (1/12 FTE.yr), technician (0.3 FTE.yr) |  | Hawaii | J. Maricic |  | DOE IF Base | Approved
DUNE FD1: Person-power for PIN diode pads hardware design, production, commissioning: faculty (1/3 FTE.yr), postdocs (0.5 FTE.yr), grad students (0.5 FTE.yr), engineer (1/12 FTE.yr), technician (0.3 FTE.yr) |  | Hawaii | J. Maricic |  | DOE IF Base | Aspirational
ProtoDUNE : Person-power for mirror pads hardware design, production, commissioning: faculty (1/12 FTE.yr), engineer (1/12 FTE.yr), technician (1/6 FTE.yr) |  | LIP | J. Maneira |  | Portugal | Approved
DUNE FD1 : Person-power for mirror pads hardware design, production, commissioning: faculty (0.3 FTE.yr), engineer (1/12 FTE.yr), technician (0.3 FTE.yr) |  | LIP | J. Maneira |  | Portugal | Aspirational

## PNS
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
ProtoDUNE-SP1: DD generator | 1 | LANL | S. Gollapinni | 0 | LANL | Approved | CERN
ProtoDUNE-SP1: Moderator and Shielding | 1 | CERN | F. Pietropaolo | 0 | CERN | Approved | CERN
ProtoDUNE-SP-2: DD generator | 1 | UC Davis | R. Svoboda | 175000 | DUNE U.S. Project | Aspirational | CERN
ProtoDUNE-SP-2: Moderator+shielding+other materials | 1 | UC Davis | R. Svoboda | 75000 | DUNE U.S. Project | Aspirational | CERN
ProtoDUNE-SP-2: Contribution to moderator+shielding | 1 | Iowa | J. Nachtman |  |  | Aspirational
ProtoDUNE-SP-2: Neutron monitoring detector | 1 | LANL | S. Gollapinni | 5000 | LANL | Aspirational | CERN
DUNE FD1: DD generators (1 new + refurbishment of PD-SP2 one) | 2 | UC Davis | R. Svoboda | 250000 | DUNE U.S. Project | Aspirational | SURF
DUNE FD1: Moderator+shielding+other materials | 1 | UC Davis | R. Svoboda | 75000 | DUNE U.S. Project | Aspirational | SURF
DUNE FD1: Contribution to Moderator+shielding | 1 | Iowa | J. Nachtman |  |  | Aspirational
DUNE FD1: Neutron monitoring detector | 1 | LANL | S. Gollapinni | 5000 | LANL | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE 1 and 2: Person-power for hardware design, production, commissioning: faculty (1 FTE.yr), postdocs (1 FTE.yr), grad students (1 FTE.yr), engineer (0.5 FTE.yr), technician (0.4 FTE.yr) |  | UCDavis | R. Svoboda |  | DOE IF Base, DUNE US Project | Aspirational
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (4 FTE.yr), postdocs (2 FTE.yr), grad students (2 FTE.yr), engineer (1 FTE.yr), technician (0.4 FTE.yr) |  | UCDavis | R. Svoboda |  | DOE IF Base | Aspirational
ProtoDUNE-SP-II: Characterization of neutron energy spectrum and yield with SDSMT He-3 hodoscope |  | SDSMT | J. Reichenbacher |  | DOE IF Base | Aspirational
DUNE FD1: Characterization of neutron energy spectrum and yield with SDSMT He-3 hodoscope |  | SDSMT | J. Reichenbacher |  | DOE IF Base | Aspirational
Data-taking and analysis of ARTIE experiment |  | UCDavis | R. Svoboda |  | DOE IF Base | Approved
Data-taking and analysis of ARTIE experiment |  | LIP | S. Andringa |  | Portugal | Approved
Simulation of neutron propagation in ProtoDUNE and DUNE FD |  | Pittsburgh | D. Naples |  | DOE IF Base | Approved
Data-analysis of ProtoDUNE-SP-I and II |  | UCDavis | R. Svoboda |  | DOE IF Base | Approved
Data-analysis of ProtoDUNE-SP-I and II |  | Pittsburgh | D. Naples |  | DOE IF Base | Approved
Data-analysis of ProtoDUNE-SP-I and II |  | LIP | S. Andringa |  | DOE IF Base | Approved

## RSDS
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to: | Comment
ProtoDUNE: Deployment system prototype, cryo-glove box with gas purge system and dummy source | 1 | SDSMT | J. Reichenbacher | 16500 | DUNE US Project, DOE IF Base, DOE EPSCoR, Start-up | Aspirational | SDSMT
ProtoDUNE: ppm gas analyzer system for cryo-glove box | 1 | SDSMT | J. Reichenbacher | 13000 | DUNE US Project | Aspirational | SDSMT
R&D towards FD1: Source prototype for tests at SDSMT | 1 | SDSMT | J. Reichenbacher | 6000 | DUNE US Project | Aspirational | SDSMT
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (0.25 FTE.yr), postdoc (0.4 FTE.yr), grad. student (0.5 FTE.yr), technician (0.5 FTE.yr) |  | SDSMT | J. Reichenbacher |  | DOE IF base or DUNE US Project | Aspirational
Simulation of neutron and gamma propagation and low energy responses |  | SDSMT | J. Reichenbacher |  | DOE IF base | Approved
Measurement of neutron and gamma yield of source prototype |  | SDSMT | J. Reichenbacher |  | DOE IF base | Approved

## Temp. Sens.
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
ProtoDUNE-SP: Dynamic thermometer upgrade | 1 | U. Hawaii | J. Maricic | 6000 | DUNE US project | Aspirational | CERN
ProtoDUNE-SP: Temperature sensors for APAs | 16 | IFIC | A. Cervera | 1500 | Spain | Approved | CERN
ProtoDUNE-SP: Temperature sensors for LAr inlets and pump | 5 | IFIC | A. Cervera | 800 | Spain | Approved | CERN
ProtoDUNE-SP: Readout for temperature sensors (upgrade) |  | CERN | X. Pons |  |  |  | CERN
DUNE FD1: Dynamic+Static movable system | 1 | Hawaii | J. Maricic | 25000 | DUNE US project | Aspirational | SURF
DUNE FD1: Temperature sensors for APAs | 600 | IFIC | A. Cervera | 60000 | Spain | Submitted | SURF
DUNE FD1: Other precision temperature sensors (GPs, LAr inlets and pumps) | 40 | IFIC | A. Cervera | 6000 | Spain | Submitted | SURF
DUNE FD1: Other standard temperature sensors (cryostat floor and walls) | 41 | IFIC | A. Cervera | 1000 | Spain | Submitted | SURF
DUNE FD1: Readout for temperature sensors |  | IFIC | A. Cervera | 10000 | Spain | Aspirational | SURF
DUNE FD1: Readout for temperature sensors |  | U. Hawaii | J. Maricic | 2000 | DUNE US project | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE-SP: CFD simulations |  | SDSU | S. Gent |  | DUNE US project | Approved
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (0.3 FTE.yr), grad. student (0.3 FTE.yr), engineer (0.1 FTE.yr), technician (0.05 FTE.yr) |  | IFIC | A. Cervera |  | Spain | Submitted
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (? FTE.yr), postdoc(? FTE.yr), grad. student (? FTE.yr), engineer (? FTE.yr), technician (? FTE.yr) |  | U. Hawaii | J. Maricic |  | DUNE US project | Approved
DUNE FD1: CFD simulations |  | SDSU | S. Gent |  | DUNE US project | Aspirational
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (1 FTE.yr), grad. student (0.3 FTE.yr), engineer (0.3 FTE.yr), technician (0.3 FTE.yr) |  | IFIC | A. Cervera |  | Spain | To be submitted
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (2 FTE.yr), postdoc(3 FTE.yr), grad. student (3 FTE.yr), engineer (0.2 FTE.yr), technician (1 FTE.yr) |  | U. Hawaii | J. Maricic |  | DUNE US project | Aspirational

## Purity Monitors
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to: | Comments
ProtoDUNE-SP: Long purity monitor (structure, electronics, DAQ, fibers, photocathodes, machine shop) | 1 | UCI | J. Bian | 32000 | DUNE US project | Aspirational | CERN
ProtoDUNE-SP: Long purity monitor (HV upgrade) | 1 | UCI | J. Bian | 25000 | DUNE US project | Aspirational | CERN
ProtoDUNE-SP: inline monitor | 1 | UCI | J. Bian | 22000 | DUNE US project | Aspirational | CERN | Very rough estimate of cost ($19k for hte monitor and $3k for support system), needs refining
DUNE FD1: Purity monitor unit | 8 | UCI | J. Bian | 152000 | DUNE US project | Aspirational | SURF
DUNE FD1: Flanges (2 cryostat, 2 inline) | 4 | U. Houston | A. Renshaw | 21900 | DUNE US project | Aspirational | SURF | cryostat flanges each at $6,600 and inline flanges each at $4,350
DUNE FD1: Mounting structure | 2 | U. Houston | A. Renshaw | 11000 | DUNE US project | Aspirational | SURF
DUNE FD1: Purity Monitor Other elements (3 Xe source, 2 HV, 4 Digitizer box, 2 PC) |  | UCI | J. Bian | 45500 | DUNE US project | Aspirational | SURF
DUNE FD1: Housing for inline purity monitors | 1 | ? | ? | 33500 | DUNE US project | Aspirational | SURF | This estimate comes from the estimate calculated for SBND inline vessel
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (0.2 FTE.yr), postdocs (0.3 FTE.yr), grad students (0.3 FTE.yr), technician (0.2 FTE.yr) |  | UCI | J. Bian |  | DOE IF Base | Approved
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (0.1 FTE.yr), postdocs (0.2 FTE.yr), grad students (0.2 FTE.yr), engineer (0.05 FTE.yr), technician (0.1 FTE.yr) |  | U. Houston | A. Renshaw |  | DOE IF Base | Aspirational
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (2 FTE.yr), postdocs (2 FTE.yr), grad students (2 FTE.yr), technician (0.5 FTE.yr) |  | UCI | J. Bian |  | DOE IF Base; DUNE US project | Aspirational
DUNE FD1: Person-power for hardware design, production, commissioning: faculty (1 FTE.yr), postdocs (1 FTE.yr), grad students (1 FTE.yr), engineer (0.05 FTE.yr), technician (0.25 FTE.yr) |  | U. Houston | A. Renshaw |  | DOE IF Base; DUNE US project | Aspirational
ProtoDUNE-SP (I & II): Purity Monitor design Validation using ProtoDUNE data analysis |  | UCI | J. Bian |  | DOE IF Base | Approved
DUNE FD1: Simulation studies of fluid dynamics within the cryostat and its effect on argon purity |  | SDSU | S. Gent |  | DUNE U.S. Project | Approved
DUNE FD1: Simulation studies of E-field distributions at the purity monitor FT location(s) |  | BNL | B. Yu |  | DOE IF Base | Approved |  | Needs confirmation from BNL

## Level meters
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
ProtoDUNE-SP: Capacitive level meters (4 m; full system) | 1 |  |  | 1300 | DUNE US project | Aspirational | CERN
DUNE FD1: Capacitive level meter | 4 |  |  | 1200 | DUNE US project | Aspirational | SURF
DUNE FD1: Readout for Capacitive level meter | 1 |  |  | 500 | DUNE US project | Aspirational | SURF
DUNE FD1: Flanges | 4 |  |  | 2000 | DUNE US project | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE-SP: analysis |  |  |  |  | DOE IF Base | Aspirational
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (0.02 FTE.yr), postdoc(0.04 FTE.yr), engineer (0.02 FTE.yr), technician (0.04 FTE.yr) |  |  |  |  | DOE IF Base | Aspirational
ProtoDUNE: Person-power for hardware design, production, commissioning: faculty (0.02 FTE.yr), postdoc(0.04 FTE.yr), engineer (0.02 FTE.yr), technician (0.04 FTE.yr) |  |  |  |  | DOE IF Base | Aspirational

## cameras
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to: | Comments
ProtoDUNE-SP-2: Cameras in Laser periscope (full system) | 2 | KSU | G. Horton-Smith | 10000 | DUNE US project | Approved | CERN | Currently expected to come out of hte LANL project funding as this is part of the Laser periscope M&S; collaborative effort between LANL and KSU
DUNE FD1: Cold cameras (full system) | 12 | ? | ? | 30300 | DUNE US project | Aspirational | SURF
DUNE FD1: Camera in Laser periscope (full system) | 12 | KSU | G. Horton-Smith | 21000 | DUNE US project | Aspirational | SURF | From CISC Warm Camera estimate, include only camera cost, camera electronics, temp. sensor, 10 m of warm and cold cables.
DUNE FD1: Computers | 2 | KSU | G. Horton-Smith | 4000 | DUNE US project | Aspirational | SURF
DUNE FD1: Light system | 15 | Drexel | C. Lane | 3900 | DUNE US project | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
ProtoDUNE-II: Camearas on Laser Periscope: Person-power for hardware design, production, commissioning: faculty (0.2 FTE.yr), grad students (0.3 FTE.yr), engineer (0.05 FTE.yr), technician (0.02 FTE.yr) |  | KSU | G. Horton-Smith |  | DOE IF Base | Approved
DUNE FD1: Camearas on Laser Periscope: Person-power for hardware design, production, commissioning: faculty (0.5 FTE.yr), postdocs (1 FTE.yr), grad students (1 FTE.yr), engineer (0.06 FTE.yr), technician (0.05 FTE.yr) |  | KSU | G. Horton-Smith |  | DOE IF Base | Aspirational
DUNE FD1: Cold Cameras: Person-power for hardware design, production, commissioning: faculty (0.5 FTE.yr), postdocs (1 FTE.yr), grad students (1 FTE.yr), engineer (0.06 FTE.yr), technician (0.05 FTE.yr) |  | ? | ? |  | DOE IF Base | Aspirational
DUNE FD1: light system: Person-power for hardware design, production, commissioning: faculty (0.5 FTE.yr), grad students (0.25 FTE.yr), Technicians (0.01 FTE.yr) |  | Drexel | C. Lane |  | DOE IF Base | Aspirational
ProtoDUNE-SP: design validation (cameras in laser periscope) |  | KSU | G. Horton-Smith |  | DOE IF Base | Aspirational

## gas analyzers
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
DUNE FD1: N2 Gas Analyzer | 1 | FNAL | A. Hahn | 30000 | DUNE US project | Aspirational | SURF
DUNE FD1: O2 analyzers (several types) | 5 | FNAL | A. Hahn | 67000 | DUNE US project | Aspirational | SURF
DUNE FD1: H2O analyzers (several types) | 3 | FNAL | A. Hahn | 40760 | DUNE US project | Aspirational | SURF
DUNE FD1: Routing panel | 1 | FNAL | A. Hahn | 30000 | DUNE US project | Aspirational | SURF
DUNE FD1: Piping | 1 | FNAL | A. Hahn | 40000 | DUNE US project | Aspirational | SURF
DUNE FD1: Vapor Compressor Pumps on Cryostat | 2 | FNAL | A. Hahn | 13600 | DUNE US project | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
DUNE FD1: Person-power for hardware design, production, commissioning: engineer (0.18 FTE.yr), technician (0.27 FTE.yr) |  | FNAL | A. Hahn |  | DUNE US project | Aspirational
ProtoDUNE: Person-power for installation and commissioning: faculty (? FTE.yr), postdoc(? FTE.yr), grad. student (? FTE.yr) |  | SDSMT | J. Reichenbacher |  | DOE IF base | Aspirational

## Pressure sensors
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
DUNE FD1: Sensors, cables and readout | 6 |  |  | 3600 | DUNE US project | Aspirational | SURF
DUNE FD1: flanges | 2 |  |  | 1200 | DUNE US project | Aspirational | SURF
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
DUNE FD1: Person-power for hardware design, production, commissioning: engineer (0.02 FTE.yr) |  |  |  |  | DOE IF Base | Aspirational

## Cryogenics test facility
Hardware
Deliverable | Quantity | Institution | Responsible Person | CORE Cost Estimate | Funding Source | Status of funding | To be delivered to:
Liquid argon during 5 years (4 fills of ICEBERG) | 10000 litres | FNAL | A. Hahn | 12000 | DUNE US project | Aspirational | FNAL
Minor Fixturing material |  | FNAL | A. Hahn | 1400 | DUNE US project | Aspirational | FNAL
Non-Hardware
Deliverable |  | Institution | Responsible Person |  | Funding Source | Status of funding
DUNE FD1: Person-power for operation and maintenance: faculty (0.2 FTE.yr), postdoc(0.36 FTE.yr), grad. student (0.36 FTE.yr), engineer (0.04 FTE.yr), technician (0.1 FTE.yr) |  | FNAL | A. Hahn |  | DUNE US project | Aspirational