## Slide 1
Cristian Boffo, Stoyan Stoynev
Coordination meeting
28 May 2020
Update on SSR solenoid design

## Slide 2: Preparations for review
TRS are finalized. [Stoyan, Cristian]
  Approved
Solenoids FRS will be incorporated in CM FRS [Bruce S., A. Martinez]
  Ongoing
Write Charge, review agenda, reviewer list [Donato]
  Draft
Approve charge, agenda, reviewers: ongoing [Cristian, Stoyan, Genfa]
Update Indico page to reflect the agenda [Donato]
  Draft
Generate TC# for the review [Donato]
  Done. TC# ED0011770
Issue a zoom link and add it to Indico page: done. [Stoyan]
  Done. See Indico site.
Invite reviewers. [Donato]
  Cristian already checked their availability. Official email will be sent after we confirm with our partners readiness and review date upon to delivery of “promised document”
9. Send invitation to presenters and attendees [Donato]
  TBD
10. Interface document [Donato]
  Updating Interface document.
11. QC plan for solenoids and e-travelers [Donato]
  Acceptance criteria [Stoyan, Cristian] - draft
  Testing plan/Travelers [Stoyan, Kumud] – two drafts
12. Facilitate the integration of the 3D model in the string assembly/CM [Donato]
  Done.
At BARC [Stoyan to coordinate/facilitate the communication]
  Finalize design
i. Done (except interfaces)
  Design report (mechanical and electromagnetic design)
i. Done
  Fabrication plan and intermediate controls
i. In preparation
ii. 2D drawings after BARC re-opens
  Final tests before shipping (to be captured in Acceptance criteria and testing plan)
  Shipping plan - in preparation
https://indico.fnal.gov/event/23501/
Indico page available (and populated:)
Tentatively – July 1st
Preparation steps (some completed):

## Slide 3: Projected delays
BARC are not fully back to work
Drawings are show-stoppers for the review