## Installation Dec #1 Labor
| Start | # |  |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
| Month | Months | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56
Logistics Facility | -12 | 48 | 2024 1: Logistics Facility
Hiring core tecs + leaders |  |  | -3: 4; -2: 7; -1: 4; 2024 1: 2; 2024 2: 2; 2024 11: 2; 2024 12: 2; 2025 24: 2; 2026 25: 3
Training core tecs + leaders |  |  | -2: 4; -1: 7; 2024 1: 4; 2024 2: 2; 2024 3: 2; 2024 4: 19; 2024 12: 2; 2025 13: 2; 2025 14: 4; 2026 25: 2; 2026 26: 3; 2026 27: 5
BSI Cavern N minimal | 1 | 3 | 2024 1: BSI N Cavern
BSI CUC | 1 | 8 | 2024 1: CBSI CUC
CUC Infrastructure and DAQ | 1 | 8 | 2024 1: CUC Infrastructure
Cable trays N Cavern/CUC | 4 | 4 | 2024 4: Cable Trays; 2024 8: 4
Racks | 1 | 7 | 2024 1: Racks CUC; 2024 3: 2; 2024 4: CUC Contr. Room; 2024 8: 4
Cavern Outfitting Labor | 1 | 15 | 2024 1: 131.04.01.03 FS Cavern Outfitting Labor
Install Warm Dec #1 | 3 | 12 | 2024 4: Warm Structure #1; 2025 16: 3.8333
Startup-Crane Install, floor beams | 1 | 3 | 2024 1: Start-up; 2024 4: 4
install stairs and access | 1 | 3 | 2024 1: Stairs-Access; 2024 4: 3
install handrails+ vertical access | 8 | 4 | 2024 7: Cryostat access; 2024 11: 2
install mezzanines | 12 | 3 | 2024 11: Mezzanines; 2025 14: 6
Install N-Cavern Bridge-Walkway | 14 | 2 | 2025 14: N Bridge; 2025 16: 7
Install Cold Dec #1 | 16 | 12 | 2025 16: Install Cryostat Cold #1
Install S-Cavern Bridge-Walkway | 24 | 1 | bar: 2025 24
Far Detector Installation Labor | 13 | 40 | 2025 13: 131.04.01.04 Far Detector Installation Labor
Top of the Cryostat Infrastructure #1 | 12 | 12 | 2024 12: Top Cryostat Infrastructure Detector #1
Install Mezzanine AC, Cable trays,etc | 14 | 2 | 2025 14: Mezz AC; 2025 16: 6
Install Barracks + AC,HVAC,Fire,Vent | 16 | 4 | 2025 16: Barracks-AC,HVAC; 2025 20: 4
Install Crossing Tubes | 16 | 4 | 2025 16: Crossing Tubes; 2025 20: 5
Install cryo venting and N2 | 12 | 6 | 2025 14: Install Cryo Venting; 2025 18: 2.1333
Detector #1 Cleanroom Setup | 14 | 14 | 2025 14: Detector #1 Cleanroom Installation Setup
N Bridge Crane System | 15 | 2 | 2025 14: CR Crane; 2025 16: 4
Cold Boxes/N System | 9 | 8 | 2024 8: Cold Box Prep; 2025 14: 6; 2025 20: Install Boxes; 2025 23: 7
Cold Box N System | 20 | 3 | 2025 20: CB N System; 2025 23: 2
DSS Feed-Thru Tubes | 16 | 4 | 2025 16: DSS Feed Thrus; 2025 20: 5
DSS Beam installation | 23 | 3 | 2025 23: DSS Beams; 2026 26: 6
CE Feed-thru/Cross/Racks | 19 | 6 | 2025 20: CE Feed/Racks; 2026 26: 5
Work shop/storage Area | 14 | 2 | 2024 2: Shop; 2024 4: 4
Cleanroom/SAS Steel Structure | 16 | 4 | 2025 16: Cleanroom Steel; 2025 20: 5
Cleanroom Infrastructure | 20 | 4 | 2025 20: Cleanroom Infra; 2025 24: 4.5
Crostat Internal Plumbing | 24 | 4 | 2025 24: Plumb; 2026 28: 5.25
Cryostat Floor | 25 | 2 | 2026 25: Floor; 2026 27: 6
Assembly SP Dec #1 | 28 | 10 | 2026 28: Assembly SP Decector #1 10 months
Cleanroom Prep | 26 | 2 | 2026 26: Prep; 2026 28: 8
Pre and install West End Wall | 28 | 3 | 2026 28: End
Start-up APA-CPA-FC 1-2 | 29 | 1.5 | 2026 29: 1; 2026 30: 2
Install APA-CPA-FC 3-24 | 30 | 5.5 | 2026 30: Install APA/HV 3-24
Install APA-/HV 25 | 36 | 1 | 2026 36: 25
Pre and install East End Wall | 36 | 2 | 2026 36: Prep; 2027 37: End
TCO Closing | 38 | 2 | 2027 38: TCO
Final Assembly Completion | 39 | 3 | 2027 39: Final
Purge Dec #1 | 42 | 2 | 2027 42: Cool/Purge
Fill Dec #1 | 44 | 10 | 2027 44: Fill 10 months
Labor Estimates
[6 empty] | A | [11 empty] | SP1 | [14 empty] | SP
|  |  | 2024 1: U; 2025 13: set; 2026 28: # |  | Labor
|  |  | 2024 1: P; 2025 13: up; 2026 28: 1 | FTE | Estimates
[62 empty] | Months | Hours
131.04.01.03-Far Site Cavern Outfitting Labor
CORE Technician |  |  | -1: 4; 2024 1: 13; 2024 2: 13; 2024 3: 13; 2024 4: 13; 2024 5: 13; 2024 6: 13; 2024 7: 13; 2024 8: 5; 2024 9: 7; 2024 10: 7; 2024 11: 9; 2024 12: 9; 2025 13: 9; 2025 14: 10; 2025 15: 10; 2025 16: 3; 2025 17: 3; 2025 18: 3; 2025 19: 3; 2025 20: 3; 2025 21: 3; 2025 22: 3; 2025 23: 12; 2025 24: 12; 2026 25: 9; 2026 26: 9; 2026 27: 9
Cryo welders |  |  | -2: 1; -1: 1; 2024 1: 1; 2024 2: 1; 2024 3: 2; 2024 4: 3; 2024 5: 4; 2024 6: 3; 2024 7: 3; 2024 8: 2; 2024 9: 3; 2024 10: 3; 2024 11: 2; 2024 12: 2; 2025 13: 2; 2025 14: 0; 2025 15: 0; 2025 16: 0; 2025 17: 0; 2025 18: 0; 2025 19: 0; 2025 20: 0; 2025 21: 0; 2025 22: 0; 2025 23: 2; 2025 24: 2; 2026 25: 2; 2026 26: 2; 2026 27: 2
131.04.01.04-Far Detector Installation Labor
CORE Technician | [12 empty] | 6 | 6 | 6 | 6 | 8 | 7 | 10 | 10 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 13.5 | 8 | 8 | 9 | 14.3438 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 12 | 3 | 3 | 3 | 3
Cryo welders |  |  | 2025 13: 1; 2025 14: 3; 2025 15: 3; 2025 16: 3; 2025 17: 3; 2025 18: 3; 2025 19: 3; 2025 20: 3; 2025 21: 3; 2025 22: 3; 2025 23: 1; 2025 24: 1; 2026 25: 1; 2026 26: 0; 2026 27: 0; 2026 28: 2; 2026 29: 2; 2026 30: 2; 2026 31: 2; 2026 32: 2; 2026 33: 2; 2026 34: 2; 2026 35: 2; 2026 36: 2; 2027 37: 2; 2027 38: 2; 2027 39: 2; 2027 40: 2; 2027 41: 2; 2027 42: 2; 2027 43: 2
Technical Labor (Activity driven)
Construction Managers |  |  | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 202 | 32320
Lead Core Tech |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  | 165 | 26400
Core Technician |  |  |  |  | 4 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 13 | 13 | 15 | 17 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 25.5 | 20 | 17 | 18 | 23.3438 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 25.375 | 12 | 6 | 6 | 6 | 6 | [13 empty] | 778.9688 | 124635
Cryo Welders |  |  |  | 1 | 1 | 1 | 1 | 2 | 3 | 4 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [13 empty] | 106 | 16960
Cabling technicians | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | [13 empty] | 112 | 17920
Support Labor (LOE) |  |  | 2028 54: Total Technical | 1363.9688 | 218235
Safety Coordinator |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 194 | 31040
Lead rigging/Crane operator(1/shift) |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  | 168 | 26880
Rigging/Crane Operator |  |  |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [13 empty] | 570 | 91200
Logistics Support |  |  | 40 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [20 empty] | 192 | 30720
Transport Crew Lead |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  | 162 | 25920
Transport Crew |  |  |  |  | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | [13 empty] | 702 | 112320
Survey |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 108 | 17280
Lead Electrician | [61 empty] | 54 | 8640 | bar: -1 to 2028 53
Electrican |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [13 empty] | 132 | 21120
Lead Mechanic | [61 empty] | 54 | 8640 | bar: -1 to 2028 53
Network | [61 empty] | 44 | 7040 | bar: -1 to 2027 43
Mechanic Tech |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [13 empty] | 88 | 14080
Total Estimated UG I&I Labor |  |  |  | 12 | 62 | 71 | 71 | 74 | 75 | 76 | 75 | 75 | 72 | 75 | 76 | 77 | 79 | 79 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 88.5 | 83 | 80 | 80 | 85.3438 | 87.375 | 87.375 | 87.375 | 87.375 | 87.375 | 87.375 | 69.375 | 69.375 | 69.375 | 65.375 | 65.375 | 52 | 46 | 45 | 45 | 44 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | Total LOE |  |  | 2468 | 394880
Consortia |  |  | 2028 54: Grand Total | 3831.9688 | 613115
APA Consortia |  |  | 2026 26: 0; 2026 27: 5.125; 2026 28: 15; 2026 29: 15; 2026 30: 15; 2026 31: 15; 2026 32: 15; 2026 33: 15; 2026 34: 15; 2026 35: 15; 2026 36: 15; 2027 37: 15; 2027 38: 15; 2027 39: 15; 2027 40: 15; 2027 41: 15 | 215.125 | 34420
CE Consortia |  |  | 2026 26: 0; 2026 27: 16; 2026 28: 30; 2026 29: 30; 2026 30: 30; 2026 31: 30; 2026 32: 30; 2026 33: 30; 2026 34: 30; 2026 35: 30; 2026 36: 30; 2027 37: 30; 2027 38: 30; 2027 39: 30; 2027 40: 30; 2027 41: 30 | 436 | 69760
PD Consortia |  |  | 2026 26: 0; 2026 27: 6; 2026 28: 12; 2026 29: 12; 2026 30: 12; 2026 31: 12; 2026 32: 12; 2026 33: 12; 2026 34: 12; 2026 35: 12; 2026 36: 12; 2027 37: 12; 2027 38: 12; 2027 39: 12; 2027 40: 12; 2027 41: 12 | 174 | 27840
HV Consortia |  |  | 2026 26: 0; 2026 27: 7; 2026 28: 14; 2026 29: 14; 2026 30: 14; 2026 31: 14; 2026 32: 14; 2026 33: 14; 2026 34: 14; 2026 35: 14; 2026 36: 14; 2027 37: 14; 2027 38: 14; 2027 39: 14; 2027 40: 14; 2027 41: 14 | 203 | 32480
DAQ/Slow Control Consortia | [18 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  | 160 | 25600
Total Consortia FTE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 38.125 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Total Consortia |  |  | 1188.125 | 190100
Total |  |  |  | 12 | 62 | 71 | 71 | 74 | 75 | 76 | 75 | 75 | 72 | 75 | 76 | 77 | 79 | 79 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 92.5 | 87 | 84 | 84 | 123.4688 | 162.375 | 162.375 | 162.375 | 162.375 | 162.375 | 162.375 | 144.375 | 144.375 | 144.375 | 140.375 | 140.375 | 127 | 121 | 120 | 49 | 48 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15

## Cavern Outfitting
[17 empty] | Tech | Weld | 2023 | [11 empty] | 2024 | [47 empty] | 2025 | [47 empty] | 2026
T0-AUP of North Cavern | line |  |  | # | Contractors |  |  | I&I |  |  |  |  | Consortia |  |  |  | FTE | FTE | -3 |  |  |  | -2 |  |  |  | -1 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  | 19 |  |  |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  | 25 |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32
Weeks | # | Marzio Activity | P-6 Activity | Weeks | Elec | Mech | CERN | Elec | Net | Surv | Weld | Tech | APA | CE | PD | HV | Hours | Hours | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128
[19 empty] | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-11-01 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2020-12-25 | 2020-01-01 | 2020-01-08 | 2020-01-15 | 2020-01-22 | 2020-02-05 | 2020-02-12 | 2020-02-19 | 2020-02-26 | 2020-03-04 | 2020-03-11 | 2020-03-18 | 2020-03-25 | 2020-04-01 | 2020-04-08 | 2020-04-15 | 2020-04-22 | 2020-05-06 | 2020-05-13 | 2020-05-20 | 2020-05-27 | 2020-06-03 | 2020-06-10 | 2020-06-17 | 2020-06-24 | 2020-07-01 | 2020-07-08 | 2020-07-15 | 2020-07-22 | 2020-08-05 | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-02 | 2020-09-09 | 2020-09-16 | 2020-09-23 | 2020-10-01 | 2020-10-07 | 2020-10-14 | 2020-10-21 | 2020-11-04 | 2020-11-11 | 2020-11-18 | 2020-11-25 | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2020-12-23 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-04-01 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-05-05 | 2020-05-12 | 2020-05-19 | 2020-05-26 | 2020-06-02 | 2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-07-01 | 2020-07-07 | 2020-07-14 | 2020-07-21 | 2020-08-04 | 2020-08-11 | 2020-08-18 | 2020-08-25 | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 2020-11-10 | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2020-12-15 | 2020-12-22 | 2020-01-05 | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-28
Cavern # 1 Preparation |  |  |  | 12 | [6 empty] | #REF! | [5 empty] | 4000 | 320 | -1 -2: Start-up Warm Structure # 1; 4 13: Warm Structure # 1; 13 49: Mezzanine
Labor training & orientation Sr Technicians | 4 | Training Core Techs + Leaders | A48692 | 4 | [12 empty] | 0 |  | -3 -12: 3; -3 -11: 3; -3 -10: 3; -3 -9: 3
Labor training & orientation Technicians | 4 |  |  | 4 | [7 empty] | 15 |  |  |  |  | 2400 |  | -2 -8: 3; -2 -7: 3; -2 -6: 3; -2 -5: 3; -1 -4: 4; -1 -3: 4; -1 -2: 4; -1 -1: 4; 1 1: 4; 1 2: 4; 1 3: 4; 1 4: 4; 2 5: 2; 2 6: 2; 2 7: 2; 2 8: 2; 3 9: 2; 3 10: 2; 3 11: 2; 3 12: 2
Labor training & orientation Welders | 4 |  |  | 4 | [6 empty] | 3 | [6 empty] | 480 | bar: 1 1 to 1 4; 3 9 to 3 12; 5 17 to 5 20
SR Tech Labor Transition for Changing Activities | 62 |  | A48694 | 20 | [7 empty] | 3 |  |  |  |  | 2400 |  | -2 -8: 3; -2 -7: 3; -2 -6: 3; -2 -5: 3; -1 -4: 3; -1 -3: 3; -1 -2: 3; -1 -1: 3; 1 1: 3; 1 2: 3; 1 3: 3; 1 4: 3; 2 5: 3; 2 6: 3; 2 7: 3; 2 8: 3; 3 9: 3; 3 10: 3; 3 11: 3; 3 12: 3
Prepare mechanical workshop | 29 | Mech Shop | A47650 | 8 | [7 empty] | 2 |  |  |  |  | 640 |  | 2 5: 2; 2 6: 2; 2 7: 2; 2 8: 2; 3 9: 2; 3 10: 2; 3 11: 2; 3 12: 2
Lower floor beams | 13 | Startup | A47640 | 12 | [7 empty] | 2 |  |  |  |  | 960 |  | 1 1: 2; 1 2: 2; 1 3: 2; 1 4: 2; 2 5: 2; 2 6: 2; 2 7: 2; 2 8: 2; 3 9: 2; 3 10: 2; 3 11: 2; 3 12: 2
Install Cavern Bridge Crane | 13 | Startup | A47670 | 12 | [7 empty] | 1 |  |  |  |  | 480 | bar: 1 1 to 3 12
| 13 | Startup |  | 8 | [6 empty] | 1 | [6 empty] | 320 | bar: 2 5 to 3 12
Install Temporary safety detectors (ODH, Fire,…) | 11 | Startup |  | 3 |  |  |  | 2 | bar: 1 4 to 2 6
Post AUP preparation ongoing Maintenance | 11 | Startup | A48542 | 12 | [7 empty] | 1 |  |  |  |  | 480 | bar: 1 1 to 3 12
Install temporary stairs | 14 | Stairs | A47956 | 12 | [7 empty] | 2 |  |  |  |  | 960 |  | 1 1: 2; 1 2: 2; 1 3: 2; 1 4: 2; 2 5: 2; 2 6: 2; 2 7: 2; 2 8: 2; 3 9: 2; 3 10: 2; 3 11: 2; 3 12: 2
Install Temporary Power/ventilation | 14 | Stairs | A47960 | 12 |  |  |  | 2 | [10 empty] | 1 1: 2; 1 2: 2; 1 3: 2; 1 4: 1; 2 5: 1; 2 6: 1; 2 7: 2; 2 8: 2; 3 9: 2; 3 10: 2; 3 11: 2; 3 12: 2
| 14 | Stairs |  | 12 | [7 empty] | 1 |  |  |  |  | 480 | bar: 1 1 to 3 12
Warm Cryostat #1 Installation |  |  |  | 52 | [12 empty] | 11520 | 3040 | bar: -3 -12 to 13 50
SR Tech Labor Transition for Changing Activities | 62 |  | A48698 | 92 | [7 empty] | 3 |  |  |  |  | 11040 | [25 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Prepare elect. isolation below beams | 12 | Install Warm Dec #1 | A47912 | 4 | [7 empty] | 2 |  |  |  |  | 320 |  | 4 13: 2; 4 14: 2; 4 15: 2; 4 16: 2; 28 109: cleanroom
| 12 | Install Warm Dec #1 | [8 empty] | 2 | [6 empty] | 320 | 4 13: 2; 4 14: 2; 4 15: 2; 4 16: 2
Prepare corner pads inside concrete slots | 12 | Install Warm Dec #1 | A47912 | 4 | [7 empty] | 2 |  |  |  |  | 320 |  | 5 17: 2; 5 18: 2; 5 19: 2; 5 20: 2
| 12 | Install Warm Dec #1 |  | 4 | [6 empty] | 2 | [6 empty] | 320 | 5 17: 2; 5 18: 2; 5 19: 2; 5 20: 2
Level Floor, Grout, install plates | 12 | Install Warm Dec #1 | A47916 | 12 | [7 empty] | 2 |  |  |  |  | 960 |  | 6 21: 2; 6 22: 2; 6 23: 2; 6 24: 2; 7 25: 2; 7 26: 2; 7 27: 2; 7 28: 2; 8 29: 2; 8 30: 2; 8 31: 2; 8 32: 2
| 12 | Install Warm Dec #1 |  | 12 | [6 empty] | 2 | [6 empty] | 960 | 6 21: 2; 6 22: 2; 6 23: 2; 6 24: 2; 7 25: 2; 7 26: 2; 7 27: 2; 7 28: 2; 8 29: 2; 8 30: 2; 8 31: 2; 8 32: 2
Ongoing Cavern Maintenance | 12 | Install Warm Dec #1 | A48696 | 48 | [7 empty] | 3 |  |  |  |  | 5760 |  | 4 13: 3; 4 14: 3; 4 15: 3; 4 16: 3; 5 17: 3; 5 18: 3; 5 19: 3; 5 20: 3; 6 21: 3; 6 22: 3; 6 23: 3; 6 24: 3; 7 25: 3; 7 26: 3; 7 27: 3; 7 28: 3; 8 29: 3; 8 30: 3; 8 31: 3; 8 32: 3; 9 33: 3; 9 34: 3; 9 35: 3; 9 36: 3; 10 37: 3; 10 38: 3; 10 39: 3; 10 40: 3; 11 41: 3; 11 42: 3; 11 43: 3; 11 44: 3; 12 45: 3; 12 46: 3; 12 47: 3; 12 48: 3; 13 49: 3; 13 50: 3; 13 51: 3; 13 52: 3; 14 53: 3; 14 54: 3; 14 55: 3; 14 56: 3; 15 57: 3; 15 58: 3; 15 59: 3; 15 60: 3
Cross check floor position and planarity (surveyors) |  |  |  | 8 | [5 empty] | 2 | [8 empty] | 1 3: 2; 1 4: 2; 2 5: 2; 2 6: 2; 2 7: 2; 2 8: 2; 3 9: 2; 3 10: 2
Prep cryostat floor (contractor) |  |  |  | 8 |  |  | 15 | [11 empty] | 1 3: 15; 1 4: 15; 2 5: 15; 2 6: 15; 2 7: 15; 2 8: 15; 3 9: 15; 3 10: 15
Install Cryostat floor Decking-Start when available |  | handrails+ vert access | A48662 | 8 | [7 empty] | 4 |  |  |  |  | 1280 |  | 9 33: 4; 9 34: 4; 9 35: 4; 9 36: 4; 10 37: 4; 10 38: 4; 10 39: 4; 10 40: 4
|  | handrails+ vert access |  | 8 | [6 empty] | 3 | [6 empty] | 960 | 9 33: 3; 9 34: 3; 9 35: 3; 9 36: 3; 10 37: 3; 10 38: 3; 10 39: 3; 10 40: 3
Install portals + belts |  |  |  | 30 |  |  | 15 | [11 empty] | 3 11: 15; 3 12: 15; 4 13: 15; 4 14: 15; 4 15: 15; 4 16: 15; 5 17: 15; 5 18: 15; 5 19: 15; 5 20: 15; 6 21: 15; 6 22: 15; 6 23: 15; 6 24: 15; 7 25: 15; 7 26: 15; 7 27: 15; 7 28: 15; 8 29: 15; 8 30: 15; 8 31: 15; 8 32: 15; 9 33: 15; 9 34: 15; 9 35: 15; 9 36: 15; 10 37: 15; 10 38: 15; 10 39: 15; 10 40: 15; 11 41: 15
Survey geometry and install plates |  |  |  | 20 | [5 empty] | 2 | [8 empty] | 4 15: 2; 4 16: 2; 5 17: 2; 5 18: 2; 5 19: 2; 5 20: 2; 6 21: 2; 6 22: 2; 6 23: 2; 6 24: 2; 7 25: 2; 7 26: 2; 7 27: 2; 7 28: 2; 8 29: 2; 8 30: 2; 8 31: 2; 8 32: 2; 9 33: 2; 9 34: 2
Install roof |  |  |  | 10 |  |  | 15 | [11 empty] | 8 31: 15; 8 32: 15; 9 33: 15; 9 34: 15; 9 35: 15; 9 36: 15; 10 37: 15; 10 38: 15; 10 39: 15; 10 40: 15; 11 41: 15; 11 42: 15; 11 43: 15; 11 44: 15; 12 45: 15; 12 46: 15; 12 47: 15; 12 48: 15; 13 49: 15; 13 50: 15
Survey geometry and install plates + top temp floor |  |  |  | 20 | [5 empty] | 2 | [8 empty] | 9 35: 2; 9 36: 2; 10 37: 2; 10 38: 2; 10 39: 2; 10 40: 2; 11 41: 2; 11 42: 2; 11 43: 2; 11 44: 2; 12 45: 2; 12 46: 2; 12 47: 2; 12 48: 2; 13 49: 2; 13 50: 2
weld plates from inside (in parallel) |  |  |  | 40 |  |  | 8 | [11 empty] | 4 15: 8; 4 16: 8; 5 17: 8; 5 18: 8; 5 19: 8; 5 20: 8; 6 21: 8; 6 22: 8; 6 23: 8; 6 24: 8; 7 25: 8; 7 26: 8; 7 27: 8; 7 28: 8; 8 29: 8; 8 30: 8; 8 31: 8; 8 32: 8; 9 33: 8; 9 34: 8; 9 35: 8; 9 36: 8; 10 37: 8; 10 38: 8; 10 39: 8; 10 40: 8; 11 41: 8; 11 42: 8; 11 43: 8; 11 44: 8; 12 45: 8; 12 46: 8; 12 47: 8; 12 48: 8; 13 49: 8; 13 50: 8
Prepare TCO structure |  |  |  | 4 |  |  | 5 | [11 empty] | 12 47: 5; 12 48: 5; 13 49: 5; 13 50: 5
Install Cryogenics Mezzanine #1 | 15 | mezzanine | A47922 | 12 | [7 empty] | 3 |  |  |  |  | 1440 |  | 11 41: 3; 11 42: 3; 11 43: 3; 11 44: 3; 12 45: 3; 12 46: 3; 12 47: 3; 12 48: 3; 13 49: 3; 13 50: 3; 13 51: 3; 13 52: 3
| 15 | mezzanine |  | 12 | [6 empty] | 1 | [6 empty] | 480 | bar: 11 41 to 13 52
Install Detector Mezzanine #1 | 15 | mezzanine | A48538 | 12 | [7 empty] | 3 |  |  |  |  | 1440 |  | 11 41: 3; 11 42: 3; 11 43: 3; 11 44: 3; 12 45: 3; 12 46: 3; 12 47: 3; 12 48: 3; 13 49: 3; 13 50: 3; 13 51: 3; 13 52: 3
| 15 | mezzanine |  | 12 | [6 empty] | 1 | [6 empty] | 480 | bar: 11 41 to 13 52
Install N-Cavern Bridge | 17 | Install Bridge | A47924 | 8 | [7 empty] | 5 |  |  |  |  | 1600 |  | 14 53: 5; 14 54: 5; 14 55: 5; 14 56: 5; 15 57: 5; 15 58: 5; 15 59: 5; 15 60: 5
Install Bridge to cyrostat walkway | 17 | Install Bridge | 13141.01.01.662 | 8 | [7 empty] | 2 |  |  |  |  | 640 |  | 14 53: 2; 14 54: 2; 14 55: 2; 14 56: 2; 15 57: 2; 15 58: 2; 15 59: 2; 15 60: 2
Install Cyrostat Cold # 1 | [16 empty] | 12480 | 1600 | 16 61: Cyrostat Cold #1
Install Cryostat Cold #1-GTT day shift-6 days/week |  |  |  | 48 | [14 empty] | 16 61: 25; 16 62: 25; 16 63: 25; 16 64: 25; 17 65: 25; 17 66: 25; 17 67: 25; 17 68: 25; 18 69: 25; 18 70: 25; 18 71: 25; 18 72: 25; 19 73: 25; 19 74: 25; 19 75: 25; 19 76: 25; 20 77: 25; 20 78: 25; 20 79: 25; 20 80: 25; 21 81: 25; 21 82: 25; 21 83: 25; 21 84: 25; 22 85: 25; 22 86: 25; 22 87: 25; 22 88: 25; 23 89: 25; 23 90: 25; 23 91: 25; 23 92: 25; 24 93: 25; 24 94: 25; 24 95: 25; 24 96: 25; 25 97: 25; 25 98: 25; 25 99: 25; 25 100: 25; 26 101: 25; 26 102: 25; 26 103: 25; 26 104: 25; 27 105: 25; 27 106: 25; 27 107: 25; 27 108: 25
Remove crates, shipping materials Cryo Cold |  |  | A47954 | 36 | [7 empty] | 3 |  |  |  |  | 4320 |  | 16 61: 3; 16 62: 3; 16 63: 3; 16 64: 3; 17 65: 3; 17 66: 3; 17 67: 3; 17 68: 3; 18 69: 3; 18 70: 3; 18 71: 3; 18 72: 3; 19 73: 3; 19 74: 3; 19 75: 3; 19 76: 3; 20 77: 3; 20 78: 3; 20 79: 3; 20 80: 3; 21 81: 3; 21 82: 3; 21 83: 3; 21 84: 3; 22 85: 3; 22 86: 3; 22 87: 3; 22 88: 3; 23 89: 3; 23 90: 3; 23 91: 3; 23 92: 3; 24 93: 3; 24 94: 3; 24 95: 3; 24 96: 3
Install East wall cryogenic piping inside cryostat | 33 | Cryostat Internal Plumbing | A47938 | 8 | [6 empty] | 2 | [6 empty] | 640 | 23 89: 2; 23 90: 2; 23 91: 2; 23 92: 2; 24 93: 2; 24 94: 2; 24 95: 2; 24 96: 2
| 33 | Cryostat Internal Plumbing |  | 8 | [7 empty] | 3 |  |  |  |  | 960 |  | 23 89: 3; 23 90: 3; 23 91: 3; 23 92: 3; 24 93: 3; 24 94: 3; 24 95: 3; 24 96: 3
Install lower cryogenic piping at the bottom | 33 | Cryostat Internal Plumbing | A47938 | 12 | [6 empty] | 2 | [6 empty] | 960 | 25 97: 2; 25 98: 2; 25 99: 2; 25 100: 2; 26 101: 2; 26 102: 2; 26 103: 2; 26 104: 2; 27 105: 2; 27 106: 2; 27 107: 2; 27 108: 2
| 33 | Cryostat Internal Plumbing |  | 12 | [7 empty] | 5 |  |  |  |  | 2400 |  | 25 97: 3; 25 98: 3; 25 99: 3; 25 100: 3; 26 101: 3; 26 102: 3; 26 103: 3; 26 104: 3; 27 105: 3; 27 106: 3; 27 107: 3; 27 108: 3
Install DSS | 31 | DSS Beam installation | Add P6 | 12 |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 2880 |  | 23 89: 6; 23 90: 6; 23 91: 6; 23 92: 6; 24 93: 6; 24 94: 6; 24 95: 6; 24 96: 6; 25 97: 6; 25 98: 6; 25 99: 6; 25 100: 6
Cryostat leak test | [6 empty] | 4 | [11 empty] | 21 83: 4; 21 84: 4; 22 85: 4; 22 86: 4; 22 87: 4; 22 88: 4; 23 89: 4; 23 90: 4; 23 91: 4; 23 92: 4; 24 93: 4; 24 94: 4; 24 95: 4; 24 96: 4; 25 97: 4; 25 98: 4; 25 99: 4; 25 100: 4; 26 101: 4; 26 102: 4; 26 103: 4; 26 104: 4
Clean Cryostat |  |  |  | 3 |  | 6 | [12 empty] | 27 106: 6; 27 107: 6; 27 108: 6
Install False floor near endwall | 34 | Cryostat Floor | A47944 | 2 | [7 empty] | 6 |  |  |  |  | 480 |  | 26 101: 6; 26 102: 6
Complete false floor installation | 34 | Cryostat Floor | A47944 | 6 | [7 empty] | 6 |  |  |  |  | 1440 |  | 26 103: 6; 26 104: 6; 27 105: 6; 27 106: 6; 27 107: 6; 27 108: 6
CUC Setup | [16 empty] | 3520 | bar: -3 -12 to 16 62
Install cable trays to the alcove | 9 | Cable trays-Alcove | Moved from | 16 | [7 empty] | 2 |  |  |  |  | 1280 |  | 4 13: 2; 4 14: 2; 4 15: 2; 4 16: 2; 5 17: 2; 5 18: 2; 5 19: 2; 5 20: 2; 6 21: 2; 6 22: 2; 6 23: 2; 6 24: 2; 7 25: 2; 7 26: 2; 7 27: 2; 7 28: 2
| 9 | Cable trays-Alcove | A47930 | [7 empty] | 1 | [6 empty] | 640 | bar: 4 13 to 7 28
Install cable trays on cavern wall | 9 | Cable trays-Cavern | Moved from | 16 | [7 empty] | 2 |  |  |  |  | 1280 |  | 4 13: 2; 4 14: 2; 4 15: 2; 4 16: 2; 5 17: 2; 5 18: 2; 5 19: 2; 5 20: 2; 6 21: 2; 6 22: 2; 6 23: 2; 6 24: 2; 7 25: 2; 7 26: 2; 7 27: 2; 7 28: 2
Control Room | 10 | CUC Control Room | Add P6 | 16 | [7 empty] | 4 |  |  |  |  | 2560 |  | 4 13: 4; 4 14: 4; 4 15: 4; 4 16: 4; 5 17: 4; 5 18: 4; 5 19: 4; 5 20: 4; 6 21: 4; 6 22: 4; 6 23: 4; 6 24: 4; 7 25: 4; 7 26: 4; 7 27: 4; 7 28: 4
CUC DAQ Room | 10 | CUC Racks | Add P6 | 12 | [7 empty] | 2 |  |  |  |  | 960 |  | 1 1: 2; 1 2: 2; 1 3: 2; 1 4: 2; 2 5: 2; 2 6: 2; 2 7: 2; 2 8: 2; 3 9: 2; 3 10: 2; 3 11: 2; 3 12: 2
[12 empty] | Contactor |  |  | Mechanical | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Contactor |  |  | CERN | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 23 | 23 | 23 | 23 | 23 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Electrical | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Net/Vent | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Surveyor | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Welder | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Tech | [7 empty] | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | APA | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | CE | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | PD | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | HV | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Contractor | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 23 | 23 | 23 | 23 | 23 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 4 | 4 | 4 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I Core Tech | [10 empty] | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Electrical |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 2; 2 5: 2; 3 9: 2; 4 13: 0; 5 17: 0; 6 21: 0; 7 25: 0; 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | I&I |  |  | Net/Vent |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 0; 2 5: 0; 3 9: 0; 4 13: 0; 5 17: 0; 6 21: 0; 7 25: 0; 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | I&I |  |  | Surveyor |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 1; 2 5: 2; 3 9: 1; 4 13: 1; 5 17: 2; 6 21: 2; 7 25: 2; 8 29: 2; 9 33: 2; 10 37: 2; 11 41: 2; 12 45: 2; 13 49: 1; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | I&I |  |  | Welder |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 1; 2 5: 1; 3 9: 2; 4 13: 3; 5 17: 4; 6 21: 3; 7 25: 3; 8 29: 2; 9 33: 3; 10 37: 3; 11 41: 2; 12 45: 2; 13 49: 2; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 2; 24 93: 2; 25 97: 2; 26 101: 2; 27 105: 2; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | I&I |  |  | Tech |  |  |  | -2 -8: 3; -1 -4: 4; 1 1: 13; 2 5: 13; 3 9: 13; 4 13: 13; 5 17: 13; 6 21: 13; 7 25: 13; 8 29: 5; 9 33: 7; 10 37: 7; 11 41: 9; 12 45: 9; 13 49: 9; 14 53: 10; 15 57: 10; 16 61: 3; 17 65: 3; 18 69: 3; 19 73: 3; 20 77: 3; 21 81: 3; 22 85: 3; 23 89: 12; 24 93: 12; 25 97: 9; 26 101: 9; 27 105: 9; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | Consortia |  |  | APA |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 0; 2 5: 0; 3 9: 0; 4 13: 0; 5 17: 0; 6 21: 0; 7 25: 0; 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | Consortia |  |  | CE |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 0; 2 5: 0; 3 9: 0; 4 13: 0; 5 17: 0; 6 21: 0; 7 25: 0; 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | Consortia |  |  | PD |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 0; 2 5: 0; 3 9: 0; 4 13: 0; 5 17: 0; 6 21: 0; 7 25: 0; 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0
[12 empty] | Consortia |  |  | HV |  |  |  | -2 -8: 0; -1 -4: 0; 1 1: 0; 2 5: 0; 3 9: 0; 4 13: 0; 5 17: 0; 6 21: 0; 7 25: 0; 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0

## Cleanroom Installation
[17 empty] | Tech | Weld | 2024 | [19 empty] | 2025 | [47 empty] | 2026 | [47 empty] | 2027
T0-AUP of North Cavern | line |  |  | # | Contractors |  |  | I&I |  |  |  |  | Consortia |  |  |  | FTE | FTE | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  | 19 |  |  |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  | 25 |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  | 33 |  |  |  | 34 |  |  |  | 35 |  |  |  | 36 |  |  |  | 37 |  |  |  | 38 |  |  |  | 39 |  |  |  | 40 |  |  |  | 41 |  |  |  | 42 |  |  |  | 43 |  |  |  | 44
Weeks | # | Marzio Activity | P-6 Activity | Weeks | Elec | Mech | CERN | Elec | Net | Surv | Weld | Tech | APA | CE | PD | HV | Hours | Hours | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176
[19 empty] | 2020-08-05 | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-02 | 2020-09-09 | 2020-09-16 | 2020-09-23 | 2020-10-01 | 2020-10-07 | 2020-10-14 | 2020-10-21 | 2020-11-04 | 2020-11-11 | 2020-11-18 | 2020-11-25 | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2020-12-23 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-04-01 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-05-05 | 2020-05-12 | 2020-05-19 | 2020-05-26 | 2020-06-02 | 2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-07-01 | 2020-07-07 | 2020-07-14 | 2020-07-21 | 2020-08-04 | 2020-08-11 | 2020-08-18 | 2020-08-25 | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 2020-11-10 | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2020-12-15 | 2020-12-22 | 2020-01-05 | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-28 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-09-01 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-12-01 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-01-04 | 2020-01-11 | 2020-01-18 | 2020-01-25 | 2020-02-01 | 2020-02-08 | 2020-02-15 | 2020-02-22 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22 | 2020-04-05 | 2020-04-12 | 2020-04-19 | 2020-04-26 | 2020-05-03 | 2020-05-10 | 2020-05-17 | 2020-05-24 | 2020-06-01 | 2020-06-07 | 2020-06-14 | 2020-06-21 | 2020-07-05 | 2020-07-12 | 2020-07-19 | 2020-07-26
Top of Cryostat Infrastructure Detector #1 | [16 empty] | 13440 | 3040 | bar: 8 29 to 27 108
Labor training & orientation Technicians |  |  | A48702 | 8 | [7 empty] | 2 |  |  |  |  | 640 |  | 12 45: 2; 12 46: 2; 12 47: 2; 12 48: 2; 13 49: 2; 13 50: 2; 13 51: 2; 13 52: 2; 25 97: 2; 25 98: 2; 25 99: 2; 25 100: 2; 26 101: 3; 26 102: 3; 26 103: 3; 26 104: 3
Install isolation transformer | 22 | Mezz-AC,Trays,racks |  | 1 | 4 | [13 empty] | 14 54: 4
Install AC power to both mezzanines | 22 | Mezz-AC,Trays,racks |  | 2 | 4 | [13 empty] | 14 55: 4; 14 56: 4
Install cryogenic mezzanine compressed air | 22 | Mezz-AC,Trays,racks |  | 4 | [7 empty] | 4 |  |  |  |  | 640 |  | 14 53: 4; 14 54: 4; 14 55: 4; 14 56: 4
Install mezzanine lighting | 22 | Mezz-AC,Trays,racks |  | 2 | 4 | [13 empty] | 14 56: 4; 15 57: 4
Mount racks on cryostat-1 electronics mezzanine | 22 | Mezz-AC,Trays,racks |  | 1 | bar: 15 59
Install electronic Mezzanine Cable trays Cryostat Cable trays Install grounding in trays | 22 | Mezz-AC,Trays,racks |  | 4 | [7 empty] | 4 |  |  |  |  | 640 |  | 15 57: 4; 15 58: 4; 15 59: 4; 15 60: 4
| 22 | Mezz-AC,Trays,racks |  | 4 | [6 empty] | 1 | [6 empty] | 160 | bar: 14 53 to 15 60
Connect power to electronic mezzanine racks | 22 | Mezz-AC,Trays,racks |  | 2 | 4 | [13 empty] | 15 59: 4; 15 60: 4
Install Ground monitoring | 22 | Mezz-AC,Trays,racks |  | 1 |  |  |  | 2 | [10 empty] | 16 61: 2
Install the detector safety system | 22 | Mezz-AC,Trays,racks |  | 1 |  |  |  | 2 | [10 empty] | 16 61: 2
Connect racks to detector safety system | 22 | Mezz-AC,Trays,racks |  | 2 |  |  |  | 2 | [10 empty] | 16 62: 2
Commission detector safety system | 22 | Mezz-AC,Trays,racks |  | 4 | bar: 16 62 to 17 65
Install Barracks-Core Tech | 23 | Barracks-HVAC,Vent |  | 16 | [7 empty] | 4 |  |  |  |  | 2560 |  | 16 61: 4; 16 62: 4; 16 63: 4; 16 64: 4; 17 65: 4; 17 66: 4; 17 67: 4; 17 68: 4; 18 69: 4; 18 70: 4; 18 71: 4; 18 72: 4; 19 73: 4; 19 74: 4; 19 75: 4; 19 76: 4
Install Barracks Ventilation | 23 | Barracks-HVAC,Vent |  | 4 |  |  |  |  | 2 | [9 empty] | 16 63: 2; 16 64: 2; 17 65: 2; 17 66: 2
Install Barracks fire suppression | 23 | Barracks-HVAC,Vent |  | 4 |  | 4 | [12 empty] | 17 68: 4; 18 69: 4; 18 70: 4; 18 71: 4
Connect barracks power | 23 | Barracks-HVAC,Vent |  | 1 | 4 | [13 empty] | 18 72: 4
Mount DAQ racks in barracks | 23 | Barracks-HVAC,Vent |  | 2 | bar: 19 73 to 19 74
Install network. |  |  |  | 4 |  |  |  |  | 2 | [9 empty] | 16 63: 2; 16 64: 2; 17 65: 2; 17 66: 2
|  |  |  | 4 | [7 empty] | 2 |  |  |  |  | 320 |  | 16 63: 2; 16 64: 2; 17 65: 2; 17 66: 2
Install cryostat crossing tubes and flanges | 30 | Crossing Tubes |  | 16 | [6 empty] | 1 | [6 empty] | 640 | 16 61: 1; 16 62: 1; 16 63: 1; 16 64: 1; 17 65: 1; 17 66: 1; 17 67: 1; 17 68: 1; 18 69: 3; 18 70: 3; 18 71: 3; 18 72: 3; 19 73: 3; 19 74: 3; 19 75: 3; 19 76: 3
| 30 | Crossing Tubes |  | 16 | [7 empty] | 5 |  |  |  |  | 3200 |  | 16 61: 5; 16 62: 5; 16 63: 5; 16 64: 5; 17 65: 5; 17 66: 5; 17 67: 5; 17 68: 5; 18 69: 5; 18 70: 5; 18 71: 5; 18 72: 5; 19 73: 5; 19 74: 5; 19 75: 5; 19 76: 5
Survey crossing tubes-I&I Surveyors | 30 | Crossing Tubes | [7 empty] | 2 | [8 empty] | 17 67: 2; 17 68: 2; 18 69: 2; 18 70: 2; 18 71: 2; 18 72: 2
Install valves and pipes for cryostat N2 blanket | 31 | Cryo Venting |  | 16 | [6 empty] | 1 | [6 empty] | 640 | bar: 14 53 to 17 68
Install feedthrough purge pipe connect Crossing | 31 | Cryo Venting |  | 16 | [6 empty] | 1 | [6 empty] | 640 | bar: 14 53 to 17 68
Core Tech Labor CryoVenting | 31 | Cryo Venting |  | 16 | [7 empty] | 2 |  |  |  |  | 1280 |  | 14 53: 2; 14 54: 2; 14 55: 2; 14 56: 2; 15 57: 2; 15 58: 2; 15 59: 2; 15 60: 2; 16 61: 2; 16 62: 2; 16 63: 2; 16 64: 2; 17 65: 2; 17 66: 2; 17 67: 2; 17 68: 2
CE Feed thrus | 32 | CE Feed-thru/Cross/Racks |  | 12 | [6 empty] | 1 | [6 empty] | 480 | bar: 20 77 to 22 88
| 32 | CE Feed-thru/Cross/Racks |  | 12 | [7 empty] | 5 |  |  |  |  | 2400 |  | 20 77: 5; 20 78: 5; 20 79: 5; 20 80: 5; 21 81: 5; 21 82: 5; 21 83: 5; 21 84: 5; 22 85: 5; 22 86: 5; 22 87: 5; 22 88: 5
Install pedestals for 12U racks | 32 | CE Feed-thru/Cross/Racks |  | 8 | [6 empty] | 1 | [6 empty] | 320 | bar: 23 89 to 24 96
| 32 | CE Feed-thru/Cross/Racks |  | 8 | [7 empty] | 5 |  |  |  |  | 1600 |  | 23 89: 5; 23 90: 5; 23 91: 5; 23 92: 5; 24 93: 5; 24 94: 5; 24 95: 5; 24 96: 5
Install 12U racks near CE crosses cryostat1 | 32 | CE Feed-thru/Cross/Racks |  | 4 | [7 empty] | 5 |  |  |  |  | 800 |  | 25 97: 5; 25 98: 5; 25 99: 5; 25 100: 5
| 32 | CE Feed-thru/Cross/Racks |  | 4 | [6 empty] | 1 | [6 empty] | 160 | bar: 25 97 to 25 100
Install fibers from DAQ to electronics mezzanine | 32 | CE Feed-thru/Cross/Racks |  | 4 |  |  |  |  | 2 | [9 empty] | 25 100: 2; 26 101: 2; 26 102: 2; 26 103: 2
Early detector installation-Top of Cryostat #1 | [16 empty] | 960 | bar: 8 29 to 32 128
Install CE power supplies on electronic mezzanine |  |  |  | 2 | [9 empty] | 4
Connect CE electronics modules to safety system/slow control and test |  |  |  | 2 | [9 empty] | 4
Install PD power supplies in the mezzanine racks |  |  |  | 2 | [10 empty] | 2
Connect PD power supplies to detector safety system/slow control and test |  |  |  | 2 | [10 empty] | 2
Install PD modules in the 12U racks |  |  |  | 1 | [10 empty] | 2
Connect PD modules to fibers to the mezzanine |  |  |  | 2 | [10 empty] | 2
Install CE crosses |  |  |  | 5 | [9 empty] | 4
Install WEIC on cryostat1 |  |  |  | 5 | [9 empty] | 4
Install cables fibers between mezzanine and WEIC |  |  | A48434 | 8 | [7 empty] | 3 |  |  |  |  | 960 |  | 18 69: 3; 18 70: 3; 18 71: 3; 18 72: 3; 19 73: 3; 19 74: 3; 19 75: 3; 19 76: 3
Install CAL electronics on electronics mezzanine |  |  |  | 20 | bar: 32 128 to 34 136
Connect CAL electronics to safety system |  |  |  | 20 | bar: 32 128 to 34 136
Cleanroom Preparation Phase1 detector #1 | bar: 8 29 to 16 64
Configure Cryostat HVAC for Det. Install |  |  |  | 4
Inspect Bridge and Crane - verify interface | 27 | Clean R Crane | A47952 | 2 |  | 4 | [5 empty] | 4 |  |  |  |  | 320 |  | 14 53: 4; 14 54: 4; 23 89: 4
Install Scaffolding for crane installation | 27 | Clean R Crane | A47952 | 2 |  | 4 | [5 empty] | 4 |  |  |  |  | 320 |  | 14 55: 4; 14 56: 4; 23 89: 4
Install Crane power infrastructure | 27 | Clean R Crane | A47952 | 2 |  |  |  | 2 |  |  |  | 4 |  |  |  |  | 320 |  | 15 57: 4; 15 58: 4; 23 89: 2; 23 90: 2
Install cleanroom crane (mechanical) | 27 | Clean R Crane | A47952 | 1 |  | 4 | [5 empty] | 4 |  |  |  |  | 160 |  | 15 59: 4; 23 90: 4; 23 91: 4
Connect CR crane power and Commission | 27 | Clean R Crane | A47952 | 1 |  |  |  | 2 |  |  |  | 4 |  |  |  |  | 160 |  | 15 60: 4; 23 92: 2; 28 109: Cleanroom
Install cleanroom steel structure detector #1 | [16 empty] | 3200 | bar: 8 29 to 11 44
Inspect Assembly Tower components | 34 | Cleanroom Steel | A47840 | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 16 61: 5; 16 62: 5
Assemble Tower sections | 34 | Cleanroom Steel |  | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 16 63: 5; 16 64: 5
Install rails, hoists, and trollies | 34 | Cleanroom Steel |  | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 17 65: 5; 17 66: 5
Install North and South towers | 34 | Cleanroom Steel |  | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 17 67: 5; 17 68: 5
Inspect roof structure materials | 34 | Cleanroom Steel |  | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 18 69: 5; 18 70: 5
Inspect CR platform, railing, stair components | 34 | Cleanroom Steel |  | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 18 71: 5; 18 72: 5
Install roof support structure | 34 | Cleanroom Steel |  | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 19 73: 5; 19 74: 5
Install CR platforms, railings, stairs and ladders | 34 | Cleanroom Steel |  | 2 | [7 empty] | 5 |  |  |  |  | 400 |  | 19 75: 5; 19 76: 5
Install CR cold boxes detector #1 | [16 empty] | 9120 | 480 | bar: 8 29 to 13 52
Inspect CR Coldbox components | 28 | Cold Box Prep | A47850 | 2 | [7 empty] | 6 |  |  |  |  | 480 |  | 8 29: 6; 8 30: 6
Install CR wall behind the cold boxes | 28 | Cold Box Prep |  | 2 | [7 empty] | 6 |  |  |  |  | 480 |  | 8 31: 6; 8 32: 6
Install pedestal for cold boxes | 28 | Cold Box Prep |  | 2 | [7 empty] | 6 |  |  |  |  | 480 |  | 9 33: 6; 9 34: 6
Assemble CB1 Body | 28 | Cold Box Prep |  | 6 | [7 empty] | 6 |  |  |  |  | 1440 |  | 9 35: 6; 9 36: 6; 10 37: 6; 10 38: 6; 10 39: 6; 10 40: 6
Assemble CB2 Body | 28 | Cold Box Prep |  | 6 | [7 empty] | 6 |  |  |  |  | 1440 |  | 11 41: 6; 11 42: 6; 11 43: 6; 11 44: 6; 12 45: 6; 12 46: 6
Assemble CB3 Body | 28 | Cold Box Prep |  | 6 | [7 empty] | 6 |  |  |  |  | 1440 |  | 12 47: 6; 12 48: 6; 13 49: 6; 13 50: 6; 13 51: 6; 13 52: 6
Install CB1 body | 28 | Cold Box Install |  | 2 | [7 empty] | 7 |  |  |  |  | 560 |  | 20 77: 7; 20 78: 7
Install CB1 doors | 28 | Cold Box Install |  | 1 | [7 empty] | 7 |  |  |  |  | 280 |  | 20 79: 7
Test CB1 | 28 | Cold Box Install |  | 1 | [7 empty] | 7 |  |  |  |  | 280 |  | 20 80: 7
Install CB2 body | 28 | Cold Box Install |  | 2 | [7 empty] | 7 |  |  |  |  | 560 |  | 21 81: 7; 21 82: 7
Install CB2 doors | 28 | Cold Box Install |  | 1 | [7 empty] | 7 |  |  |  |  | 280 |  | 21 83: 7
Test CB2 | 28 | Cold Box Install |  | 1 | [7 empty] | 7 |  |  |  |  | 280 |  | 21 84: 7
Install CB3 body | 28 | Cold Box Install |  | 2 | [7 empty] | 7 |  |  |  |  | 560 |  | 22 85: 7; 22 86: 7
Install CB3 doors | 28 | Cold Box Install |  | 1 | [7 empty] | 7 |  |  |  |  | 280 |  | 22 87: 7
Test CB3 | 28 | Cold Box Install |  | 1 | [7 empty] | 7 |  |  |  |  | 280 |  | 22 88: 7
Welding on Cold Boxes | 28 | Cold Box Install |  | 12 | [6 empty] | 1 | [6 empty] | 480 | 9 33: 3; 9 34: 3; 9 35: 3; 9 36: 3; 10 37: 3; 10 38: 3; 10 39: 3; 10 40: 3; 11 41: 3; 11 42: 3; 11 43: 3; 11 44: 3; 12 45: 3; 12 46: 3; 12 47: 3; 12 48: 3; 13 49: 1; 13 50: 1; 13 51: 1; 13 52: 1; 20 77: 1; 20 78: 1; 20 79: 1; 20 80: 1; 21 81: 1; 21 82: 1; 21 83: 1; 21 84: 1; 22 85: 1; 22 86: 1; 22 87: 1; 22 88: 1
Cleanroom Preparation Phase2 detector #1 | [16 empty] | 4000 | 480 | bar: 8 29 to 27 108
Install coldbox cryogenics
Install coldbox cryogenic plant |  |  |  | 18
N2 system | 29 | N2 System | A48482,86,88 | 12 | [7 empty] | 2 |  |  |  |  | 960 |  | 20 77: 2; 20 78: 2; 20 79: 2; 20 80: 2; 21 81: 2; 21 82: 2; 21 83: 2; 21 84: 2; 22 85: 2; 22 86: 2; 22 87: 2; 22 88: 2
| 29 | N2 System | A48482,86,88 | 12 | [6 empty] | 1 | [6 empty] | 480 | bar: 20 77 to 22 88
Commission cold boxes |  |  |  | 4 | bar: 28 110 to 29 113
Install CR walls against cryostat and cavern | 35 | Cleanroom Infrastructure |  | 3
Install CR temporary sprinkler system | 35 | Cleanroom Infrastructure
Install cleanroom cable trays | 35 | Cleanroom Infrastructure |  | 2 | [14 empty] | 28 109: Cleanroom
Install Temporary CR power | 35 | Cleanroom Infrastructure |  | 1 |  |  |  | 2 | [10 empty] | 20 77: 2
Install rack in CR | 35 | Cleanroom Infrastructure |  | 1 | bar: 20 78
Run fiberoptic to rack connect WIFI | 35 | Cleanroom Infrastructure |  | 1 |  |  |  |  | 2 | [9 empty] | 20 79: 2
Install temporary CR roof lighting | 35 | Cleanroom Infrastructure |  | 1
Install temporary air scrubbers | 35 | Cleanroom Infrastructure |  | 1
Connect power to hoists in CR | 35 | Cleanroom Infrastructure |  | 1 |  |  |  | 2
Install APA assembly frames | 35 | Cleanroom Infrastructure |  | 1
Electrical hookup to APA assembly frames | 35 | Cleanroom Infrastructure |  | 2 |  |  |  | 2 | [10 empty] | 21 81: 2; 21 82: 2
Install CPA assembly frame | 35 | Cleanroom Infrastructure |  | 1
Install cleanroom roof and remaining walls | 35 | Cleanroom Infrastructure | Add to | 4 |  | 8 | [12 empty] | 21 82: 8; 21 83: 8; 21 84: 8; 22 85: 8
Install access Eqp. to roof over coldbox | 35 | Cleanroom Infrastructure | P6 | 1
Install CE crosses on cold boxes | 35 | Cleanroom Infrastructure |  | 1
Install power supplies for coldbox and cables | 35 | Cleanroom Infrastructure |  | 1 | [14 empty] | 21 81: 2
Install WEIC on cold boxes | 35 | Cleanroom Infrastructure |  | 1 | [14 empty] | 21 81: 2
Leak test CB, CE cross and WEIC | 35 | Cleanroom Infrastructure |  | 1 | [14 empty] | 28 109: Cleanroom
Commission CB readout | 35 | Cleanroom Infrastructure |  | 4 | [14 empty] | 21 82: 4; 21 83: 4; 21 84: 4; 22 85: 4
Install ESD floor tile and check conductivity | 35 | Cleanroom Infrastructure |  | 1 |  |  |  | 2
Place EDS wrist strap ground points | 35 | Cleanroom Infrastructure |  | 1 |  |  |  | 2
Ground towers and cold boxes | 35 | Cleanroom Infrastructure |  | 1 |  |  |  | 2
Install cleanroom doors | 35 | Cleanroom Infrastructure |  | 1
Check CR light spectrum for UV+ measure air flows | 35 | Cleanroom Infrastructure |  | 1
Install washing station in SAS | 35 | Cleanroom Infrastructure |  | 1
Core Tech Labor for Infrastructure | 35 | Cleanroom Infrastructure |  | 24 | [7 empty] | 3 |  |  |  |  | 2880 |  | 20 77: 3; 20 78: 3; 20 79: 3; 20 80: 3; 21 81: 3; 21 82: 3; 21 83: 3; 21 84: 3; 22 85: 3; 22 86: 3; 22 87: 3; 22 88: 3; 23 89: 3; 23 90: 3; 23 91: 3; 23 92: 3; 24 93: 3; 24 94: 3; 24 95: 3; 24 96: 3; 25 97: 3; 25 98: 3; 25 99: 3; 25 100: 3
Setup for wire tension measurements |  |  |  | 5 | [8 empty] | 4 | [5 empty] | 26 104: 4; 27 105: 4; 27 106: 4; 27 107: 4; 27 108: 4
Setup for FEMB testing |  |  |  | 5 | [9 empty] | 2 |  |  |  |  | 26 104: 2; 27 105: 2; 27 106: 2; 27 107: 2; 27 108: 2
Setup for electronics testing on towers |  |  |  | 5 | [9 empty] | 2 |  |  |  |  | 26 104: 2; 27 105: 2; 27 106: 2; 27 107: 2; 27 108: 2
Setup for CPA assembly |  |  |  | 5 | [11 empty] | 4 |  |  | 26 104: 4; 27 105: 4; 27 106: 4; 27 107: 4; 27 108: 4
Install CR environmental monitoring |  |  |  | 2 |  |  |  | 2 |  |  |  | 2 |  |  |  |  | 160 |  | 26 103: 2; 26 104: 2
Cleanroom ready for startup
Cleanroom Startup Detector #1 | [16 empty] | 2560 | bar: 8 29 to 11 44
Furnish changing rooms and material SAS | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 26 101: 8
Clean cleanroom and inspect cleanroom | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 26 102: 8
Bring clean tools and rigging eqp. into cleanroom | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 26 103: 8
Set up desks for CAL installation | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 26 104: 8
Setup Field cage assembly area | 39 | Cleanroom Prep | A47950 | 1 | [11 empty] | 4 |  |  | 27 107: 4; 27 108: 4
Bring custom lifting tooling into cleanroom | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 27 105: 8
Install desks, cabinets, carts, and work platforms | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 27 106: 8
Install and commission CR scissor lifts | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 27 107: 8
Place and commission PD scanner | 39 | Cleanroom Prep | A47950 | 2 | [10 empty] | 4 |  |  |  | 27 107: 4; 27 108: 4
Setup for PD installation | 39 | Cleanroom Prep | A47950 | 2 | [10 empty] | 4 |  |  |  | 27 107: 4; 27 108: 4
Install Cables and patch panels in CB | 39 | Cleanroom Prep | A47950 | 1 | [7 empty] | 8 |  |  |  |  | 320 |  | 27 108: 8
Calibration and Cryo instrumentation #1 | [16 empty] | 0 | bar: 8 29 to 11 44
Installation of CI and cryo instrumentation | [11 empty] | 0 |  |  |  |  | 0
Build End Wall Modules |  |  |  | 3 | [11 empty] | 4 |  |  | 27 107: 4; 27 108: 4; 28 109: 4
Install End Wall |  |  |  | 4 | [11 empty] | 7 |  |  | 28 109: 7; 28 110: 7; 28 111: 7; 28 112: 7
Start PD work |  |  |  | 4 | [10 empty] | 6 |  |  |  | 28 109: 4; 28 110: 2; 28 111: 2; 28 112: 6
Start APA work |  |  |  | 4 | [8 empty] | 8 | [5 empty] | 28 109: 4; 28 110: 6; 28 111: 8; 28 112: 8
Start CE work |  |  |  | 4 | [9 empty] | 12 |  |  |  |  | 28 109: 4; 28 110: 8; 28 111: 8; 28 112: 12
Start Cal work |  |  |  | 4 | [14 empty] | 28 109: 6; 28 110: 6; 28 111: 6; 28 112: 6
[12 empty] | Contactor |  |  | Mechanical |  | Electrical |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Contactor |  |  | CERN |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Electrical |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Net/Vent |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Surveyor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Welder |  |  |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Tech |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 16 | 16 | 18 | 18 | 18 | 18 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 14 | 12 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | CE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | PD |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 4 | 2 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia |  |  | HV |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 12 | 12 | 11 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Contractor | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I | [6 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 16 | 16 | 18 | 18 | 18 | 18 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 14 | 12 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Consortia | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 28 | 28 | 23 | 23 | 25 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | I&I |  |  | Electrical |  |  |  | 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 3; 16 61: 1.5; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0.5; 21 81: 1; 22 85: 0; 23 89: 1.5; 24 93: 0; 25 97: 0; 26 101: 1; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | I&I |  |  | Net/Vent |  |  |  | 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 2; 17 65: 2; 18 69: 0; 19 73: 0; 20 77: 0.5; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0.5; 26 101: 1.5; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | I&I |  |  | Surveyor |  |  |  | 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 1; 18 69: 2; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | I&I |  |  | Welder |  |  |  | 8 29: 0; 9 33: 3; 10 37: 3; 11 41: 3; 12 45: 3; 13 49: 1; 14 53: 3; 15 57: 3; 16 61: 3; 17 65: 3; 18 69: 3; 19 73: 3; 20 77: 3; 21 81: 3; 22 85: 3; 23 89: 1; 24 93: 1; 25 97: 1; 26 101: 0; 27 105: 0; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | I&I |  |  | Tech |  |  |  | 8 29: 6; 9 33: 6; 10 37: 6; 11 41: 6; 12 45: 8; 13 49: 7; 14 53: 10; 15 57: 10; 16 61: 17; 17 65: 17; 18 69: 17; 19 73: 17; 20 77: 17; 21 81: 17; 22 85: 17; 23 89: 13.5; 24 93: 8; 25 97: 8; 26 101: 9; 27 105: 8; 28 109: 0; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | Consortia |  |  | APA |  |  |  | 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 1; 27 105: 4; 28 109: 6.5; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | Consortia |  |  | CE |  |  |  | 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 1; 27 105: 4; 28 109: 8; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | Consortia |  |  | PD |  |  |  | 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 0; 27 105: 4; 28 109: 3.5; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0
[12 empty] | Consortia |  |  | HV |  |  |  | 8 29: 0; 9 33: 0; 10 37: 0; 11 41: 0; 12 45: 0; 13 49: 0; 14 53: 0; 15 57: 0; 16 61: 0; 17 65: 0; 18 69: 0; 19 73: 0; 20 77: 0; 21 81: 0; 22 85: 0; 23 89: 0; 24 93: 0; 25 97: 0; 26 101: 1; 27 105: 8; 28 109: 8; 29 113: 0; 30 117: 0; 31 121: 0; 32 125: 0; 33 129: 0; 34 133: 0; 35 137: 0; 36 141: 0; 37 145: 0; 38 149: 0; 39 153: 0; 40 157: 0; 41 161: 0; 42 165: 0; 43 169: 0; 44 173: 0

## SP1 Labor Force
Week 1
[9 empty] | Day 1 |  |  |  | Day 2 |  |  |  | Day 3 |  |  |  | Day 4 |  |  |  | Day 5 |  |  |  | Day 6 |  |  |  | Day 7
| Labor Force | [7 empty] | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2
| Task |  |  |  |  | Surv |  | Location | 6:00 | 11:00 | 15:00 | 20:00 | 6:00 | 11:00 | 17:00 | 22:00 | 6:00 | 11:00 | 17:00 | 22:00 | 6:00 | 11:00 | 17:00 | 22:00 | 6:00 | 11:00 | 17:00 | 22:00 | 6:00 | 11:00 | 17:00 | 22:00 | 6:00 | 11:00 | 17:00 | 22:00
|  | APA | CE | PD | HV | Cal | INT
| Photon Detector Integration | # FTE | # FTE | # FTE | # FTE | # FTE | # FTE
1 | Photon Detector Supervisors-1 per shift |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Photon Detector Scientist/Postdoc-1 per shift |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Test PD in scanner |  |  | 4 |  |  |  | cleanroom | 4 | 4 | [12 empty] | 4 | 4
4 | Rotate box to vertical & put on pallet move, into SAS, clean, and remove covers | 2 | [5 empty] | SAS | 2 |  |  |  | 2 |  |  |  | 2
5 | Clean, and remove covers and move APAs to PD integration area | 1 | [5 empty] | SAS |  | 1 |  |  |  | 1 |  |  |  | 1
6 | Install PD top APA and test-APA#1 |  |  | 4 |  |  |  | PD Area |  |  | 4 | 4
7 | Install PD Bottom APA and Test-APA #1 |  |  | 4 |  |  |  | PD Area |  |  |  |  | 4 | 4
8 | Install PD top APA and test-APA#2 |  |  | 4 |  |  |  | PD Area | [6 empty] | 4 | 4
9 | Install PD Bottom APA and Test-APA #2 |  |  | 4 |  |  |  | PD Area | [8 empty] | 4 | 4
10 | Install PD top APA and test-APA#3 |  |  | 4 |  |  |  | PD Area | [10 empty] | 4 | 4
11 | Install PD Bottom APA and Test-APA #3 |  |  | 4 |  |  |  | PD Area | [12 empty] | 4 | 4
| APA Consortia Supervisor/Scientist | 1 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CE Consortia Supervisor/Scientist |  | 1 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1
| CE Consortia Supervisor/Engineer |  | 1 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| I&I on the weekend | [5 empty] | 2 | [17 empty] | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2
| I&I-Cleanroom/SAS Cleaning | [5 empty] | 1 |  |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1
APA Prep in Cavern
1 | Rotate APA Frame and mount to cart. | 2 | [5 empty] | Cavern | 2 |  |  |  | 2 |  |  |  | 2
[7 empty] | 2 |  | 2 |  |  |  | 2 |  |  |  | 2
2 | Remove outer covers. Move APA Frame to SAS remove inner bags | 2 | [5 empty] | Cavern |  | 2 |  |  |  | 2 |  |  |  | 2
[7 empty] | 2 |  |  | 2 |  |  |  | 2 |  |  |  | 2
3 | Misc. cleanup of dunnage to surface | 2 | [5 empty] | Cavern | [12 empty] | 2 | 2
[7 empty] | 2 | [13 empty] | 2 | 2
Line # 1
1 | Move APA Bottom and top to APA Assembly frame | 2 | [5 empty] | line#1 | 2
[7 empty] | 3 |  | 3
2 | Connect PD Cables, test, connect linkage test and form APA doublet | 2 | [5 empty] | line#1 |  | 2
[7 empty] | 1 |  |  | 1
3 | APA wire tension, Install CR Boards, install bias voltage Hareness | 4 | [5 empty] | line#1 |  |  | 4 | 4 | 4 | 4
4 | Install CE FEBMs top and bottom APA |  | 4 |  |  |  |  | line#1 | [6 empty] | 4 | 4 | 4 | 4
5 | Move APA Doublet to cabling station and install cable trays |  | 4 | [15 empty] | 4
6 | Install top and bottom CE cables |  | 4 |  |  |  |  | line#1 | [11 empty] | 4
7 | CE Cable management/PD Cable |  | 4 |  |  |  |  | line#1 | [12 empty] | 4
8 | Test electronics warm +Bias test/PD test |  | 4 |  |  |  |  | line#1 | [13 empty] | 4 | 4
9 | Remove Protective panels move to front of Cold Box | 3 | [5 empty] | line#1 | [15 empty] | 3
[7 empty] | 1 | [16 empty] | 1
10 | Photogrammetry/survey | 1 | [5 empty] | line#1 | 1 | 1
[7 empty] | 2 |  | 2 | 2
11 | Move to cold box and cable |  | 2 |  |  |  |  | Cold Box #1 |  |  | 2 | 2
[7 empty] | 2 |  |  |  | 2 | 2
12 | Warm check APA and close box |  | 2 |  |  |  |  | Cold Box #1 |  |  |  |  | 2 | 2 | 2 | 2
13 | Cool down Cold Box |  | 2 |  |  |  |  | Cold Box #1 | [8 empty] | 2 | 2 | 2 | 2
14 | Cold test Cold Box |  | 2 |  |  |  |  | Cold Box #1 | [12 empty] | 2 | 2 | 2 | 2
15 | Warm up Cold Box |  | 2 |  |  |  |  | Cold Box #1 | [16 empty] | 2 | 2
16 | Move out of cold box and uncable, move to switchyard |  | 2 |  |  |  |  | Cold Box #1 | 2 | 2
[7 empty] | 2 |  | 2 | 2
Line # 2
1 | Move APA Bottom and top to APA Assembly frame | 2 | [5 empty] | line#2 |  |  |  |  | 2
[7 empty] | 3 | [5 empty] | 3
2 | Connect PD Cables, test, connect linkage test and form APA doublet | 2 | [5 empty] | line#2 | [5 empty] | 2
[7 empty] | 3 | [6 empty] | 3
3 | APA wire tension, Install CR Boards, install bias voltage Hareness | 4 | [5 empty] | line#2 | [6 empty] | 4 | 4 | 4 | 4
4 | Install CE FEBMs top and bottom APA |  | 4 |  |  |  |  | line#2 | [10 empty] | 4 | 4 | 4 | 4
5 | Move APA Doublet to cabling station and install cable trays |  | 4 |  |  |  |  | line#2 | [14 empty] | 4
6 | Install top and bottom CE cables |  | 4 |  |  |  |  | line#2 | [15 empty] | 4
7 | CE Cable management/PD Cable |  | 4 |  |  |  |  | line#2 | 4
8 | Test electronics warm +Bias test/PD test |  | 4 |  |  |  |  | line#2 |  | 4 | 4
9 | Remove Protective panels move to front of Cold Box | 3 | [5 empty] | line#2 |  |  |  | 3
[7 empty] | 3 |  |  |  |  | 3
10 | Photogrammetry/survey | 1 | [5 empty] | line#2 |  |  |  |  | 1 | 1
[6 empty] | 2 | [6 empty] | 2 | 2
11 | Move to cold box and cable |  | 2 |  |  |  |  | Cold Box #2 | [6 empty] | 2 | 2
[7 empty] | 2 | [7 empty] | 2 | 2
12 | Warm check APA and close box |  | 2 |  |  |  |  | Cold Box #2 | [8 empty] | 2 | 2 | 2 | 2
13 | Cool down Cold Box |  | 2 |  |  |  |  | Cold Box #2
14 | Cold test Cold Box |  | 2 |  |  |  |  | Cold Box #2
15 | Warm up Cold Box |  | 2 |  |  |  |  | Cold Box #2 | [20 empty] | 2 | 2
16 | Move out of cold box and uncable, move to switchyard |  | 2 |  |  |  |  | Cold Box #2 |  |  |  |  | 2 | 2
[7 empty] | 2 | [5 empty] | 2 | 2
Line # 3
1 | Move APA Bottom and top to APA Assembly frame | 2 | [5 empty] | line#3 | [8 empty] | 2
[7 empty] | 3 | [9 empty] | 3
2 | Connect PD Cables, test, connect linkage test and form APA doublet | 2 | [5 empty] | line#3 | [9 empty] | 2
[7 empty] | 3 | [10 empty] | 3
3 | APA wire tension, Install CR Boards, install bias voltage Hareness | 4 | [5 empty] | line#3 | [10 empty] | 4 | 4 | 4 | 4
4 | Install CE FEBMs top and bottom APA |  | 4 |  |  |  |  | line#3 | 4 | 4 | [12 empty] | 4 | 4
5 | Move APA Doublet to cabling station and install cable trays |  | 4 |  |  |  |  | line#3 |  |  | 4
6 | Install top and bottom CE cables |  | 4 |  |  |  |  | line#3 |  |  |  | 4
7 | CE Cable management/PD Cable |  | 4 |  |  |  |  | line#3 |  |  |  |  | 4
8 | Test electronics warm +Bias test/PD test |  | 4 |  |  |  |  | line#3 | [5 empty] | 4 | 4
9 | Remove Protective panels move to front of Cold Box | 3 | [5 empty] | line#3 | [7 empty] | 3
[7 empty] | 3 | [8 empty] | 3
10 | Photogrammetry/survey | 1 | [5 empty] | line#3 | [8 empty] | 1 | 1
[6 empty] | 2 | [10 empty] | 2 | 2
11 | Move to cold box and cable |  | 2 |  |  |  |  | Cold Box #3 | [10 empty] | 2 | 2
[7 empty] | 2 | [11 empty] | 2 | 2
12 | Warm check APA and close box |  | 2 |  |  |  |  | Cold Box #3 | [12 empty] | 2 | 2 | 2 | 2
13 | Cool down Cold Box |  | 2 |  |  |  |  | Cold Box #3
14 | Cold test Cold Box |  | 2 |  |  |  |  | Cold Box #3
15 | Warm up Cold Box |  | 2 |  |  |  |  | Cold Box #3 | [24 empty] | 2 | 2
16 | Move out of cold box and uncable, move to switchyard |  | 2 |  |  |  |  | Cold Box #3 |  |  | 2 | 2
[7 empty] | 2 |  |  |  | 2 | 2
Cabling of TPC Electronics inside and top Cryostat
APA Pair #1
1 | Move APA to cryostat-Position | [5 empty] | 3 | Cryostat |  |  | 3 | 3
2 | Final Cable-Cryostat-in & out |  | 2 |  |  |  |  | Cryo |  |  |  |  | 2 | 2 | 2 | 2
[7 empty] | 2 | [5 empty] | 2 | 2 | 2 | 2
3 | DAQ Test/seal flange/He Leak check |  | 2 |  |  |  |  | Cryo | [8 empty] | 2 | 2
[7 empty] | 2 | [9 empty] | 2 | 2
CPA Pair#1
4 | Move CPA to cryostat-Position | [5 empty] | 3 | Cryo |  |  |  |  | 3 | 3
APA Pair #2
5 | Move APA to cryostat-Position | [5 empty] | 3 | Cryo | [6 empty] | 3 | 3
6 | Final Cable-Cryostat-in & out |  | 2 |  |  |  |  | Cryo | [8 empty] | 2 | 2 | 2 | 2
[7 empty] | 2 | [9 empty] | 2 | 2 | 2 | 2
7 | DAQ Test/seal flange/He Leak check |  | 2 |  |  |  |  | Cryo |  |  | 2 | 2
[7 empty] | 2 |  |  |  | 2 | 2
CPA Pair#1
8 | Move CPA to cryostat-Position | [5 empty] | 3 | Cryo | [8 empty] | 3 | 3
APA Pair #3
5 | Move APA to cryostat-Position | [5 empty] | 3 | Cryo | [10 empty] | 3 | 3
6 | Final Cable-Cryostat-in & out |  | 2 |  |  |  | 2 | Cryo | [12 empty] | 2 | 2 | 2 | 2
[7 empty] | 2 | [13 empty] | 2 | 2 | 2 | 2
7 | DAQ Test/seal flange/He Leak check |  | 2 |  |  |  |  | Cryo | 2 | 2
[7 empty] | 2 |  | 2 | 2
8 | I&I Crew-Riggers/techs Top of Cryostat | [5 empty] | 2 | Top Cryo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| HV Consortia Supervisor/Scientist-1 per shift |  |  |  | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CPA Pair #1
1 | Bring CPA & FC boxes in | [5 empty] | 2 | Mat Han |  | 2
2 | Lift CPA1A and bolt to frame |  |  |  | 4 |  |  | CPA 1 | 4 | 4
3 | Lift CPA1b and bolt to frame |  |  |  | 4 |  |  | CPA 1 |  |  | 4 | 4
4 | Add Field Shaping at profiles |  |  |  | 4 |  |  | CPA 1 |  |  |  |  | 4
5 | Add disfuser and Top FC |  |  |  | 4 |  |  | CPA 1 | [5 empty] | 4
CPA Pair #2
1 | Bring CPA & FC boxes in | [5 empty] | 2 | Mat Han |  |  |  |  | 2
2 | Lift CPA2A and bolt to frame |  |  |  | 4 |  |  | CPA 2 | [6 empty] | 4 | 4
3 | Lift CPA2b and bolt to frame |  |  |  | 4 |  |  | CPA 2 | [8 empty] | 4 | 4
4 | Add Field Shaping at profiles |  |  |  | 4 |  |  | CPA 2 | [10 empty] | 4
5 | Add disfuser and Top FC |  |  |  | 4 |  |  | CPA 2 | [11 empty] | 4
Build FC and End Walls
1 | Bring in Frames, profiles, electrical | [5 empty] | 2 | Mat Han |  |  |  | 2
2 | Build FC Frame |  |  |  | 2 |  |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2
3 | Install Profiles and test |  |  |  | 2 | [5 empty] | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2
4 | Clean, removal of boxes, repair and test |  |  |  | 4 | [15 empty] | 4 | 4 | 4 | 4
[8 empty] | Total HV FTE | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| APA Consortia | [7 empty] | 8 | 7 | 5 | 8 | 12 | 11 | 5 | 8 | 12 | 11 | 5 | 5 | 7 | 7 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CE Consortia | [7 empty] | 14 | 14 | 16 | 12 | 12 | 12 | 16 | 12 | 14 | 14 | 18 | 18 | 16 | 16 | 20 | 16 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0
| PD Consortia | [7 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HV Consortia | [7 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Calibration & Survey | [7 empty] | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&I Core Technicians | [7 empty] | 13 | 13 | 12 | 17 | 16 | 14 | 10 | 13 | 14 | 14 | 10 | 10 | 8 | 8 | 7 | 8 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0
[8 empty] | Total | 48 | 47 | 46 | 50 | 55 | 52 | 44 | 46 | 55 | 54 | 46 | 46 | 44 | 44 | 41 | 41 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0
[9 empty] | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2
[9 empty] | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday |  |  |  | Saturday |  |  |  | Sunday
Inside and Top Cryostat
| HV Consortia | [7 empty] | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
| CE Consortia | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2
| Inside I&I Crew-Riggers/technicians | [7 empty] | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 5 | 5 | 4 | 4 | 4 | 4
| I&I Top of the Cryostat | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Inside and top Cryostat-Total | [7 empty] | 6 | 6 | 9 | 9 | 11 | 11 | 9 | 9 | 13 | 13 | 9 | 9 | 10 | 10 | 8 | 8
Average FTE
| FTE 4910 level | Day Shift |  | Night Shift |  | Weekend
| APA Consortia | 9.375 |  | 5.125
| CE Consortia | 14 |  | 16 |  | 3
| PD Consortia | 6 |  | 6
| HV Consortia | 7 |  | 7
| Calibration & Survey | 1 |  | 0
| I&I Crew-Riggers/technicians | 12.5 |  | 10.875 |  | 2
| FTE 4910 level-Total | 49.875 |  | 45 |  | 5
Inside & Top Cryostat
| HV Consortia | 1 |  | 0
| CE Consortia | 2.5 |  | 2
| I&I Crew-Riggers/technicians | 6.5 |  | 6.75
| Inside & Top Cryostat-Total | 10 |  | 8.75
| Deployment of Drift Volume-In Cryostat | [7 empty] | Row 1 | [7 empty] | Row 2 | [7 empty] | Row 3
Drift Volume 1
1 | Remove floor, clean, install temp, test |  |  |  |  | 1 |  | Cryo | 1 | 1 | [6 empty] | 1 | 1 | [6 empty] | 1 | 1
[7 empty] | 3 |  | 3 | [7 empty] | 3 | [7 empty] | 3
2 | Deploy T&B FC Drift Volume 1 | [5 empty] | 3 | Cryo |  | 3 | [7 empty] | 3 | [7 empty] | 3
3 | Final Test and HV Elec Connections |  | 2 |  | 2 |  |  | Cryo |  |  | 2 | 2 | [6 empty] | 2 | 2 | [6 empty] | 2 | 2
Drift Volume 2 & 3
4 | Remove floor, clean, install temp, test |  |  |  |  | 1 |  | Cryo |  |  |  |  | 1 | 1 | [6 empty] | 1 | 1 | [6 empty] | 1 | 1
[7 empty] | 3 | [5 empty] | 3 | [7 empty] | 3 | [7 empty] | 3
5 | Deploy T&B FC Drift Volume 2 | [5 empty] | 3 | [6 empty] | 3 | [7 empty] | 3 | [7 empty] | 3
6 | Final Test and HV Elec Connections |  | 2 |  | 2 |  |  | Cryo | [6 empty] | 2 | 2 | [6 empty] | 2 | 2 | [6 empty] | 2 | 2
4 | Remove floor, clean, install temp, test |  |  |  |  | 1 | [6 empty] | 1 | 1 | [6 empty] | 1 | 1 | [6 empty] | 1 | 1
[7 empty] | 3 | [5 empty] | 3 | [7 empty] | 3 | [7 empty] | 3
5 | Deploy T&B FC Drift Volume 3 | [5 empty] | 3 | Cryo | [5 empty] | 3 | [7 empty] | 3 | [7 empty] | 3
6 | Final Test and HV Elec Connections |  | 2 |  | 2 |  |  | Cryo | [6 empty] | 2 | 2 | [6 empty] | 2 | 2 | [6 empty] | 2 | 2
Drift Volume 4
1 | Remove floor, clean, install temp, test |  |  |  |  | 1 |  | Cryo | 1 | 1 | [6 empty] | 1 | 1 | [6 empty] | 1 | 1
[7 empty] | 3 |  | 3 | [7 empty] | 3 | [7 empty] | 3
2 | Deploy T&B FC Drift Volume 1 | [5 empty] | 3 | Cryo |  | 3 | [7 empty] | 3 | [7 empty] | 3
3 | Final Test and HV Elec Connections |  | 2 |  | 2 |  |  | Cryo |  |  | 2 | 2 | [6 empty] | 2 | 2 | [6 empty] | 2 | 2
Weekend
| Deployment-In/Top Cryostat | Day Shift |  | Night Shift |  | Day Shift |  | Night Shift
| APA Consortia | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CE Consortia | 0 |  | 4 |  | 0 |  | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4
| PD Consortia | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HV Consortia | 0 |  | 4 |  | 0 |  | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4
| Calibration & Survey | 2 |  | 0 |  | 2 |  | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0
| I&I Crew-Riggers/technicians | 6 |  | 0 |  | 6 |  | 0 | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0
| Total FTE | 8 |  | 8 |  | 8 |  | 8

## SP1-Deployment
Months |  |  | 28 |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  | 33 |  |  |  | 34 |  |  |  | 35 |  |  |  | 36 |  |  |  | 37 |  |  |  | 38 |  |  |  | 39 |  |  |  | 40
Week | -2 | -1 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111
P6 Schedule | -1: Endwall 1; 29 65: Row 1-2; 30 69: Row 3-4; 30 72: Row 5-6; 31 75: Row 7-8; 32 78: Row 9-10; 33 81: Row 11-12; 33 84: Row 13-14; 34 87: Row 15-16; 35 90: Row 17-18; 36 93: Row 19-20; 36 96: Row 21-22; 37 99: Row 23-24; 38 102: Row 25; 39 105: End Wall 2
TASK
End Wall | -2: EW Prep; 28 61: End Wall 1
APA Pair 1 | 28 64: APA 1; 29 66: CB1
APA Pair 2 | 29 65: APA 2; 29 67: CB2
APA Pair 3 | 29 66: APA 3; 29 68: CB3
Row 1 APA | 29 67: Row 1
APA Pair 4 | 29 66: APA 4; 29 68: CB1
APA Pair 5 | 29 67: APA 5; 30 69: CB2
APA Pair 6 | 29 68: APA 6; 30 70: CB3
Row 2 APA | 30 69: Row 2
APA Pair 7 | 29 68: APA7; 30 69: CB1
APA Pair 8 | 30 69: APA8; 30 70: CB2
APA Pair 9 | 30 70: APA9; 30 71: CB3
Row 3 APA | 30 71: Row3
APA Pair 10 | 30 69: AP10; 30 70: CB1
APA Pair 11 | 30 70: AP11; 30 71: CB2
APA Pair 12 | 30 71: AP12; 30 72: CB3
Row 4 APA | 30 72: Row4
APA Pair 13 | 30 70: AP13; 30 71: CB1
APA Pair 14 | 30 71: AP14; 30 72: CB2
APA Pair 15 | 30 72: AP15; 31 73: CB3
Row 5 APA | 31 73: Row5
APA Pair 16 | 30 71: AP16; 30 72: CB1
APA Pair 17 | 30 72: AP16; 31 73: CB2
APA Pair 18 | 31 73: AP18; 31 74: CB3
Row 6 APA | 31 74: Row6
Row 7 APA | bar: 31 75
Row 8 APA | bar: 31 76
Row 9 APA | bar: 32 77
Row 10 APA | bar: 32 78
Row 11 APA | bar: 32 79
Row 12 APA | bar: 32 80
Row 13 APA | bar: 33 81
Row 14 APA | bar: 33 82
Row 15 APA | bar: 33 83
Row 16 APA | bar: 33 84
Row 17 APA | bar: 34 85
Row 18 APA | bar: 34 86
Row 19 APA | bar: 34 87
Row 20 APA | bar: 34 88
Row 21 APA | bar: 35 89
Row 22 APA | bar: 35 90
APA Pair 67 | 35 90: AP67; 35 91: CB1
APA Pair 68 | 35 91: AP68; 35 92: CB2
APA Pair 69 | 35 92: AP69; 36 93: CB3
Row 23 APA | bar: 36 93
APA Pair 70 | 35 91: AP70; 35 92: CB1
APA Pair 71 | 35 92: AP71; 36 93: CB2
APA Pair 72 | 36 93: AP72; 36 94: CB3
Row 24 APA | 36 94: R-24
APA Pair 73 | 35 92: APA 73; 36 94: CB1
APA Pair 74 | 36 93: APA 74; 36 95: CB2
APA Pair 75 | 36 94: APA 75; 36 96: CB3
Row 25 APA | 36 96: Row-25
6 weeks of float
Row 1 CPA | bar: 29 67 to 29 68
Row 2 CPA | bar: 30 69
Row 3-4 CPA | bar: 30 70
Row 5 CPA | bar: 30 71
Row 6 CPA | bar: 30 72
Row 7-8 CPA | bar: 31 73
Row 9 CPA | bar: 31 74
Row 10 CPA | bar: 31 75
Row 11-12 CPA | bar: 31 76
Row 13 CPA | bar: 32 77
Row 14 CPA | bar: 32 78
Row 15-16 CPA | bar: 32 79
Row 17 CPA | bar: 32 80
Row 18 CPA | bar: 33 81
Row 19-20 CPA | bar: 33 82
Row 21 CPA | bar: 33 83
Row 22 CPA | bar: 33 84
Row 23-24 CPA | bar: 34 85
Row 25 CPA | 37 97: EW Prep
Deploy | 38 104: 6 weeks of float
Row 1-2 | bar: 34 86
Row 3-4 | bar: 34 87
Row 5-6 | bar: 34 88
Row 7-8 | bar: 35 89
Row 9-10 | bar: 35 90
Row 11-12 | bar: 35 91
Row 13-14 | bar: 35 92
Row 15-16 | bar: 36 93
Row 17-18 | bar: 36 94
Row 19-20 | bar: 36 95
Row 21-22 | bar: 36 96
Row 23-24 | bar: 37 97
Row 25 | bar: 37 98
End Wall | 37 97: EW Prep; 37 99: End Wall 2

## AR Schedule
2020
| March | April | May | June | July | August | September | October |  | November | December
ProtoDUNE 2 Trial Assembly-Phase 1
Vic and Ken, protoype latches and hangers
Order materials/fabricate Module 0 components
Module 0 ProtoDUNE 2 FC delivered
Module 0 ProtoDUNE 2 CPA,EW delivered
LSU Build End Wall
UAT/SBU Build FC
First ProtoDUNE 2 installation tests
Remove ProtoDUNE Support structure
ProtoDUNE 2 Trial Assembly-Phase 2- Upside down APA
Design DSS Steel Support/Platform System-Barr
Review design, bid documents, procure
Fabricate/Install DSS steel support structure
Initial Test DSS
APA Shipping Frame Tests: 4 weeks
Ship APA Box Plus APAs to SURF- 3-4 Weeks
Module 0 HV TPC components fabricated/delivered
First Row installation/deployment tests
25th Row Installation tests
Revised installation tooling and TPC
First Row installation/deployment tests
25th Row Installation/Deployment tests
Trial Assembly Phase 3
Planning, designing, review & procure
Installation of mechanical DSS feed thru
Installation of mechanical Cable feed thru
First Row installation/deployment tests
25th Row Installation/Deployment tests
ProtoDUNE-II CERN | [8 empty] | Ash River Average 2 FTE
Prep tools, documentation, training
Disassembly TCO drift volume
Open TCO
2021
| January | February | March | April | May | June | July | August |  | September | October | November | December
Revised installation tooling and TPC
First Row installation/deployment tests
25th Row Installation/Deployment tests
Trial Assembly Phase 3
Planning, designing, review & procure
Installation of mechanical DSS feed thru
Installation of mechanical Cable feed thru
First Row installation/deployment tests
25th Row Installation/Deployment tests
ProtoDUNE-II CERN |  |  |  | Ash River Average 2 FTE | [5 empty] | Ash River Average 2 FTE
Open TCO
Remove ProtoDUNE-SP TPC
Prep Cleanroom
Clean Cryostat/Cleanroom
Modifiy and install CPAs
Integrate, test & install APA 1-2
Integrate, test & install APA 3-4
Install EW
Close TCO-2022