## Slide 1: Photon Detector System Cost and Schedule Status
David Warner
LBNF/DUNE-US Directors Review
18-19 June 2020

## Slide 2: Outline
Distribution of Responsibility across Consortium
Cost Summary (M&S)
Cost Summary (Labor)
Brief Basis of Estimate Narrative
Risks
Schedule Summary
  Schedule/Milestones
  Covid delays
  ProtoDUNE Plans
Summary

## Slide 3: Distribution of Responsibility Across Consortium
Component | Description | Quantity (per 10 kT) | Primary Responsibility
Detector support | Support rails, electrical connectors, cables | 10 per APA. 1,500 total | DUNE-US
Light collector modules | X-ARAPUCA modules (frames, filters, assembly) | 10 per APA. 1,500 total | Brazil
Photosensors | 6X6mm2 SiPMs | 192 per module. 288,000 total | Italy, Spain, Czech Rep.
Cold electronics | Photosensor ganging (6X SiPM passive, 8X active) | 1 per module 1,500 total | Italy, Spain
Warm electronics | DAPHNE system. Based on Mu2e ultrasound ADC | 1 unit per APA 150 total | Colombia, Peru, DUNE-US
Calibration and monitoring | Pulsed UV flasher with CPA mounted diffusers | 204 diffusers, 18 control modules | DUNE-US
Installation and integration | Module insertion, installation in cryostat |  | DUNE-US, Brazil, Europe

## Slide 4: Cost Summary (M&S)
DOE
International
Total M&S, PDS Detector 1 10.2 M$
Note: International validation/development phase not included
P6 cost book data are separated into DOE and non-DOE (international in this case)
Contributions. Also, Detector 2 in included in international numbers.

## Slide 5: Cost Summary (Labor)
DOE
International
Total Labor (Hours), PDS Detector 1 110k hours
Note: International validation/development phase not included
P6 cost book data are separated into DOE and non-DOE (international in this case)
Contributions. Also, Detector 2 in included in international numbers.

## Slide 6: Basis of Estimate Summary
Photosensors and Cold Electronics:
  M&S based on vendor estimates,
  Labor based on ProtoDUNE 1 and prototype development.
Modules:
  M&S based on vendor quotations for all major components.
  Labor based on ProtoDUNE module assembly and other time and motion studies.
DAPHNE:
  M&S based on vendor quotes for initial prototype components.
  Labor based on engineering estimates.
Monitoring System
  M&S based on vendor quotations and ProtoDUNE 1 costs.
  Labor based on engineering estimates.
Rails/Cables
  M&S based on vendor quotations fro all components.
  Labor based on time and motion studies assembling prototypes at CSU.

## Slide 7: Schedule Summary (Milestones)
Note: 1 year float following PD
module assembly before installation

## Slide 8: ProtoDUNE-2 plans
40 “Module 0” PD modules
  Single- and double-sided modules
  Two candidate SiPMs (down-select following ProtoDUNE 2)
“Module 0” readout chain
  Cables/connectors/flanges
  Cold amplifiers
  DAPHNE warm readout electronics
  DAQ interface firmware
“Module 0” Monitoring system
  Single LED control unit (modified SSP)
  8 diffusers
  Final candidate flanges, fibers
Will provide final validation for PRR for entire PD system

## Slide 9: PD Rail/Cable System Fabrication
PD rails and cables are mounted inside the APA frames prior to TPC wire wrapping.
This requires ProtoDUNE-ready (post FDR) rail delivery to Daresbury in Q4 2020.
  Special FDR for PD rails/cables Q3 2020.
  Greatly increases necessity of re-opening rail fabrication facilities.
  Long lead time item (Custom cable) already in hand.
    Good News! CSU assembly facility began
    re-opening 6/18/20! Impact on schedule
    will be evaluated and schedules updated

## Slide 10: Impact of COVID-19
Lab work stopped at nearly all national laboratories / universities worldwide in March 2020.
Activities stopped / delayed
  PD/APA cold integration testing at PSL halted
  Light collector module (X-ARAPUCA) tests at ICEBERG, Milano test beds halted
  Warm electronics (DAPHNE) prototypes fabrication delayed
  Module mechanical prototyping/production preparation at UNICAMP Brazil delayed.
  Impact of these delays on the ProtoDUNE 2 schedule not yet critical, but failure to restart by late June 2020 may begin to impact our schedule
Some progress continuing however
  Module/rail installation tests at Ash River satisfactorily completed
  Cable bundle installation in APA frames at PSL satisfactorily completed
  Sample photosensor fabrication/delivery continuing
    Hamamatsu photosensors delivered to Milano late April 2020
    FBK photosensors being delivered to Milano now

## Slide 11: Plans for Restart
Some European labs/universities reopening on a limited basis
  Photosensor testing beginning (Italy, Spain)
  X-ARAPUCA module (small prototypes) (Italy)
  Photosensor active ganging (cold testing) (Italy)
APA/PD cold interface testing at PSL progressing, albeit at a reduced rate
  Delayed by lack of PD rails, cables, test modules
Many US and Latin American institutions beginning to evaluate schedules for re-opening, but the prognosis is unclear.
Priority Validation Items (Critical Path for FDR, ProtoDUNE):
  Photosensors: Progressing, but at slowed pace
  Warm electronics: Prototype module design fabrication continuing, should proceed through delivery of fabricated modules in Summer 2020. At that point availability of US, Latin American, European testing sites becomes critical
  PD/DAQ interface: PD/DAQ interface tests scheduled for Q3 2020 are critical to ProtoDUNE 2 electronics development. Requires re-opening of DAQ testing sites
  CERN cold box test: Q1 2020(?)-- Critical “Vertical slice” test of electronics system
    NOTE: 10 mechanical models/cables, ~ 10 SIPM-instrumented supercells initially, more supercells in spring.
  Light collector module prototype components can be ordered from commercial sites in the US, Brazil, Spain but fabrication delays hindering APA testing.
Summary: Situation not yet critical, but will rapidly deteriorate if reopening of US, Latin American sites delayed past June 2020

## Slide 12: Summary
DUNE PD scope, schedule, and costs well understood.
International PD consortium solidly established.
FDR and ProtoDUNE Fabrication beginning Q4 2020.
ProtoDUNE 2 experience will provide critical validation for PRR
Detector 1 PD module fabrication begins Q1 2022, ends Q4 2024
First modules delivered to SURF Q4 2023 , Installation begins Q1 2026
Last modules delivered so SURF Q2 2025, Installation ends Q1 2027
Approximately 1 year float in production schedule
  Critical exception: Rails & Cables! Initial deliveries Q4 2020