## Slide 1: Photon Detector System Installation Plans
David Warner
LBNF/DUNE-US Directors Review
18-19 June 2020

## Slide 2: Outline
Installation task responsibility
Rail/Cable Installation
Module Installation
Labor Summary
QC testing/data maintenance
Schedule
Summary

## Slide 3: PD installation task responsibility (i)
PD consortium personnel
  Module Installation
  DAPHNE installation & checkout
  Monitoring system LED driver installation & checkout
  Power supply
  Warm fiber/signal connections
  Monitoring of cold box checkout
  Supervision of other PD related tasks
  Bi-weekly dark operation in cryostat
  Supervision of all PD-related installation tasks
APA consortium personnel
  Installation of rails/cables into APAs (with PD supervision)
  Joining of upper/lower APA PD readout cables

## Slide 4: PD installation task responsibility (ii)
JT-HV consortium tasks
  Mounting of diffusers to CPAs underground
  Routing fibers to top of CPAs during installation
TPC consortium personnel
  Connection of PD cables in cold box test
  Connection of cables in cryostat to from APA to flange
I&I support personnel
  Monitoring system fiber routing on DSS
  Monitoring system fiber junction during CPA installation
  Support for cryostat signal cabling connections
  Communication fiber routing
  Power supply cable routing

## Slide 5: Rail/Cable Installation
Rails and internal cables will be installed during the APA frame assembly prior to wire wrapping.
Performed by APA personnel
Procedures generated by and progress monitored by PD personnel
Rail Alignment fixturing prototypes

## Slide 6: Module Installation (i)
Pre-installation inspection of modules includes:
  Visual inspection of module, including critical dimension check and photography
  LED scanner check-out (as in ProtoDUNE 1)
PD module scanner used in ProtoDUNE 1.
Will increase capacity to 5 modules at a time.

## Slide 7: Module Installation (ii)
Modules are self-fixturing. No external tooling is needed to install them
One person can safely handle a module (~3kg), however 2 are optimal for installation

## Slide 8: Module Installation (iii)
Module are installed into APA frames before they are removed from the transport frame.
Two two-person lifts are used to lift installation teams to appropriate height. Modules installed by hand.

## Slide 9: Module Installation Tool
Module fixed into APA frame
With two captive screws
(not shown)
Torque wrench will be used
M4 captive screw here

## Slide 10: Post-installation check-out
Automated module connector test box hooked to cables prior to module installation.
  Visible during installation from person lift.
  Visual indicator (green light) indicates successful connection & correct module orientation.
  Same style of apparatus used during upper-lower APA connection, and during APA installation into cryostat.

## Slide 11: Installation labor force
Two PD shifts per day (10 hours each), 4 days/week
Each PD installation team consists of:
  1 post-doc
  1 technician/engineer
  2 students
This labor force will be a combination of US, Latin American and European personnel, with a minimum requirement of 2 post docs, 2 technicians, and 4 students at all times.
  Expressions of interest from many points
  We hope to keep at least one additional post-doc and one additional student to assist with electronics installation, supervise other installation steps, participate in bi-weekly TPC slice checkout, and fill in additional hands where necessary.
A faculty-level responsible person (not necessarily on-site) will provide supervision of installation.
1 year duration

## Slide 12: QC checks following module installation
Upper/lower APA connection continuity
Cold box operation
Post cryostat installation cable continuity checkout
Post DAPHNE installation checkout
Bi-weekly checkout with monitoring system

## Slide 13: Bi-Weekly PD operation in darkened cryostat
A TPC detector slice (6 APAs, two CPA planes) will be installed every two weeks.
It is planned to darken the cryostat on the weekend shift immediately following the completion of a row to allow an operational test (warm) of the installed PD modules.
This plan is included in the Installation/PDS interface control document.
DAPHNE and monitoring system electronics will be installed prior to installation of a TPC slice, to facilitate this test.
2 PD personnel will be required for this test beyond the standard 4-day workweek (an additional 10 hour shift is allocated).

## Slide 14: Summary
Advances in module design and cabling have allowed for significant reductions in the required person power for module installation over ProtoDUNE 1
We understand the steps necessary for installing the PD system and the resources needed
QC steps during installation are planned and based on ProtoDUNE 1 (with improvements!)
The TCP dark-cryostat test represents a significant opportunity to address any problems during installation
Installation plans will advance prior to the FDR.