## Slide 1: Questions
Q1 Please present the schedule for transport box design effort, final review, and production including the prototyping process at Ash River and SURF that would be required. When does a shipping box need to be available to be sent to CERN. Include in this schedule the plan for developing a QC-plan, and any installation/use/HA documents required for certifying its use in the prototyping?
Q2 Please present the resources budgeted and plans for the remaining engineering.
Q3 What is the plan for developing the QC-plan, and what is the schedule for the testing and certifying for use in the prototyping? When must APAs be shipped to CERN for Cold Box Testing (Q1 FY20201?)
Q4 Do you have a list of documentation that needs to be drafted and approved before the boxes can be used at CERN, SURF, and Ash River.
Q7 Please present a brief summary of the transport box BOE. (This should be done last after the other questions have been addressed.)

## Slide 2: The APA Consortium plan
We are presenting a technically limited schedule, still subject to delays caused by COVID-19 and uncertainties in funding in US
The plan:
  Start construction of a pre-production APA in UK and a pre-production APA in US in October
  One would be a “top” APA and the other a “bottom” APA.
  Ship to the two APAs to CERN using Protodune-style shipping boxes and perform integration tests with CE and PDS and cold box tests (early 2021)
  If OK, use them in ProtoDUNE-II
  Plan to start of APA production in UK with 4 winding machines in March
  The first DUNE transport box needed in UK to ship the two additional APAs (top/bottom pair) for ProtoDUNE-II in late spring 2021

## Slide 3: The transport box plan

## Slide 4: Manpower resources for shipping box
50% of Peter Sutcliffe (ME) in UK
100% of George Stavrakis (ME) in UK
25% of Gwenn Mouster (ME) in UK
25% of David Payne (Phys.) in UK
Jeff Nelson (Phys.) + Machinist availability at W&M
  $46.9k APA Shipping box prototype
  $6.4k APA Vertical cart prototype
PSL personnel for Ash River tests
Ang Lee (ME) at Fermilab for FEA analyses, 1.5 months, to be agreed by TC

## Slide 5: List of documentation
Final drawings and engineering notes for the APA shipping box and the APA carts
  Approved as appropriate by TC/Compliance Office
Formal BTH/ASME certification for the APA shipping box by certified manufacturer
Detailed test plan for Ash River tests
  List of materials with drawings and weight specifications
  Unpacking and handling instructions
  Approval by DUNE ES&H/U. Minnesota
  Hazard analysis documentation
Detailed test plan for SURF tests
  List of materials with drawings and weight specifications
  Unpacking and handling instructions
  Approval by DUNE ES&H/SDSTA
  Hazard analysis documentation
  Critical lift documentation
  No previous experience of the Consortium with working at SURF
Detailed procedure for handling the APA shipping box and for extraction of APAs
  List of materials with drawings and weight specifications
  Unpacking and handling instructions
  Approval by DUNE ES&H/CERN NP/HSE
  Hazard analysis documentation