## 10Year Plan-V09-Sep-2009
Proj # | Programs/Projects | Group | Validation Lead | Email | Phone# | FY08 | FY09 | FY10/Q1 | FY10/Q2 | FY10/Q3 | FY10/Q4 | FY11/Q1 | FY11/Q2 | FY11/Q3 | FY11/Q4 | FY12/H1 | FY12/H2 | FY13/H1 | FY13/H2 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19
1 | Tevatron | A1 | Ron Moore | ronmoore@fnal.gov | 6466
2 | Tevatron Decommissioning | A2 | Paul Czarapata | pcceed@fnal.gov | 3106 | [10 empty] | Cold Standby |  |  |  | Decommissioning
3 | Main Injector | A3 | Ioanis Kourbanis | ioanis@fnal.gov | 4423
4 | Linac and Booster | A3 | Eric Prebys | prebys@fnal.gov | 8369
5 | PBar | A3 | Keith Gollwitzer | gollwitzer@fnal.gov | 8282 | [18 empty] | for mu2e | for mu2e
6 | Recycler | A3 | Paul Derwent | derwent@fnal.gov | 8520
7 | Booster Neutrino Beam | A3 | Craig Moore | cmoore@fnal.gov | 2251 | [13 empty] | MicroBooNE
8 | NuMI | A3 | Craig Moore | cmoore@fnal.gov | 2251 | [13 empty] | NOvA
10 | LARP | A4 | Eric Prebys | prebys@fnal.gov | 8369
11 | LASF | A4 | David McGinnis (TBC) | mcginnis@fnal.gov | 2789
12 | LHC Phase 1 Upgrade (APUL) | A4 | Mike Lamm Sandor Feher | lamm@fnal.gov fehers@fnal.gov | 4098 2240 |  |  |  | CD-1 | CD-2 | CD-3a | CD-3b
13 | LHC Phase 2 Upgrade | A4 | Mike Lamm Sasha Zlobin Giorgio Ambrosio | lamm@fnal.gov zlobin@fnal.gov giorgioa@fnal.gov | 4098 8192 2297
14 | Testbeam | A3 | Erik Ramberg | ramberg@fnal.gov | 5731, 2460
15 | Project X | A5 | Stephen Holmes | holmes@fnal.gov | 3988 | [5 empty] | CD-0 |  |  |  |  | CD-1 (Q1) |  |  | CD-2 (Q3) |  | CD-3 (Q1)
16 | SRF / ILCTA-NML | A6 | Rich Stanek | rstanek@fnal.gov | 3519
17 | ILC Accelerator | A6 | Rich Stanek | rstanek@fnal.gov | 3519
18 | HINS | A7 | Giorgio Apollinari | apollina@fnal.gov | 4641
19 | Other Projects - Mag Sys | A8 | Mike Lamm Sasha Zlobin | lamm@fnal.gov zlobin@fnal.gov | 4098 8192
20 | Generic Accelerator R&D including A0, muon collider | A7 | Vladimir Shiltsev Steve Geer | shiltsev@fnal.gov sgeer@fnal.gov | 5241 2395
21 | Accelerator Modeling | A7 | Panagiotis Spentzouris | spentz@fnal.gov | 4342/3266
22 | CDF | E1 | Michael Lindgren | mlindgre@fnal.gov | 8409 | [10 empty] | Analysis | Analysis | Analysis | Analysis | Analysis | Analysis | Analysis
23 | CDF Decommissioning | E2 | Phil Schlabach | schlabach@fnal.gov | 5037
24 | DZero | E1 | George Ginther | ginther@fnal.gov | 6337 | [10 empty] | Analysis | Analysis | Analysis | Analysis | Analysis | Analysis | Analysis
25 | Dzero Decommissioning | E2 | George Ginther | ginther@fnal.gov | 6337
26 | CMS Operations Detector, Software, Computing | E8 | Lothar Bauerdick | bauerdick@fnal.gov | 6804
27 | CMS Phase 1 Upgrade | E8 | Lothar Bauerdick | bauerdick@fnal.gov | 6804
28 | CMS Phase 2 Upgrade | E8 | Lothar Bauerdick | bauerdick@fnal.gov | 6804
29 | MiniBooNE | E3 | Stephen Brice | sbrice@fnal.gov | 8748 | [6 empty] | Analysis | Analysis | Analysis | Analysis | Analysis | Analysis
30 | SciBooNE | E3 | Stephen Brice | sbrice@fnal.gov | 8748 |  | Analysis | Analysis | Analysis | Analysis | Analysis
31 | MicroBooNE | E3 | Cat James | cjames@fnal.gov | 2287 |  | CD-0 (Q4) | CD-1 | CD-2 |  |  | CD-3 | [9 empty] | Analysis | Analysis
32 | MINOS | E3 | Steve Brice | sbrice@fnal.gov | 2262 | [11 empty] | Analysis | Analysis | Analysis | Analysis
33 | MINERvA | E3 | Deborah Harris | dharris@fnal.gov | 4545 | CD-3b |  |  | CD-4 | [7 empty] | shutdown | shutdown |  |  | Analysis | Analysis | Analysis
34 | NOvA | E4 | John Cooper | jcooper@fnal.gov | 2235 | CD-2 | CD-3a | CD-3b
35 | LBNE | E6 | Gina Rameika | rameika@fnal.gov | 2262 |  | CD-0 (Q4) |  |  |  |  | CD-1 |  |  |  |  | CD-2 (Q3) |  |  | CD-3 (Q1)
37 | Mu2e | E7 | Ron Ray | rray@fnal.gov | 8090 |  | CD-0 (Q4) |  |  |  | CD-1 |  |  | CD-2 |  |  |  | CD-3 (Q1)
39 | DES | E9 | Brenna Flaugher | brenna@fnal.gov | 2934 | CD-3a
45 | Advanced Computing R&D |  | Ruth Pordes | ruth@fnal.gov | 3921
46 | Lattice QCD | T1 | Jim Simone | simone@fnal.gov | 3748
47 | Theory - Particle Physics | T1 | Chris Hill | hill@fnal.gov | 4301
48 | Theory - Particle Astrophysics | T1 | Albert Stebbins | stebbins@fnal.gov | 3663
49 | Education |  | Marge Bardeen | mbardeen@fnal.gov | 2031
50 | Programmatic Support (Direct) |  | Division/Section Rep*
51 | Other Projects |  | Division/Section Rep*
52 | Other Support (Direct) |  | Division/Section Rep*
53 | Division Management and Support (Direct) |  | Division/Section Rep*
54 | Indirect Support |  | Division/Section Rep*
55 | Programs/Projects Independent |  | Division/Section Rep*
New Buildings
60 | High Performance Computing Building |  | Vicky White | white@fnal.gov | 3936
| IARC |  | Bob Kephart | kephart@fnal.gov | 3135
SLI
61 | Utilities Upgrade |  | Randy Ortgiesen | ortgiesen@fnal.gov | 6288 |  |  | CD-0 |  |  |  | CD-1 |  | CD-2 |  | CD-3 (Q1)
63 | Industrial Facilities Consolidation |  | Randy Ortgiesen | ortgiesen@fnal.gov | 6288
ARRA
GPP
Advanced Tech R&D Augment
Small Scale Initiatives
| Proton Research (small projects) |  | Mike Lindgren | mlindgre@fnal.gov | 8409
ATLAS
g-2
Drell-Yan
Kaon
| Generic Detector R&D (All KA15) |  | Peter Wilson | pjw@fnal.gov | 2156
Core & Infrastructue
Sensors
Detector Systems
DAQ & Computing
| FCPA Experimental Initiatives (all KA13 experiments) |  | Dan Bauer | bauer@fnal.gov | 4771
CDMS
COUPP
SDSS
Pier Auger
Holographic Interferometry
GammeV
QUIET CMB experiment
21 cm baryon acoustic oscillations
Liquid Argon - dark matter
Other dark matter - CCDs, ACTs
Other surveys - LSST, low-noise CCDs
Other axions - Solid Xenon, Chameleons
Other dark energy
JDEM
Projects not included
DUSEL Detector Phase 2 for the final detector
mu2e Detector Phase 2 for Project X
1 ton scale Dark Matter Detector
Color Codes
Fully Operating
Stanby/Decommissioning
Construction
R&D
Division/Section/Center Validation Lead
| AD - Paul Czarapata |  |  | pcceed@fnal.gov | 3106
| APC - Vladimir Shiltsev |  |  | shiltsev@fnal.gov | 5241
| BSS - Dave Carlson |  |  | carlson@fnal.gov | 8998
| CPA - Craig Hogan |  |  | cjhogan@fnal.gov | 3159
| CD - Vicky White |  |  | white@fnal.gov | 3936
| CMSC - Lothar Bauerdick |  |  | bauerdick@fnal.gov | 6804
| Dir - Bruce Chrisman |  |  | chrisman@fnal.gov | 2359
| ES&H - Nancy Grossman |  |  | grossman@fnal.gov | 3810
| FESS - Randy Ortgiesen |  |  | ortgiesen@fnal.gov | 6288
| FS - Cindy Conger |  |  | conger@fnal.gov | 2993
| PPD - Bruce Baller |  |  | baller@fnal.gov | 2427
| TD - David Harding |  |  | harding@fnal.gov | 2971
| WD&RS - Kay VanVreede |  |  | vanvreed@fnal.gov | 3396
Note on B43: Central Computing Computer Networking DAQ/Online/R&D Technical Facilities Engineering Support TV System Support Travel for Conferences U.S. Particle School Office Conference/Workshop Support
Note on B44: Neutron Therapy Work for Others
Note on B45: Buildings/Facilities
Note on B46: Management/Supervision General Purpose Equipment and Support Computing Support/Information Systems Training and Education
Note on B47: Management/Supervision Human Resources Visual Media Services Information Resources Internal Audit Inventory Management Workshops/Meetings/Special Function Public Affairs Computing Support/Information Systems T&M Management Travel Buildings and Facilities Roads and Grounds Training/Education ES&H Accommodations Cafeteria

## New Data Input
1 | Functional Discipline | Functional Category | Functional Role |  | FY10 |  |  |  | FY11 |  |  |  | FY12 |  | FY13
2 |  | Tier 1 | Tier2 | FY09 | FY10/Q1 | FY10/Q2 | FY10/Q3 | FY10/Q4 | FY11/Q1 | FY11/Q2 | FY11/Q3 | FY11/Q4 | FY12/H1 | FY12/H2 | FY13/H1 | FY13/H2 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19
3 | Administration | Functional Category Tier 1: Communications; Functional Role Tier2: Media Services
4 |  | Functional Role Tier2: Public Relations
5 |  | Functional Category Tier 1: Finance; Functional Role Tier2: Accounting-Accountant
6 |  | Functional Role Tier2: Accounting-Clerical
7 |  | Functional Role Tier2: Operations Finance
8 |  | Functional Category Tier 1: Human Resources; Functional Role Tier2: Benefits
9 |  | Functional Role Tier2: Compensation
10 |  | Functional Role Tier2: Early Childhood Education
11 |  | Functional Role Tier2: Education
12 |  | Functional Role Tier2: Employee/Labor Relations
13 |  | Functional Role Tier2: Equal Opportunity
14 |  | Functional Role Tier2: HRIS
15 |  | Functional Role Tier2: Human Resources Generalist
16 |  | Functional Role Tier2: International Human Resources
17 |  | Functional Role Tier2: Recruitment
18 |  | Functional Category Tier 1: Other Administration; Functional Role Tier2: Administrative Support; FY12 FY12/H1: 1; FY12 FY12/H2: 1; FY13 FY13/H1: 1; FY13 FY13/H2: 1; FY13 FY14: 1
19 |  | Functional Role Tier2: Audit
20 |  | Functional Role Tier2: Executive Direction
21 |  | Functional Role Tier2: General Administrative
22 |  | Functional Role Tier2: Legal
23 |  | Functional Role Tier2: Library
24 |  | Functional Role Tier2: Training
25 |  | Functional Role Tier2: Travel
26 |  | Functional Category Tier 1: Procurement; Functional Role Tier2: Procurement
27 |  | Functional Category Tier 1: Project Management; Functional Role Tier2: Project Controls
28 |  | Functional Role Tier2: Project Finance; FY12 FY12/H1: 1; FY12 FY12/H2: 1; FY13 FY13/H1: 1; FY13 FY13/H2: 1; FY13 FY14: 1
29 |  | Functional Role Tier2: Project Manager; FY12 FY12/H1: 1; FY12 FY12/H2: 1; FY13 FY13/H1: 1; FY13 FY13/H2: 1; FY13 FY14: 1
30 |  | Functional Role Tier2: Project Support
31 | Engineer | Functional Category Tier 1: Civil Engineer; Functional Role Tier2: CFS Design Engineer
34 |  | Functional Role Tier2: CFS Operations Engineer
36 |  | Functional Role Tier2: CFS Technical Manager
37 |  | Functional Category Tier 1: Electrical Engineer; Functional Role Tier2: ASIC Design Engineer; FY11 FY11/Q1: 0.5; FY11 FY11/Q2: 0.5; FY11 FY11/Q3: 0.5; FY11 FY11/Q4: 0.5; FY12 FY12/H1: 0.75; FY12 FY12/H2: 0.75; FY13 FY13/H1: 0.525; FY13 FY13/H2: 0.525; FY13 FY14: 0.375
38 |  | Functional Role Tier2: Control System Engineer; FY11 FY11/Q1: 1; FY11 FY11/Q2: 1; FY11 FY11/Q3: 1; FY11 FY11/Q4: 1; FY12 FY12/H1: 1; FY12 FY12/H2: 1; FY13 FY13/H1: 0.7; FY13 FY13/H2: 0.7; FY13 FY14: 0.5
44 |  | Functional Role Tier2: Electrical Design Engineer; FY11 FY11/Q1: 1; FY11 FY11/Q2: 1; FY11 FY11/Q3: 1; FY11 FY11/Q4: 1; FY12 FY12/H1: 1; FY12 FY12/H2: 1; FY13 FY13/H1: 0.7; FY13 FY13/H2: 0.7; FY13 FY14: 0.5
46 |  | Functional Role Tier2: Electrical Technical Manager
51 |  | Functional Role Tier2: Electronics Design Engineer; FY11 FY11/Q1: 0.7; FY11 FY11/Q2: 0.7; FY11 FY11/Q3: 0.7; FY11 FY11/Q4: 0.7; FY12 FY12/H1: 1.25; FY12 FY12/H2: 1.25; FY13 FY13/H1: 1.525; FY13 FY13/H2: 1.525; FY13 FY14: 1.375
57 |  | Functional Role Tier2: Interlock Engineer
60 |  | Functional Role Tier2: RF Design Engineer
62 |  | Functional Category Tier 1: Mechanical Engineer; Functional Role Tier2: Cryogenics Engineer
64 |  | Functional Role Tier2: Magnet Design Engineer
67 |  | Functional Role Tier2: Materials Engineer
72 |  | Functional Role Tier2: Mechanical Analysis Engineer
74 |  | Functional Role Tier2: Mechanical Design Engineer; FY11 FY11/Q1: 0.2; FY11 FY11/Q2: 0.2; FY11 FY11/Q3: 0.2; FY11 FY11/Q4: 0.2; FY12 FY12/H1: 4.5; FY12 FY12/H2: 4.5; FY13 FY13/H1: 3.8; FY13 FY13/H2: 3.8; FY13 FY14: 3
78 |  | Functional Role Tier2: Mechanical Technical Manager
79 |  | Functional Role Tier2: Process/Controls Engineer
81 | ES&H | Functional Category Tier 1: ES&H; Functional Role Tier2: Construction Safety
82 |  | Functional Role Tier2: Electrical Safety
83 |  | Functional Role Tier2: Emergency Planner
84 |  | Functional Role Tier2: Environmental
85 |  | Functional Role Tier2: General ES&H
86 |  | Functional Role Tier2: Industrial Hygienist
87 |  | Functional Role Tier2: Laboratory Analysis
88 |  | Functional Role Tier2: Occupational Medicine Nurse
89 |  | Functional Role Tier2: Occupational Medicine Physician
90 |  | Functional Role Tier2: Radiation Protection
91 |  | Functional Role Tier2: Safety
92 |  | Functional Role Tier2: Waste Management
93 | Facilities Mgmt | Functional Category Tier 1: Facilities Management; Functional Role Tier2: Building Services
94 |  | Functional Role Tier2: Business Administration
95 |  | Functional Role Tier2: Carpenter
96 |  | Functional Role Tier2: Communications/Dispatcher
97 |  | Functional Role Tier2: Construction Coordinator
98 |  | Functional Role Tier2: Driver
99 |  | Functional Role Tier2: Facilities Mgmt.
100 |  | Functional Role Tier2: Firefighter
101 |  | Functional Role Tier2: Groundskeeping
102 |  | Functional Role Tier2: Housing/ Accommodations
103 |  | Functional Role Tier2: Logistics
104 |  | Functional Role Tier2: Maintenance
105 |  | Functional Role Tier2: Material Services
106 |  | Functional Role Tier2: Mechanic
107 |  | Functional Role Tier2: Security
108 |  | Functional Role Tier2: Telecommunication
109 | Information Technology | Functional Category Tier 1: Information Technology; Functional Role Tier2: Applications Development & Systems Analyst
110 |  | Functional Role Tier2: Communications Website Coordinator
111 |  | Functional Role Tier2: Computational Physics Developer
112 |  | Functional Role Tier2: Computer Customer Support
113 |  | Functional Role Tier2: Computer Science Researcher
114 |  | Functional Role Tier2: Computer Security Analyst
115 |  | Functional Role Tier2: Computing Services Specialist
116 |  | Functional Role Tier2: Database Administration Analyst
117 |  | Functional Role Tier2: Functional Analyst
118 |  | Functional Role Tier2: Network Analyst
119 |  | Functional Role Tier2: PC Support Associate
120 |  | Functional Role Tier2: Systems Administrator
121 |  | Functional Role Tier2: Web Applications Developer
122 | Scientific | Functional Category Tier 1: Scientist; Functional Role Tier2: Accelerator Physicist Experimental
123 |  | Functional Role Tier2: Accelerator Physicist Theory
124 |  | Functional Role Tier2: Chemist
125 |  | Functional Role Tier2: Magnet Scientist
126 |  | Functional Role Tier2: Particle Physicist Experimental
127 |  | Functional Role Tier2: Particle Physicist Theory
128 |  | Functional Role Tier2: Particle-Astro Physicist Experimental; FY11 FY11/Q1: 0.2; FY11 FY11/Q2: 0.2; FY11 FY11/Q3: 0.2; FY11 FY11/Q4: 0.2; FY12 FY12/H1: 0.5; FY12 FY12/H2: 0.5; FY13 FY13/H1: 1; FY13 FY13/H2: 1; FY13 FY14: 1
129 |  | Functional Role Tier2: Particle-Astro Physicist Theory
130 |  | Functional Role Tier2: RF Scientist
131 | Technical | Functional Category Tier 1: Alignment; Functional Role Tier2: Geodesist
134 |  | Functional Role Tier2: Metrologist
135 |  | Functional Category Tier 1: Design; Functional Role Tier2: Cryo Designer
139 |  | Functional Role Tier2: Electrical Designer; FY11 FY11/Q1: 0.7; FY11 FY11/Q2: 0.7; FY11 FY11/Q3: 0.7; FY11 FY11/Q4: 0.7; FY12 FY12/H1: 1.25; FY12 FY12/H2: 1.25; FY13 FY13/H1: 1.525; FY13 FY13/H2: 1.525; FY13 FY14: 1.375
140 |  | Functional Role Tier2: Electrical Drafter
144 |  | Functional Role Tier2: Magnet Designer
145 |  | Functional Role Tier2: Mechanical Designer; FY11 FY11/Q1: 0.2; FY11 FY11/Q2: 0.2; FY11 FY11/Q3: 0.2; FY11 FY11/Q4: 0.2; FY12 FY12/H1: 2.5; FY12 FY12/H2: 2.5; FY13 FY13/H1: 2.4; FY13 FY13/H2: 2.4; FY13 FY14: 2
146 |  | Functional Role Tier2: Mechanical Drafter
147 |  | Functional Category Tier 1: Electrical Technician; Functional Role Tier2: Electrical Assembly Technician
151 |  | Functional Role Tier2: Electrical Interlock Technician
152 |  | Functional Role Tier2: Electrical Task Manager
154 |  | Functional Role Tier2: Electrical Technician; FY11 FY11/Q1: 1; FY11 FY11/Q2: 1; FY11 FY11/Q3: 1; FY11 FY11/Q4: 1; FY12 FY12/H1: 2; FY12 FY12/H2: 2; FY13 FY13/H1: 1.4; FY13 FY13/H2: 1.4; FY13 FY14: 1
156 |  | Functional Role Tier2: Electrical Technician Supervisor
157 |  | Functional Role Tier2: Electronics Technician; FY11 FY11/Q1: 1.1; FY11 FY11/Q2: 1.1; FY11 FY11/Q3: 1.1; FY11 FY11/Q4: 1.1; FY12 FY12/H1: 3.25; FY12 FY12/H2: 3.25; FY13 FY13/H1: 4.225; FY13 FY13/H2: 4.225; FY13 FY14: 3.875
159 |  | Functional Category Tier 1: Mechanical Technician; Functional Role Tier2: Cryo Technician
160 |  | Functional Role Tier2: High Vac Technician
161 |  | Functional Role Tier2: Mechanical Assembly Technician; FY11 FY11/Q1: 0.3; FY11 FY11/Q2: 0.3; FY11 FY11/Q3: 0.3; FY11 FY11/Q4: 0.3; FY12 FY12/H1: 1; FY12 FY12/H2: 1; FY13 FY13/H1: 0.7; FY13 FY13/H2: 0.7; FY13 FY14: 0.5
165 |  | Functional Role Tier2: Mechanical Instrument Technician
166 |  | Functional Role Tier2: Mechanical SRF Technician
170 |  | Functional Role Tier2: Mechanical Systems Technician; FY12 FY12/H1: 1.75; FY12 FY12/H2: 1.75; FY13 FY13/H1: 2.2; FY13 FY13/H2: 2.2; FY13 FY14: 2
171 |  | Functional Role Tier2: Mechanical Task Manager; FY11 FY11/Q1: 0.2; FY11 FY11/Q2: 0.2; FY11 FY11/Q3: 0.2; FY11 FY11/Q4: 0.2; FY12 FY12/H1: 1.5; FY12 FY12/H2: 1.5; FY13 FY13/H1: 1.7; FY13 FY13/H2: 1.7; FY13 FY14: 1.5
172 |  | Functional Role Tier2: Mechanical Technician Supervisor
173 |  | Functional Category Tier 1: Operations; Functional Role Tier2: Accelerator Operator
174 |  | Functional Role Tier2: Accelerator Systems Specialist
175 |  | Functional Role Tier2: Operations Manager
176 |  | Functional Role Tier2: Operations Specialist
177 |  | Functional Category Tier 1: Other Technical; Functional Role Tier2: Construction Manager
178 |  | Functional Role Tier2: Fabrication Specialist
179 |  | Functional Role Tier2: Machinist
180 |  | Functional Role Tier2: QC Technical
181 |  | Functional Role Tier2: Quality Assurance; FY12 FY12/H1: 1; FY12 FY12/H2: 1; FY13 FY13/H1: 0.7; FY13 FY13/H2: 0.7; FY13 FY14: 0.5
182 |  | Functional Role Tier2: Welder
|  |  | Totals: | 0 | 0 | 0 | 0 | 0 | 7.1 | 7.1 | 7.1 | 7.1 | 26.25 | 26.25 | 26.1 | 26.1 | 22.5 | 0 | 0 | 0 | 0 | 0
|  |  |  | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19
|  |  | Average Per Year: | 0 | 0 | 7.1 | 26.25 | 26.1 | 22.5 | 0 | 0 | 0 | 0 | 0

## Old Tier 2 Input
|  |  | CMS Phase 1 Upgrade Construction | [9 empty] | CMS Phase 2 Upgrade Construction | [9 empty] | DUSEL Beamline | [9 empty] | DUSEL Detector | [9 empty] | HINS | [9 empty] | ILC Accelerator | [9 empty] | MicroBooNE | [9 empty] | Mu2e | [9 empty] | Project X | [9 empty] | SRF / ILCTA-NML
Functional Discipline | Functional Category - Tier 1 | Functional Role - Tier2 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
Administration | Communications | Media Services | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Public Relations | ILC Accelerator FY09: 0.5; ILC Accelerator FY10: 0.5; ILC Accelerator FY11: 0.5; ILC Accelerator FY12: 0.5; ILC Accelerator FY13: 0.5; ILC Accelerator FY14: 0.5; ILC Accelerator FY15: 0.5; ILC Accelerator FY16: 0.5; ILC Accelerator FY17: 0.5; ILC Accelerator FY18: 0.5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Finance | Accounting-Accountant | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Accounting-Clerical | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Operations Finance | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Human Resources | Benefits | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Compensation | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Early Childhood Education | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Education | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Employee/Labor Relations | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Equal Opportunity | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | HRIS | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Human Resources Generalist | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | International Human Resources | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Recruitment | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Other Administration | Administrative Support | CMS Phase 1 Upgrade Construction FY10: 1; CMS Phase 1 Upgrade Construction FY11: 1; CMS Phase 1 Upgrade Construction FY12: 1; CMS Phase 1 Upgrade Construction FY13: 1; CMS Phase 2 Upgrade Construction FY10: 1; CMS Phase 2 Upgrade Construction FY11: 1; CMS Phase 2 Upgrade Construction FY12: 1; CMS Phase 2 Upgrade Construction FY13: 1; CMS Phase 2 Upgrade Construction FY14: 1; DUSEL Beamline FY09: 0.5; DUSEL Beamline FY10: 1; DUSEL Beamline FY11: 1; DUSEL Beamline FY12: 2; DUSEL Beamline FY13: 2; DUSEL Beamline FY14: 2; DUSEL Beamline FY15: 2; DUSEL Beamline FY16: 2; DUSEL Beamline FY17: 2; DUSEL Beamline FY18: 2; ILC Accelerator FY09: 0.15; ILC Accelerator FY10: 0.15; ILC Accelerator FY11: 0.15; ILC Accelerator FY12: 0.15; ILC Accelerator FY13: 0.15; ILC Accelerator FY14: 0.15; ILC Accelerator FY15: 0.15; ILC Accelerator FY16: 0.15; ILC Accelerator FY17: 0.15; ILC Accelerator FY18: 0.15; Mu2e FY09: 0.1; Mu2e FY10: 0.5; Mu2e FY11: 1; Mu2e FY12: 1; Mu2e FY13: 1; Mu2e FY14: 1; Mu2e FY15: 1; Mu2e FY16: 1; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0.25; Project X FY10: 0.5; Project X FY11: 1; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 0.5; SRF / ILCTA-NML FY11: 0.5; SRF / ILCTA-NML FY12: 0.5; SRF / ILCTA-NML FY13: 0.5; SRF / ILCTA-NML FY14: 0.5; SRF / ILCTA-NML FY15: 0.5; SRF / ILCTA-NML FY16: 0.5; SRF / ILCTA-NML FY17: 0.5; SRF / ILCTA-NML FY18: 0.5
|  | Audit | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Executive Direction | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | General Administrative | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Legal | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Library | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Training | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Travel | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Procurement | Procurement | HINS FY09: 0.5; HINS FY10: 0.5; HINS FY11: 0.5; HINS FY12: 0.25; HINS FY13: 0.1; HINS FY14: 0; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 0.5; ILC Accelerator FY10: 0.5; ILC Accelerator FY11: 0.5; ILC Accelerator FY12: 0.5; ILC Accelerator FY13: 0.5; ILC Accelerator FY14: 0.5; ILC Accelerator FY15: 0.5; ILC Accelerator FY16: 0.5; ILC Accelerator FY17: 0.5; ILC Accelerator FY18: 0.5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 1; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Project Management | Project Controls | DUSEL Beamline FY09: 0.5; DUSEL Beamline FY10: 1; DUSEL Beamline FY11: 2; DUSEL Beamline FY12: 2; DUSEL Beamline FY13: 4; DUSEL Beamline FY14: 4; DUSEL Beamline FY15: 4; DUSEL Beamline FY16: 4; DUSEL Beamline FY17: 4; DUSEL Beamline FY18: 4; DUSEL Detector FY09: 0.4; DUSEL Detector FY10: 1; DUSEL Detector FY11: 1; DUSEL Detector FY12: 1; DUSEL Detector FY13: 1; DUSEL Detector FY14: 1; DUSEL Detector FY15: 1; DUSEL Detector FY16: 1; DUSEL Detector FY17: 1; DUSEL Detector FY18: 1; MicroBooNE FY09: 0.5; MicroBooNE FY10: 0.5; MicroBooNE FY11: 0.5; MicroBooNE FY12: 0.5; MicroBooNE FY13: 0.5; Mu2e FY09: 1; Mu2e FY10: 2; Mu2e FY11: 2; Mu2e FY12: 2; Mu2e FY13: 2; Mu2e FY14: 2; Mu2e FY15: 2; Mu2e FY16: 1; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0.5; Project X FY10: 2; Project X FY11: 3; Project X FY12: 5; Project X FY13: 5; Project X FY14: 5; Project X FY15: 5; Project X FY16: 5; Project X FY17: 5; Project X FY18: 1; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 0.5; SRF / ILCTA-NML FY11: 0.5; SRF / ILCTA-NML FY12: 0.5; SRF / ILCTA-NML FY13: 0.5; SRF / ILCTA-NML FY14: 0.5
|  | Project Finance | CMS Phase 1 Upgrade Construction FY10: 1; CMS Phase 1 Upgrade Construction FY11: 1; CMS Phase 1 Upgrade Construction FY12: 1; CMS Phase 1 Upgrade Construction FY13: 1; CMS Phase 2 Upgrade Construction FY10: 1; CMS Phase 2 Upgrade Construction FY11: 1; CMS Phase 2 Upgrade Construction FY12: 1; CMS Phase 2 Upgrade Construction FY13: 1; CMS Phase 2 Upgrade Construction FY14: 1; MicroBooNE FY09: 0.5; MicroBooNE FY10: 0.5; MicroBooNE FY11: 0.5; MicroBooNE FY12: 0.5; MicroBooNE FY13: 0.5; Mu2e FY09: 0.5; Mu2e FY10: 1; Mu2e FY11: 1; Mu2e FY12: 1; Mu2e FY13: 1; Mu2e FY14: 1; Mu2e FY15: 1; Mu2e FY16: 1; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0.25; Project X FY10: 1; Project X FY11: 2; Project X FY12: 2; Project X FY13: 2; Project X FY14: 2; Project X FY15: 2; Project X FY16: 2; Project X FY17: 2; Project X FY18: 1
|  | Project Manager |  | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 | 1 | [24 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | [5 empty] | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Project Support | ILC Accelerator FY09: 3; ILC Accelerator FY10: 3; ILC Accelerator FY11: 3; ILC Accelerator FY12: 3; ILC Accelerator FY13: 3; ILC Accelerator FY14: 3; ILC Accelerator FY15: 3; ILC Accelerator FY16: 3; ILC Accelerator FY17: 3; ILC Accelerator FY18: 3; MicroBooNE FY09: 0.2; MicroBooNE FY10: 0.2; MicroBooNE FY11: 0.2; MicroBooNE FY12: 0.2; MicroBooNE FY13: 0.2; Project X FY09: 1; Project X FY10: 1; Project X FY11: 2; Project X FY12: 3; Project X FY13: 6; Project X FY14: 6; Project X FY15: 6; Project X FY16: 6; Project X FY17: 4; Project X FY18: 1; SRF / ILCTA-NML FY09: 1.5; SRF / ILCTA-NML FY10: 1.5; SRF / ILCTA-NML FY11: 1.5; SRF / ILCTA-NML FY12: 1.5; SRF / ILCTA-NML FY13: 1.5; SRF / ILCTA-NML FY14: 1.5; SRF / ILCTA-NML FY15: 0.75; SRF / ILCTA-NML FY16: 0.75; SRF / ILCTA-NML FY17: 0.75; SRF / ILCTA-NML FY18: 0.75
Engineer | Civil Engineer | CFS Design Engineer | DUSEL Beamline FY09: 0.5; DUSEL Beamline FY10: 1; DUSEL Beamline FY11: 2; DUSEL Beamline FY12: 2; DUSEL Beamline FY13: 2; DUSEL Beamline FY14: 2; DUSEL Beamline FY15: 2; DUSEL Beamline FY16: 2; DUSEL Beamline FY17: 2; DUSEL Beamline FY18: 2; ILC Accelerator FY09: 3.5; ILC Accelerator FY10: 3.5; ILC Accelerator FY11: 3.5; ILC Accelerator FY12: 3.5; ILC Accelerator FY13: 3.5; ILC Accelerator FY14: 3.5; ILC Accelerator FY15: 3.5; ILC Accelerator FY16: 3.5; ILC Accelerator FY17: 3.5; ILC Accelerator FY18: 3.5; MicroBooNE FY10: 0.2; MicroBooNE FY11: 0.4; Mu2e FY09: 1; Mu2e FY10: 1; Mu2e FY11: 3.5; Mu2e FY12: 4; Mu2e FY13: 2; Mu2e FY14: 0.1; Project X FY09: 0.6; Project X FY10: 0.6; Project X FY11: 0.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 2; SRF / ILCTA-NML FY10: 2; SRF / ILCTA-NML FY11: 2; SRF / ILCTA-NML FY12: 2; SRF / ILCTA-NML FY13: 2; SRF / ILCTA-NML FY14: 2
|  | CFS Operations Engineer | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | CFS Technical Manager | Mu2e FY09: 0.1; Mu2e FY10: 0.25; Mu2e FY11: 0.25; Mu2e FY12: 0.25; Mu2e FY13: 0.25; Mu2e FY14: 0.1; Mu2e FY15: 0; Mu2e FY16: 0; Mu2e FY17: 0; Project X FY09: 0.6; Project X FY10: 0.6; Project X FY11: 0.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Electrical Engineer | ASIC Design Engineer | CMS Phase 1 Upgrade Construction FY10: 0.75; CMS Phase 1 Upgrade Construction FY11: 0.75; CMS Phase 1 Upgrade Construction FY12: 0.525; CMS Phase 1 Upgrade Construction FY13: 0.375; CMS Phase 2 Upgrade Construction FY10: 0.75; CMS Phase 2 Upgrade Construction FY11: 0.75; CMS Phase 2 Upgrade Construction FY12: 0.525; CMS Phase 2 Upgrade Construction FY13: 0.375; CMS Phase 2 Upgrade Construction FY14: 0.15; DUSEL Beamline FY09: 0.25; DUSEL Beamline FY10: 0.5; DUSEL Beamline FY11: 1; DUSEL Beamline FY12: 3; DUSEL Beamline FY13: 3; DUSEL Beamline FY14: 2; DUSEL Beamline FY15: 2; DUSEL Beamline FY16: 2; DUSEL Beamline FY17: 2; DUSEL Beamline FY18: 2; DUSEL Detector FY09: 0.1; DUSEL Detector FY10: 0.25; DUSEL Detector FY11: 1; DUSEL Detector FY12: 1; DUSEL Detector FY13: 1; DUSEL Detector FY14: 1; Mu2e FY10: 1; Mu2e FY11: 0.5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Control System Engineer | CMS Phase 1 Upgrade Construction FY10: 1; CMS Phase 1 Upgrade Construction FY11: 1; CMS Phase 1 Upgrade Construction FY12: 0.7; CMS Phase 1 Upgrade Construction FY13: 0.5; CMS Phase 2 Upgrade Construction FY10: 1; CMS Phase 2 Upgrade Construction FY11: 1; CMS Phase 2 Upgrade Construction FY12: 0.7; CMS Phase 2 Upgrade Construction FY13: 0.5; CMS Phase 2 Upgrade Construction FY14: 0.2; HINS FY09: 1; HINS FY10: 1; HINS FY11: 1; HINS FY12: 1; HINS FY13: 0.5; HINS FY14: 0.25; HINS FY15: 0.2; HINS FY16: 0.2; HINS FY17: 0.2; HINS FY18: 0.2; ILC Accelerator FY09: 0.75; ILC Accelerator FY10: 0.75; ILC Accelerator FY11: 0.75; ILC Accelerator FY12: 0.75; ILC Accelerator FY13: 0.75; ILC Accelerator FY14: 0.75; ILC Accelerator FY15: 0.75; ILC Accelerator FY16: 0.75; ILC Accelerator FY17: 0.75; ILC Accelerator FY18: 0.75; Mu2e FY09: 0; Mu2e FY10: 0; Mu2e FY11: 0; Mu2e FY12: 2.1365; Mu2e FY13: 0.95588; Mu2e FY14: 0.36941; Mu2e FY15: 0.68706; Mu2e FY16: 0; Mu2e FY17: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1.3; SRF / ILCTA-NML FY10: 1.3; SRF / ILCTA-NML FY11: 1.3; SRF / ILCTA-NML FY12: 1.3; SRF / ILCTA-NML FY13: 1.3; SRF / ILCTA-NML FY14: 1.3; SRF / ILCTA-NML FY15: 1; SRF / ILCTA-NML FY16: 1; SRF / ILCTA-NML FY17: 1; SRF / ILCTA-NML FY18: 1
|  | Electrical Design Engineer | CMS Phase 1 Upgrade Construction FY10: 1; CMS Phase 1 Upgrade Construction FY11: 1; CMS Phase 1 Upgrade Construction FY12: 0.7; CMS Phase 1 Upgrade Construction FY13: 0.5; HINS FY09: 1; HINS FY10: 2; HINS FY11: 2; HINS FY12: 2; HINS FY13: 1; HINS FY14: 0.5; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 0.25; ILC Accelerator FY10: 0.25; ILC Accelerator FY11: 0.25; ILC Accelerator FY12: 0.25; ILC Accelerator FY13: 0.25; ILC Accelerator FY14: 0.25; ILC Accelerator FY15: 0.25; ILC Accelerator FY16: 0.25; ILC Accelerator FY17: 0.25; ILC Accelerator FY18: 0.25; Mu2e FY09: 0.39353; Mu2e FY10: 1.3412; Mu2e FY11: 0.85059; Mu2e FY12: 1.1653; Mu2e FY13: 0.47824; Mu2e FY14: 0.065294; Mu2e FY16: 0; Mu2e FY17: 0; Project X FY09: 1.8; Project X FY10: 3; Project X FY11: 3.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1; SRF / ILCTA-NML FY10: 1.5; SRF / ILCTA-NML FY11: 1.5; SRF / ILCTA-NML FY12: 1.5; SRF / ILCTA-NML FY13: 1.5; SRF / ILCTA-NML FY14: 1.5
|  | Electrical Technical Manager | HINS FY09: 2; HINS FY10: 1; HINS FY11: 1; HINS FY12: 0.5; HINS FY13: 0.25; HINS FY14: 0.1; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; Mu2e FY09: 0; Mu2e FY10: 1; Mu2e FY11: 1; Mu2e FY12: 1; Mu2e FY13: 1; Mu2e FY14: 1; Mu2e FY15: 1; Mu2e FY16: 1; Mu2e FY17: 0; Project X FY09: 0.6; Project X FY10: 0.6; Project X FY11: 0.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Electronics Design Engineer | CMS Phase 1 Upgrade Construction FY10: 0.95; CMS Phase 1 Upgrade Construction FY11: 1.25; CMS Phase 1 Upgrade Construction FY12: 1.525; CMS Phase 1 Upgrade Construction FY13: 1.375; CMS Phase 2 Upgrade Construction FY10: 2.65; CMS Phase 2 Upgrade Construction FY11: 3.25; CMS Phase 2 Upgrade Construction FY12: 2.975; CMS Phase 2 Upgrade Construction FY13: 3.125; CMS Phase 2 Upgrade Construction FY14: 2.45; HINS FY09: 2.5; HINS FY10: 3; HINS FY11: 3; HINS FY12: 3; HINS FY13: 1.5; HINS FY14: 0.7; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; MicroBooNE FY10: 1; MicroBooNE FY11: 1; Mu2e FY09: 0.2; Mu2e FY10: 2.4; Mu2e FY11: 0.62882; Mu2e FY12: 0.93412; Mu2e FY13: 0.30353; Mu2e FY14: 0.65471; Project X FY09: 1.2; Project X FY10: 1.8; Project X FY11: 3; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Interlock Engineer | HINS FY09: 0.5; HINS FY10: 0.5; HINS FY11: 0.5; HINS FY12: 0.5; HINS FY13: 0.2; HINS FY14: 0.2; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | RF Design Engineer | HINS FY09: 1.5; HINS FY10: 1.5; HINS FY11: 1.5; HINS FY12: 1; HINS FY13: 0.5; HINS FY14: 0.25; HINS FY15: 0.1; HINS FY16: 0.1; HINS FY17: 0.1; HINS FY18: 0.1; ILC Accelerator FY09: 1.5; ILC Accelerator FY10: 1.5; ILC Accelerator FY11: 1.5; ILC Accelerator FY12: 1.5; ILC Accelerator FY13: 1.5; ILC Accelerator FY14: 1.5; ILC Accelerator FY15: 1.5; ILC Accelerator FY16: 1.5; ILC Accelerator FY17: 1.5; ILC Accelerator FY18: 1.5; Mu2e FY09: 0.25; Mu2e FY10: 0.5; Mu2e FY11: 0.5; Project X FY09: 0.6; Project X FY10: 0.6; Project X FY11: 0.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1.5; SRF / ILCTA-NML FY10: 2; SRF / ILCTA-NML FY11: 2; SRF / ILCTA-NML FY12: 2; SRF / ILCTA-NML FY13: 2; SRF / ILCTA-NML FY14: 2; SRF / ILCTA-NML FY15: 1; SRF / ILCTA-NML FY16: 1; SRF / ILCTA-NML FY17: 1; SRF / ILCTA-NML FY18: 1
| Mechanical Engineer | Cryogenics Engineer | [20 empty] | 0.5 | 1 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 0.1 | 0.25 | 0.25 | 1 | 1 | [5 empty] | 2 | 1.5 | 1.25 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1 | 0.75 | 0.6 | 0.1 | 0.1 | 0.1 |  |  |  |  | 0 | 0.1 | 0.1 | 1.4618 | 0.25059 | 0.41235 | 0.62353 | 0.19353 | 0 |  | 2.4 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2
|  | Magnet Design Engineer | HINS FY09: 0.5; HINS FY10: 0.5; HINS FY11: 0.5; HINS FY12: 0.5; HINS FY13: 0.25; HINS FY14: 0; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 1; ILC Accelerator FY10: 1; ILC Accelerator FY11: 1; ILC Accelerator FY12: 1; ILC Accelerator FY13: 1; ILC Accelerator FY14: 1; ILC Accelerator FY15: 1; ILC Accelerator FY16: 1; ILC Accelerator FY17: 1; ILC Accelerator FY18: 1; Mu2e FY09: 0.8; Mu2e FY10: 2; Mu2e FY11: 3; Mu2e FY12: 3; Mu2e FY13: 4; Mu2e FY14: 5; Mu2e FY15: 5; Mu2e FY16: 0.2; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 1; SRF / ILCTA-NML FY11: 1; SRF / ILCTA-NML FY12: 1; SRF / ILCTA-NML FY13: 1; SRF / ILCTA-NML FY14: 1
|  | Materials Engineer | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1; SRF / ILCTA-NML FY10: 1; SRF / ILCTA-NML FY11: 1; SRF / ILCTA-NML FY12: 1; SRF / ILCTA-NML FY13: 1; SRF / ILCTA-NML FY14: 1; SRF / ILCTA-NML FY15: 0.5; SRF / ILCTA-NML FY16: 0.5; SRF / ILCTA-NML FY17: 0.5; SRF / ILCTA-NML FY18: 0.5
|  | Mechanical Analysis Engineer | Mu2e FY09: 0.2; Mu2e FY10: 0.2; Mu2e FY11: 0.1; Mu2e FY12: 0.1; Mu2e FY13: 0.1; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 0.5; SRF / ILCTA-NML FY11: 0.5; SRF / ILCTA-NML FY12: 0.5; SRF / ILCTA-NML FY13: 0.5; SRF / ILCTA-NML FY14: 0.5
|  | Mechanical Design Engineer |  | 4.2 | 4.5 | 3.8 | 3 | [6 empty] | 4.4 | 5 | 4.2 | 4 | 2.8 | [24 empty] | 4.25 | 4.25 | 2 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0.3 | 0.5 | 0.5 | [7 empty] | 1 | 3.7 | 3.9529 | 1.6971 | 1.3976 | 0.44824 | 0.15941 | 0.79 | 0.32588 |  | 3 | 7.8 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 2.5 | 2.5 | 2.5 | 2.5
|  | Mechanical Technical Manager | Mu2e FY09: 0.5; Mu2e FY10: 1; Mu2e FY11: 1; Mu2e FY12: 2; Mu2e FY13: 2; Mu2e FY14: 2; Mu2e FY15: 2; Mu2e FY16: 2; Mu2e FY17: 0; Project X FY09: 1.8; Project X FY10: 1.8; Project X FY11: 1.8; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Process/Controls Engineer | ILC Accelerator FY09: 0.5; ILC Accelerator FY10: 0.5; ILC Accelerator FY11: 0.5; ILC Accelerator FY12: 0.5; ILC Accelerator FY13: 0.5; ILC Accelerator FY14: 0.5; ILC Accelerator FY15: 0.5; ILC Accelerator FY16: 0.5; ILC Accelerator FY17: 0.5; ILC Accelerator FY18: 0.5; MicroBooNE FY11: 0.3; Project X FY09: 1.2; Project X FY10: 1.2; Project X FY11: 2.4; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1; SRF / ILCTA-NML FY10: 1; SRF / ILCTA-NML FY11: 1; SRF / ILCTA-NML FY12: 1; SRF / ILCTA-NML FY13: 1; SRF / ILCTA-NML FY14: 1; SRF / ILCTA-NML FY15: 1; SRF / ILCTA-NML FY16: 1; SRF / ILCTA-NML FY17: 1; SRF / ILCTA-NML FY18: 1
ES&H | ES&H | Construction Safety | DUSEL Beamline FY09: 0.1; DUSEL Beamline FY10: 0.1; DUSEL Beamline FY11: 0.1; DUSEL Beamline FY12: 0.1; DUSEL Beamline FY13: 1; DUSEL Beamline FY14: 2; DUSEL Beamline FY15: 2; DUSEL Beamline FY16: 2; DUSEL Beamline FY17: 2; DUSEL Beamline FY18: 2; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Electrical Safety | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Emergency Planner | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Environmental | Mu2e FY10: 0.25; Mu2e FY11: 0.25; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | General ES&H | HINS FY09: 0.3; HINS FY10: 0.3; HINS FY11: 0.2; HINS FY12: 0.2; HINS FY13: 0.2; HINS FY14: 0.2; HINS FY15: 0.2; HINS FY16: 0.2; HINS FY17: 0.2; HINS FY18: 0.2; Mu2e FY09: 0.05; Mu2e FY10: 0.1; Mu2e FY11: 0.1; Mu2e FY12: 0.1; Mu2e FY13: 0.1; Mu2e FY14: 0.1; Mu2e FY15: 0.1; Mu2e FY16: 0.1; Mu2e FY17: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.1; SRF / ILCTA-NML FY10: 0.1; SRF / ILCTA-NML FY11: 0.1; SRF / ILCTA-NML FY12: 0.1; SRF / ILCTA-NML FY13: 0.1; SRF / ILCTA-NML FY14: 0.1; SRF / ILCTA-NML FY15: 0.1; SRF / ILCTA-NML FY16: 0.1; SRF / ILCTA-NML FY17: 0.1; SRF / ILCTA-NML FY18: 0.1
|  | Industrial Hygienist | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Laboratory Analysis | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Occupational Medicine Nurse | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Occupational Medicine Physician | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Radiation Protection | HINS FY09: 0.1; HINS FY10: 0.1; HINS FY11: 0.1; HINS FY12: 0.1; HINS FY13: 0.05; HINS FY14: 0.05; HINS FY15: 0.05; HINS FY16: 0.05; HINS FY17: 0.05; HINS FY18: 0.05; Mu2e FY09: 0.25; Mu2e FY10: 0.25; Mu2e FY11: 0.3; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.1; SRF / ILCTA-NML FY10: 0.1; SRF / ILCTA-NML FY11: 0.1; SRF / ILCTA-NML FY12: 0.1; SRF / ILCTA-NML FY13: 0.1; SRF / ILCTA-NML FY14: 0.1; SRF / ILCTA-NML FY15: 0.1; SRF / ILCTA-NML FY16: 0.1; SRF / ILCTA-NML FY17: 0.1; SRF / ILCTA-NML FY18: 0.1
|  | Safety | Project X FY09: 0; Project X FY10: 1; Project X FY11: 1; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Waste Management | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
Facilities Mgmt | Facilities Management | Building Services | MicroBooNE FY12: 0.1; MicroBooNE FY13: 0.1; MicroBooNE FY14: 0.1; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Business Administration | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Carpenter | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Communications/Dispatcher | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Construction Coordinator | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Driver | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Facilities Mgmt. | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Firefighter | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Groundskeeping | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Housing/ Accommodations | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Logistics | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Maintenance | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Material Services | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Mechanic | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Security | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Telecommunication | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
Information Technology | Information Technology | Applications Development & Systems Analyst | DUSEL Beamline FY10: 0.5; DUSEL Beamline FY11: 0.5; DUSEL Beamline FY12: 0.5; DUSEL Beamline FY13: 1; DUSEL Beamline FY14: 1; DUSEL Beamline FY15: 1; DUSEL Beamline FY16: 1; DUSEL Beamline FY17: 1; DUSEL Beamline FY18: 1; DUSEL Detector FY09: 1; DUSEL Detector FY10: 2; DUSEL Detector FY11: 2; DUSEL Detector FY12: 2; DUSEL Detector FY13: 2; DUSEL Detector FY14: 2; DUSEL Detector FY15: 2; DUSEL Detector FY16: 2; DUSEL Detector FY17: 2; DUSEL Detector FY18: 2; HINS FY09: 3; HINS FY10: 4; HINS FY11: 4; HINS FY12: 2; HINS FY13: 2; HINS FY14: 2; HINS FY15: 2; HINS FY16: 1; HINS FY17: 1; HINS FY18: 1; Project X FY09: 1.2; Project X FY10: 2.4; Project X FY11: 2.4; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Communications Website Coordinator | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Computational Physics Developer | Mu2e FY09: 1; Mu2e FY10: 1.6; Mu2e FY11: 2; Mu2e FY12: 1.5; Mu2e FY13: 1.5; Mu2e FY14: 1.5; Mu2e FY15: 0.5; Mu2e FY16: 0.5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Computer Customer Support | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Computer Science Researcher | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Computer Security Analyst | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Computing Services Specialist | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Database Administration Analyst | HINS FY09: 0.2; HINS FY10: 0.2; HINS FY11: 0.2; HINS FY12: 0.2; HINS FY13: 0.2; HINS FY14: 0.2; HINS FY15: 0.2; HINS FY16: 0.2; HINS FY17: 0.2; HINS FY18: 0.2; ILC Accelerator FY09: 0.24; ILC Accelerator FY10: 0.24; ILC Accelerator FY11: 0.24; ILC Accelerator FY12: 0.24; ILC Accelerator FY13: 0.24; ILC Accelerator FY14: 0.24; ILC Accelerator FY15: 0.24; ILC Accelerator FY16: 0.24; ILC Accelerator FY17: 0.24; ILC Accelerator FY18: 0.24; Mu2e FY11: 0.25; Mu2e FY12: 0.25; Mu2e FY13: 0.1; Mu2e FY14: 0.1; Mu2e FY15: 0.1; Mu2e FY16: 0.1; Project X FY09: 0.6; Project X FY10: 0.6; Project X FY11: 0.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.25; SRF / ILCTA-NML FY10: 0.25; SRF / ILCTA-NML FY11: 0.25; SRF / ILCTA-NML FY12: 0.25; SRF / ILCTA-NML FY13: 0.25; SRF / ILCTA-NML FY14: 0.25; SRF / ILCTA-NML FY15: 0.25; SRF / ILCTA-NML FY16: 0.25; SRF / ILCTA-NML FY17: 0.25; SRF / ILCTA-NML FY18: 0.25
|  | Functional Analyst | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Network Analyst | Project X FY09: 0.6; Project X FY10: 0.6; Project X FY11: 1.2; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | PC Support Associate | HINS FY09: 0.1; HINS FY10: 0.1; HINS FY11: 0.1; HINS FY12: 0.1; HINS FY13: 0.1; HINS FY14: 0.1; HINS FY15: 0.1; HINS FY16: 0.1; HINS FY17: 0.1; HINS FY18: 0.1; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Systems Administrator | HINS FY09: 0.1; HINS FY10: 0.1; HINS FY11: 0.1; HINS FY12: 0.1; HINS FY13: 0.1; HINS FY14: 0.1; HINS FY15: 0.1; HINS FY16: 0.1; HINS FY17: 0.1; HINS FY18: 0.1; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Web Applications Developer | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
Scientific | Scientist | Accelerator Physicist Experimental | [20 empty] | 3 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0.5 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | [10 empty] | 2.0259 | 4.0965 | 4.6482 | 4.0047 | 4 | 4 | 4 | 2 | 0 | 0 | 4.8 | 7.2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1 | 1 | 1 | 1
|  | Accelerator Physicist Theory | HINS FY09: 1; HINS FY10: 0; HINS FY11: 0; HINS FY12: 0; HINS FY13: 0; HINS FY14: 0; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 1; ILC Accelerator FY10: 1; ILC Accelerator FY11: 1; ILC Accelerator FY12: 1; ILC Accelerator FY13: 1; ILC Accelerator FY14: 1; ILC Accelerator FY15: 1; ILC Accelerator FY16: 1; ILC Accelerator FY17: 1; ILC Accelerator FY18: 1; Project X FY09: 3.6; Project X FY10: 6; Project X FY11: 6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Chemist | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Magnet Scientist | ILC Accelerator FY09: 0.25; ILC Accelerator FY10: 0.25; ILC Accelerator FY11: 0.25; ILC Accelerator FY12: 0.25; ILC Accelerator FY13: 0.25; ILC Accelerator FY14: 0.25; ILC Accelerator FY15: 0.25; ILC Accelerator FY16: 0.25; ILC Accelerator FY17: 0.25; ILC Accelerator FY18: 0.25; Mu2e FY09: 1.5; Mu2e FY10: 2; Mu2e FY11: 2; Mu2e FY12: 2; Mu2e FY13: 1.5; Mu2e FY14: 1.5; Mu2e FY15: 1.5; Mu2e FY16: 1; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Particle Physicist Experimental | MicroBooNE FY09: 1.5; MicroBooNE FY10: 2; MicroBooNE FY11: 3; MicroBooNE FY12: 4; MicroBooNE FY13: 4; MicroBooNE FY14: 4; MicroBooNE FY15: 3.5; MicroBooNE FY16: 3.5; MicroBooNE FY17: 3.5; MicroBooNE FY18: 3.5; Mu2e FY09: 2.2; Mu2e FY10: 5.2; Mu2e FY11: 6; Mu2e FY12: 6; Mu2e FY13: 6; Mu2e FY14: 6; Mu2e FY15: 6; Mu2e FY16: 6; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1; SRF / ILCTA-NML FY10: 1; SRF / ILCTA-NML FY11: 1; SRF / ILCTA-NML FY12: 1; SRF / ILCTA-NML FY13: 1; SRF / ILCTA-NML FY14: 1
|  | Particle Physicist Theory | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Particle-Astro Physicist Experimental | CMS Phase 1 Upgrade Construction FY10: 0.2; CMS Phase 1 Upgrade Construction FY11: 0.5; CMS Phase 1 Upgrade Construction FY12: 1; CMS Phase 1 Upgrade Construction FY13: 1; CMS Phase 2 Upgrade Construction FY10: 0.4; CMS Phase 2 Upgrade Construction FY11: 1; CMS Phase 2 Upgrade Construction FY12: 1.4; CMS Phase 2 Upgrade Construction FY13: 2; CMS Phase 2 Upgrade Construction FY14: 2; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Particle-Astro Physicist Theory | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | RF Scientist | HINS FY09: 0.5; HINS FY10: 0.5; HINS FY11: 0.5; HINS FY12: 0.5; HINS FY13: 0.25; HINS FY14: 0.1; HINS FY15: 0.1; HINS FY16: 0.1; HINS FY17: 0.1; HINS FY18: 0.1; ILC Accelerator FY09: 2; ILC Accelerator FY10: 2; ILC Accelerator FY11: 2; ILC Accelerator FY12: 2; ILC Accelerator FY13: 2; ILC Accelerator FY14: 2; ILC Accelerator FY15: 2; ILC Accelerator FY16: 2; ILC Accelerator FY17: 2; ILC Accelerator FY18: 2; Project X FY09: 1.2; Project X FY10: 1.2; Project X FY11: 1.2; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 2; SRF / ILCTA-NML FY10: 2; SRF / ILCTA-NML FY11: 2; SRF / ILCTA-NML FY12: 2; SRF / ILCTA-NML FY13: 2; SRF / ILCTA-NML FY14: 2; SRF / ILCTA-NML FY15: 0.5; SRF / ILCTA-NML FY16: 0.5; SRF / ILCTA-NML FY17: 0.5; SRF / ILCTA-NML FY18: 0.5
Technical | Alignment | Geodesist | HINS FY09: 0.1; HINS FY10: 0.1; HINS FY11: 0.1; HINS FY12: 0.1; HINS FY13: 0.05; HINS FY14: 0.05; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; Mu2e FY11: 1; Mu2e FY12: 1; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Metrologist | DUSEL Beamline FY09: 0.2; DUSEL Beamline FY10: 0.5; DUSEL Beamline FY11: 0.5; DUSEL Beamline FY12: 0.5; DUSEL Beamline FY13: 1; DUSEL Beamline FY14: 1; DUSEL Beamline FY15: 1; DUSEL Beamline FY16: 1; DUSEL Beamline FY17: 1; DUSEL Beamline FY18: 1; HINS FY09: 0.1; HINS FY10: 0.1; HINS FY11: 0.1; HINS FY12: 0.1; HINS FY13: 0.05; HINS FY14: 0.05; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; MicroBooNE FY10: 0.1; MicroBooNE FY11: 0.1; MicroBooNE FY12: 0.1; Mu2e FY09: 0; Mu2e FY10: 0; Mu2e FY11: 1.1; Mu2e FY12: 1.2; Mu2e FY13: 0.4; Mu2e FY14: 0.10471; Mu2e FY15: 0.066471; Mu2e FY16: 0.2; Mu2e FY17: 0.1; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Design | Cryo Designer | DUSEL Beamline FY09: 1; DUSEL Beamline FY10: 2; DUSEL Beamline FY11: 3; DUSEL Beamline FY12: 3; DUSEL Beamline FY13: 3; DUSEL Beamline FY14: 5; DUSEL Beamline FY15: 3; DUSEL Beamline FY16: 3; DUSEL Beamline FY17: 1; DUSEL Beamline FY18: 1; DUSEL Detector FY10: 0.5; DUSEL Detector FY11: 0.5; DUSEL Detector FY12: 0.5; DUSEL Detector FY13: 0.5; DUSEL Detector FY14: 0.5; Mu2e FY15: 0.2; Mu2e FY16: 0.2; Mu2e FY17: 0.2; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 2; SRF / ILCTA-NML FY10: 3; SRF / ILCTA-NML FY11: 3; SRF / ILCTA-NML FY12: 3; SRF / ILCTA-NML FY13: 3; SRF / ILCTA-NML FY14: 3
|  | Electrical Designer | CMS Phase 1 Upgrade Construction FY10: 0.95; CMS Phase 1 Upgrade Construction FY11: 1.25; CMS Phase 1 Upgrade Construction FY12: 1.525; CMS Phase 1 Upgrade Construction FY13: 1.375; CMS Phase 2 Upgrade Construction FY10: 1.9; CMS Phase 2 Upgrade Construction FY11: 2.5; CMS Phase 2 Upgrade Construction FY12: 2.45; CMS Phase 2 Upgrade Construction FY13: 2.75; CMS Phase 2 Upgrade Construction FY14: 2.3; Mu2e FY09: 0.2; Mu2e FY10: 1.2006; Mu2e FY11: 1.5; Mu2e FY12: 1.2; Mu2e FY13: 0.6; Mu2e FY14: 0.1; Mu2e FY15: 0; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 1; SRF / ILCTA-NML FY11: 1; SRF / ILCTA-NML FY12: 1; SRF / ILCTA-NML FY13: 1; SRF / ILCTA-NML FY14: 1
|  | Electrical Drafter | Mu2e FY09: 0.10529; Mu2e FY10: 1.2006; Mu2e FY11: 1.5; Mu2e FY12: 1; Mu2e FY13: 0.5; Mu2e FY14: 0.1; Mu2e FY15: 0; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 1.8; Project X FY10: 3.6; Project X FY11: 3.6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Magnet Designer | ILC Accelerator FY09: 0.25; ILC Accelerator FY10: 0.25; ILC Accelerator FY11: 0.25; ILC Accelerator FY12: 0.25; ILC Accelerator FY13: 0.25; ILC Accelerator FY14: 0.25; ILC Accelerator FY15: 0.25; ILC Accelerator FY16: 0.25; ILC Accelerator FY17: 0.25; ILC Accelerator FY18: 0.25; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 1; SRF / ILCTA-NML FY11: 1; SRF / ILCTA-NML FY12: 1; SRF / ILCTA-NML FY13: 1; SRF / ILCTA-NML FY14: 1
|  | Mechanical Designer | CMS Phase 1 Upgrade Construction FY10: 2.2; CMS Phase 1 Upgrade Construction FY11: 2.5; CMS Phase 1 Upgrade Construction FY12: 2.4; CMS Phase 1 Upgrade Construction FY13: 2; CMS Phase 2 Upgrade Construction FY10: 2.4; CMS Phase 2 Upgrade Construction FY11: 3; CMS Phase 2 Upgrade Construction FY12: 2.8; CMS Phase 2 Upgrade Construction FY13: 3; CMS Phase 2 Upgrade Construction FY14: 2.4; HINS FY09: 2; HINS FY10: 1; HINS FY11: 0.5; HINS FY12: 0.25; HINS FY13: 0.1; HINS FY14: 0; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 1.5; ILC Accelerator FY10: 1.5; ILC Accelerator FY11: 1.5; ILC Accelerator FY12: 1.5; ILC Accelerator FY13: 1.5; ILC Accelerator FY14: 1.5; ILC Accelerator FY15: 1.5; ILC Accelerator FY16: 1.5; ILC Accelerator FY17: 1.5; ILC Accelerator FY18: 1.5; MicroBooNE FY09: 0.4; MicroBooNE FY10: 0.5; MicroBooNE FY11: 0.5; Mu2e FY09: 0.2; Mu2e FY10: 2.7847; Mu2e FY11: 1.2565; Mu2e FY12: 3.0488; Mu2e FY13: 0.33294; Mu2e FY14: 0; Mu2e FY15: 0; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 3; SRF / ILCTA-NML FY10: 3; SRF / ILCTA-NML FY11: 3; SRF / ILCTA-NML FY12: 3; SRF / ILCTA-NML FY13: 3; SRF / ILCTA-NML FY14: 3
|  | Mechanical Drafter | HINS FY09: 3; HINS FY10: 2; HINS FY11: 0.5; HINS FY12: 0.25; HINS FY13: 0.1; HINS FY14: 0; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 0.25; ILC Accelerator FY10: 0.25; ILC Accelerator FY11: 0.25; ILC Accelerator FY12: 0.25; ILC Accelerator FY13: 0.25; ILC Accelerator FY14: 0.25; ILC Accelerator FY15: 0.25; ILC Accelerator FY16: 0.25; ILC Accelerator FY17: 0.25; ILC Accelerator FY18: 0.25; Mu2e FY09: 0.2; Mu2e FY10: 2.7847; Mu2e FY11: 1.2565; Mu2e FY12: 3.0488; Mu2e FY13: 0.33294; Mu2e FY14: 0; Mu2e FY15: 0; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 4.8; Project X FY10: 8.4; Project X FY11: 10.8; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1; SRF / ILCTA-NML FY10: 2; SRF / ILCTA-NML FY11: 2; SRF / ILCTA-NML FY12: 2; SRF / ILCTA-NML FY13: 2; SRF / ILCTA-NML FY14: 2
| Electrical Technician | Electrical Assembly Technician | DUSEL Beamline FY10: 0.5; DUSEL Beamline FY11: 0.5; DUSEL Beamline FY12: 0.5; DUSEL Beamline FY13: 1; DUSEL Beamline FY14: 1; DUSEL Beamline FY15: 3; DUSEL Beamline FY16: 3; DUSEL Beamline FY17: 2; DUSEL Beamline FY18: 2; DUSEL Detector FY10: 0.5; DUSEL Detector FY11: 0.5; DUSEL Detector FY12: 0.5; DUSEL Detector FY13: 0.5; DUSEL Detector FY14: 0.5; Mu2e FY09: 0; Mu2e FY10: 0; Mu2e FY11: 0; Mu2e FY12: 0.79882; Mu2e FY13: 0.16471; Mu2e FY14: 0.030588; Mu2e FY15: 0.049412; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Electrical Interlock Technician | HINS FY09: 1; HINS FY10: 2; HINS FY11: 2; HINS FY12: 1; HINS FY13: 0.5; HINS FY14: 0; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Electrical Task Manager | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Electrical Technician | CMS Phase 1 Upgrade Construction FY10: 2; CMS Phase 1 Upgrade Construction FY11: 2; CMS Phase 1 Upgrade Construction FY12: 1.4; CMS Phase 1 Upgrade Construction FY13: 1; CMS Phase 2 Upgrade Construction FY10: 2; CMS Phase 2 Upgrade Construction FY11: 2; CMS Phase 2 Upgrade Construction FY12: 1.4; CMS Phase 2 Upgrade Construction FY13: 1; CMS Phase 2 Upgrade Construction FY14: 0.4; HINS FY09: 1.1; HINS FY10: 1.1; HINS FY11: 1.1; HINS FY12: 0.1; HINS FY13: 0.1; HINS FY14: 0; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 1; ILC Accelerator FY10: 1; ILC Accelerator FY11: 1; ILC Accelerator FY12: 1; ILC Accelerator FY13: 1; ILC Accelerator FY14: 1; ILC Accelerator FY15: 1; ILC Accelerator FY16: 1; ILC Accelerator FY17: 1; ILC Accelerator FY18: 1; Mu2e FY09: 0.1; Mu2e FY10: 0.2; Mu2e FY11: 0.52588; Mu2e FY12: 3.4288; Mu2e FY13: 1.7482; Mu2e FY14: 0.16; Mu2e FY15: 0.29; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 1.2; Project X FY10: 3; Project X FY11: 5.4; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 3; SRF / ILCTA-NML FY10: 3; SRF / ILCTA-NML FY11: 3; SRF / ILCTA-NML FY12: 3; SRF / ILCTA-NML FY13: 3; SRF / ILCTA-NML FY14: 3
|  | Electrical Technician Supervisor | ILC Accelerator FY09: 0.25; ILC Accelerator FY10: 0.25; ILC Accelerator FY11: 0.25; ILC Accelerator FY12: 0.25; ILC Accelerator FY13: 0.25; ILC Accelerator FY14: 0.25; ILC Accelerator FY15: 0.25; ILC Accelerator FY16: 0.25; ILC Accelerator FY17: 0.25; ILC Accelerator FY18: 0.25; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 0.5; SRF / ILCTA-NML FY11: 0.5; SRF / ILCTA-NML FY12: 0.5; SRF / ILCTA-NML FY13: 0.5; SRF / ILCTA-NML FY14: 0.5
|  | Electronics Technician | CMS Phase 1 Upgrade Construction FY10: 2.35; CMS Phase 1 Upgrade Construction FY11: 3.25; CMS Phase 1 Upgrade Construction FY12: 4.225; CMS Phase 1 Upgrade Construction FY13: 3.875; CMS Phase 2 Upgrade Construction FY10: 3.7; CMS Phase 2 Upgrade Construction FY11: 5.5; CMS Phase 2 Upgrade Construction FY12: 5.95; CMS Phase 2 Upgrade Construction FY13: 7.25; CMS Phase 2 Upgrade Construction FY14: 6.5; HINS FY09: 1; HINS FY10: 1; HINS FY11: 1; HINS FY12: 2; HINS FY13: 2; HINS FY14: 1; HINS FY15: 0.5; HINS FY16: 0.5; HINS FY17: 0.5; HINS FY18: 0.5; MicroBooNE FY10: 0.2; MicroBooNE FY11: 1; MicroBooNE FY12: 1.5; Mu2e FY09: 0.2; Mu2e FY10: 0.2; Mu2e FY11: 2; Mu2e FY12: 1.7412; Mu2e FY13: 1.1647; Mu2e FY14: 1.0306; Mu2e FY15: 1.0494; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Mechanical Technician | Cryo Technician | [21 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 2 | 6 | 6 | 3 |  |  | 0.5 | 0.5 | 0.5 | [5 empty] | 0.75 | 1 | 2 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1.2 | 1.1 | 2.7 | 1.5 |  | 0.6 | 1.2 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 7 | 7 | 7 | 7 | 7 | 3.5 | 3.5 | 3.5 | 3.5
|  | High Vac Technician | Mu2e FY09: 0; Mu2e FY10: 0.64706; Mu2e FY11: 0.7; Mu2e FY12: 1.5006; Mu2e FY13: 0.78941; Mu2e FY14: 0.32176; Mu2e FY15: 1.1541; Mu2e FY16: 0.13176; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 2; SRF / ILCTA-NML FY10: 2; SRF / ILCTA-NML FY11: 2; SRF / ILCTA-NML FY12: 2; SRF / ILCTA-NML FY13: 2; SRF / ILCTA-NML FY14: 2; SRF / ILCTA-NML FY15: 1.5; SRF / ILCTA-NML FY16: 1.5; SRF / ILCTA-NML FY17: 1.5; SRF / ILCTA-NML FY18: 1.5
|  | Mechanical Assembly Technician | CMS Phase 1 Upgrade Construction FY10: 1; CMS Phase 1 Upgrade Construction FY11: 1; CMS Phase 1 Upgrade Construction FY12: 0.7; CMS Phase 1 Upgrade Construction FY13: 0.5; CMS Phase 2 Upgrade Construction FY10: 1; CMS Phase 2 Upgrade Construction FY11: 1; CMS Phase 2 Upgrade Construction FY12: 0.7; CMS Phase 2 Upgrade Construction FY13: 0.5; CMS Phase 2 Upgrade Construction FY14: 0.2; HINS FY09: 5.75; HINS FY10: 6.75; HINS FY11: 5; HINS FY12: 3; HINS FY13: 1.5; HINS FY14: 0.5; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; MicroBooNE FY10: 0.3; MicroBooNE FY11: 2; MicroBooNE FY12: 6; MicroBooNE FY13: 4; MicroBooNE FY14: 0.2; MicroBooNE FY15: 0.3; Mu2e FY09: 0.5; Mu2e FY10: 1.3; Mu2e FY11: 1.3; Mu2e FY12: 2.4406; Mu2e FY13: 1.3; Mu2e FY14: 0.18706; Mu2e FY15: 0.11529; Mu2e FY16: 1.3; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Mechanical Instrument Technician | HINS FY09: 2; HINS FY10: 2; HINS FY11: 2; HINS FY12: 2; HINS FY13: 2; HINS FY14: 1; HINS FY15: 0.2; HINS FY16: 0.2; HINS FY17: 0.2; HINS FY18: 0.2; Mu2e FY09: 0.1; Mu2e FY10: 0.4; Mu2e FY11: 0.18118; Mu2e FY12: 0.25412; Mu2e FY13: 0.39294; Mu2e FY14: 0.32471; Mu2e FY15: 0.028235; Mu2e FY16: 0; Mu2e FY17: 0; Mu2e FY18: 0; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1; SRF / ILCTA-NML FY10: 1; SRF / ILCTA-NML FY11: 1; SRF / ILCTA-NML FY12: 1; SRF / ILCTA-NML FY13: 1; SRF / ILCTA-NML FY14: 1; SRF / ILCTA-NML FY15: 0.3; SRF / ILCTA-NML FY16: 0.3; SRF / ILCTA-NML FY17: 0.3; SRF / ILCTA-NML FY18: 0.3
|  | Mechanical SRF Technician | ILC Accelerator FY09: 5; ILC Accelerator FY10: 5; ILC Accelerator FY11: 5; ILC Accelerator FY12: 5; ILC Accelerator FY13: 5; ILC Accelerator FY14: 5; ILC Accelerator FY15: 5; ILC Accelerator FY16: 5; ILC Accelerator FY17: 5; ILC Accelerator FY18: 5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 7; SRF / ILCTA-NML FY10: 8; SRF / ILCTA-NML FY11: 8; SRF / ILCTA-NML FY12: 8; SRF / ILCTA-NML FY13: 8; SRF / ILCTA-NML FY14: 8; SRF / ILCTA-NML FY15: 3; SRF / ILCTA-NML FY16: 3; SRF / ILCTA-NML FY17: 3; SRF / ILCTA-NML FY18: 3
|  | Mechanical Systems Technician | CMS Phase 1 Upgrade Construction FY10: 1.3; CMS Phase 1 Upgrade Construction FY11: 1.75; CMS Phase 1 Upgrade Construction FY12: 2.2; CMS Phase 1 Upgrade Construction FY13: 2; CMS Phase 2 Upgrade Construction FY10: 1.6; CMS Phase 2 Upgrade Construction FY11: 2.5; CMS Phase 2 Upgrade Construction FY12: 2.8; CMS Phase 2 Upgrade Construction FY13: 3.5; CMS Phase 2 Upgrade Construction FY14: 3.2; Mu2e FY09: 0; Mu2e FY10: 0.5; Mu2e FY11: 1; Mu2e FY12: 1; Mu2e FY13: 1; Mu2e FY14: 0.5; Mu2e FY15: 0.3; Mu2e FY16: 2; Mu2e FY17: 0.2; Mu2e FY18: 0; Project X FY09: 1.2; Project X FY10: 6; Project X FY11: 6; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Mechanical Task Manager | CMS Phase 1 Upgrade Construction FY10: 1.2; CMS Phase 1 Upgrade Construction FY11: 1.5; CMS Phase 1 Upgrade Construction FY12: 1.7; CMS Phase 1 Upgrade Construction FY13: 1.5; CMS Phase 2 Upgrade Construction FY10: 1.4; CMS Phase 2 Upgrade Construction FY11: 2; CMS Phase 2 Upgrade Construction FY12: 2.1; CMS Phase 2 Upgrade Construction FY13: 2.5; CMS Phase 2 Upgrade Construction FY14: 2.2; MicroBooNE FY12: 0.5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Mechanical Technician Supervisor | HINS FY09: 1; HINS FY10: 1; HINS FY11: 1; HINS FY12: 0.5; HINS FY13: 0.5; HINS FY14: 0.1; HINS FY15: 0; HINS FY16: 0; HINS FY17: 0; HINS FY18: 0; ILC Accelerator FY09: 1.5; ILC Accelerator FY10: 1.5; ILC Accelerator FY11: 1.5; ILC Accelerator FY12: 1.5; ILC Accelerator FY13: 1.5; ILC Accelerator FY14: 1.5; ILC Accelerator FY15: 1.5; ILC Accelerator FY16: 1.5; ILC Accelerator FY17: 1.5; ILC Accelerator FY18: 1.5; MicroBooNE FY11: 0.3; MicroBooNE FY12: 0.5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 2; SRF / ILCTA-NML FY10: 2; SRF / ILCTA-NML FY11: 2; SRF / ILCTA-NML FY12: 2; SRF / ILCTA-NML FY13: 2; SRF / ILCTA-NML FY14: 2; SRF / ILCTA-NML FY15: 0.5; SRF / ILCTA-NML FY16: 0.5; SRF / ILCTA-NML FY17: 0.5; SRF / ILCTA-NML FY18: 0.5
| Operations | Accelerator Operator | HINS FY09: 0.5; HINS FY10: 1; HINS FY11: 1; HINS FY12: 2; HINS FY13: 2; HINS FY14: 2; HINS FY15: 2; HINS FY16: 2; HINS FY17: 2; HINS FY18: 2; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Accelerator Systems Specialist | HINS FY09: 1; HINS FY10: 1; HINS FY11: 1; HINS FY12: 1; HINS FY13: 1; HINS FY14: 1; HINS FY15: 1; HINS FY16: 1; HINS FY17: 1; HINS FY18: 1; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Operations Manager | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Operations Specialist | Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
| Other Technical | Construction Manager | DUSEL Beamline FY12: 0.5; DUSEL Beamline FY13: 1; DUSEL Beamline FY14: 1; DUSEL Beamline FY15: 1; DUSEL Beamline FY16: 1; DUSEL Beamline FY17: 1; DUSEL Beamline FY18: 1; MicroBooNE FY11: 0.2; MicroBooNE FY12: 0.2; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0
|  | Fabrication Specialist | ILC Accelerator FY09: 0.5; ILC Accelerator FY10: 0.5; ILC Accelerator FY11: 0.5; ILC Accelerator FY12: 0.5; ILC Accelerator FY13: 0.5; ILC Accelerator FY14: 0.5; ILC Accelerator FY15: 0.5; ILC Accelerator FY16: 0.5; ILC Accelerator FY17: 0.5; ILC Accelerator FY18: 0.5; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 0.5; SRF / ILCTA-NML FY11: 0.5; SRF / ILCTA-NML FY12: 0.5; SRF / ILCTA-NML FY13: 0.5; SRF / ILCTA-NML FY14: 0.5
|  | Machinist | ILC Accelerator FY09: 0.5; ILC Accelerator FY10: 0.5; ILC Accelerator FY11: 0.5; ILC Accelerator FY12: 0.5; ILC Accelerator FY13: 0.5; ILC Accelerator FY14: 0.5; ILC Accelerator FY15: 0.5; ILC Accelerator FY16: 0.5; ILC Accelerator FY17: 0.5; ILC Accelerator FY18: 0.5; MicroBooNE FY10: 0.1; MicroBooNE FY11: 0.55; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 0.5; SRF / ILCTA-NML FY11: 0.5; SRF / ILCTA-NML FY12: 0.5; SRF / ILCTA-NML FY13: 0.5; SRF / ILCTA-NML FY14: 0.5; SRF / ILCTA-NML FY15: 0; SRF / ILCTA-NML FY16: 0; SRF / ILCTA-NML FY17: 0; SRF / ILCTA-NML FY18: 0
|  | QC Technical | ILC Accelerator FY09: 0.25; ILC Accelerator FY10: 0.25; ILC Accelerator FY11: 0.25; ILC Accelerator FY12: 0.25; ILC Accelerator FY13: 0.25; ILC Accelerator FY14: 0.25; ILC Accelerator FY15: 0.25; ILC Accelerator FY16: 0.25; ILC Accelerator FY17: 0.25; ILC Accelerator FY18: 0.25; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.5; SRF / ILCTA-NML FY10: 0.5; SRF / ILCTA-NML FY11: 0.5; SRF / ILCTA-NML FY12: 0.5; SRF / ILCTA-NML FY13: 0.5; SRF / ILCTA-NML FY14: 0.5
|  | Quality Assurance | CMS Phase 1 Upgrade Construction FY10: 1; CMS Phase 1 Upgrade Construction FY11: 1; CMS Phase 1 Upgrade Construction FY12: 0.7; CMS Phase 1 Upgrade Construction FY13: 0.5; CMS Phase 2 Upgrade Construction FY10: 1; CMS Phase 2 Upgrade Construction FY11: 1; CMS Phase 2 Upgrade Construction FY12: 0.7; CMS Phase 2 Upgrade Construction FY13: 0.5; CMS Phase 2 Upgrade Construction FY14: 0.2; ILC Accelerator FY09: 0.25; ILC Accelerator FY10: 0.25; ILC Accelerator FY11: 0.25; ILC Accelerator FY12: 0.25; ILC Accelerator FY13: 0.25; ILC Accelerator FY14: 0.25; ILC Accelerator FY15: 0.25; ILC Accelerator FY16: 0.25; ILC Accelerator FY17: 0.25; ILC Accelerator FY18: 0.25; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 0.25; SRF / ILCTA-NML FY10: 0.25; SRF / ILCTA-NML FY11: 0.25; SRF / ILCTA-NML FY12: 0.25; SRF / ILCTA-NML FY13: 0.25; SRF / ILCTA-NML FY14: 0.25
|  | Welder | ILC Accelerator FY09: 1; ILC Accelerator FY10: 1; ILC Accelerator FY11: 1; ILC Accelerator FY12: 1; ILC Accelerator FY13: 1; ILC Accelerator FY14: 1; ILC Accelerator FY15: 1; ILC Accelerator FY16: 1; ILC Accelerator FY17: 1; ILC Accelerator FY18: 1; MicroBooNE FY11: 0.1; MicroBooNE FY12: 0.2; Project X FY09: 0; Project X FY10: 0; Project X FY11: 0; Project X FY12: 0; Project X FY13: 0; Project X FY14: 0; Project X FY15: 0; Project X FY16: 0; Project X FY17: 0; Project X FY18: 0; SRF / ILCTA-NML FY09: 1.5; SRF / ILCTA-NML FY10: 1.5; SRF / ILCTA-NML FY11: 1.5; SRF / ILCTA-NML FY12: 1.5; SRF / ILCTA-NML FY13: 1.5; SRF / ILCTA-NML FY14: 1.5; SRF / ILCTA-NML FY15: 0; SRF / ILCTA-NML FY16: 0; SRF / ILCTA-NML FY17: 0; SRF / ILCTA-NML FY18: 0
Grand Total |  |  |  | 23.1 | 26.25 | 26.1 | 22.5 | [6 empty] | 27.2 | 33.5 | 31.7 | 34 | 28 |  |  |  |  | 6.55 | 12.6 | 20.1 | 25.6 | 31 | 31 | 32 | 36 | 33 | 30 | 2.1 | 6.5 | 8.75 | 10.5 | 10.5 | 9 | 7 | 7 | 7 | 7 | 42.15 | 42.9 | 38.55 | 29.05 | 20.85 | 13.95 | 10.25 | 9.25 | 9.25 | 9.25 | 37.11 | 37.11 | 37.11 | 37.11 | 37.11 | 37.11 | 37.11 | 37.11 | 37.11 | 37.11 | 5.15 | 7.6 | 12.5 | 15.15 | 10.15 | 4.4 | 3.8 | 3.5 | 3.5 | 3.5 | 16.1747 | 44.7053 | 51.2506 | 60.2612 | 41.6618 | 33.4094 | 32.0229 | 25.4153 | 2.3259 | 0 | 39.4 | 69.1 | 89.2 | 16 | 19 | 19 | 19 | 19 | 17 | 6 | 61 | 70 | 70 | 70 | 70 | 70 | 20.5 | 20.5 | 20.5 | 20.5

## Old Project X Tier 1 Input
Project/Program Name | Functional Discipline | Functional Category - Tier 1 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
Project X | Administration | Communications | 0 | 1 | 1 | 1 | 1 | 1 | 1
Project X | Administration | Finance | 0 | 2 | 4 | 4 | 4 | 4 | 2
Project X | Administration | Human Resources | 0 | 2 | 2 | 2 | 1 | 1 | 1
Project X | Administration | Other Administration | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project X | Administration | Procurement | 0 | 2 | 2 | 2 | 2 | 1 | 1
Project X | Administration | Project Management
Project X | Engineer | Civil Engineer | 1.8 | 9 | 6.18 | 6.18 | 6.18 | 6.18 | 6.18
Project X | Engineer | Electrical Engineer | 7.8 | 9 | 10.8 | 10.8 | 10.8 | 10.8 | 7.8
Project X | Engineer | Mechanical Engineer | 22.8 | 15 | 12 | 12 | 12 | 12 | 9
Project X | ES&H | ES&H | 1 | 2 | 2 | 2 | 2 | 2 | 2
Project X | Facilities Mgmt | Facilities Management | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project X | Information Technology | Information Technology | 4.8 | 4.2 | 3 | 3 | 2.4 | 1.8 | 1.8
Project X | Scientific | Scientist | 19.2 | 15 | 13.8 | 12 | 12 | 12 | 9.6
Project X | Technical | Alignment | 0 | 0 | 0 | 1.2 | 2.4 | 4.8 | 4.8
Project X | Technical | Design | 15 | 15 | 10.2155 | 9.9079 | 9.7304 | 3.9663 | 2.6595
Project X | Technical | Electrical Technician | 6 | 7.2 | 12 | 15.7098 | 26.3489 | 26.3736 | 17.016
Project X | Technical | Mechanical Technician | 8.4 | 8.4 | 11.4 | 14.8878 | 31.6835 | 32.9424 | 23.184
Project X | Technical | Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project X | Technical | Other Technical | 0 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
|  | Totals: | 87.8 | 93.4 | 91.9955 | 98.2855 | 125.1428 | 121.4623 | 90.6395

## Functional Definitions
Functional Discipline | Functional Category | Functional Role | Functional Skills | Functional Resource Role Definition | HR Related Job Titles (May not be all inclusive)
| Tier 1 | Tier2 | Tier 3
Administration | Communications | Media Services |  | Provides duplicating, photography, A/V support, video production, graphic arts and FTP services for employees and users.
|  | Public Relations |  | Manage flow of information between Fermilab and the publics.
| Finance | Accounting-Accountant |  | Supports maintaining the books and records of the Laboratory primarily through analysis, recording, and reporting and the application of generally accepted accounting principles, in accordance with DOE and other applicable regulations.
|  | Accounting-Clerical |  | Supports maintaining the books and records of the Laboratory primarily through transaction processing activities, including but not limited to payroll, accounts payable disbursements, inventory, receivables and cash.
|  | Operations Finance |  | Manages budget, finance & reporting for Divisions, Sections and Centers, or the Lab as a whole. Has strong analytical skills to analyze and act in response to the financial reports.
| Human Resources | Benefits |  | Plans, develops, administers benefits, wellness and recreation programs.
|  | Compensation |  | Develops and analyzes salary administration programs and policies.
|  | Early Childhood Education |  | Administers day care program for infants through kindergarden children.
|  | Education |  | Develops and implements scientific educational programs for K through 12.
|  | Employee/Labor Relations |  | Handles employee problems, discipline, and grievance issues and union contract negotiation.
|  | Equal Opportunity |  | Handles discrimination complaints and cases, Affirmative Action compliance, and diversity.
|  | HRIS |  | Keeps employee data bases and records.
|  | Human Resources Generalist |  | Functions in more than one HR functional group.
|  | International Human Resources |  | Processes visas and develops programs and policies for long term assignments.
|  | Recruitment |  | Hires and orients new employees.
| Other Administration | Administrative Support |  | Provides clerical/administrative assistance and support by performing duties, tasks, and assignments supporting operations or project activities. | Administrative Support Assistant I, Administrative Support Assistant II, Administrative Support Assistant III, Administrative Support Assistant IV, Administrative Support Assistant V, Supervisor, Administrative Support, Administrative Associate , Administ
|  | Audit |  | Support the performance of audits to monitor the adequacy, effectiveness and performance of the internal controls and ensure prudent business practices and compliance with the Prime Contract between FRA and the Department of Energy. | Audit Analyst, Audit Services Manager, Audit Specialist, IT Audit Analyst, IT Audit Specialist
|  | Executive Direction |  | Includes functions associated with the executive level of management as determined by the Manager III designation.
|  | General Administrative |  | Primary responsibility to coordinate and support Lab events like conferences, accelerator school and cultural events.
|  | Legal |  | Provides legal support to Laboratory management and staff concerning all aspects of Laboratory operations. | Chief Legal Counsel, Deputy Chief Legal Counsel, Senior Staff Attorney, Staff Attorney
|  | Library |  | Supports the operation of the library, including acquisition, circulation, classification, indexing, cataloging, research and search requests.
|  | Training |  | Primary responsible to organizing, developing or conduction training.
|  | Travel |  | Primary responsible for making business travel arrangements for employees and users.
| Procurement | Procurement |  | Procures equipment, materials and services in support of the project including Reqs, RFPs, RFQs RFIs and POs.
| Project Management | Project Controls |  | Develops, analyzes ,and maintains project Resource Loaded Schedules (RLS). Sets up, maintains, and reports on the project’s Earned Value Management.
|  | Project Finance |  | Manages budget, finance & reporting for Projects. Has strong analytical skills to analyze and act in response to the financial reports. Familiar with Earned Value Management System and project scheduling.
|  | Project Manager |  | Manages projects by establishing project objectives, coordinating project activities, leading project staff, and implementing the project plan. This type of person may have a title of Project Manager, Deputy Project Manager or Associate Project Manager.
|  | Project Support |  | Provides project management support to one or multiple projects and the project support role is in other areas than as a Project Controls, Project Finance and Project Manager. The individual can be a member of a project’s or Division’s project management
Engineer | Civil Engineer | CFS Design Engineer | Architect | Perform site planning, space planning and facility design for personnel and experiments. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Civil Engineer | Perform site planning, wetland mitigation and design of roads, parking, utilities and grading; shielding design and documentation. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Electrical Engineer | Design of site wide high & medium voltage and facility medium & low voltage power distribution. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Fire Protection Engineer | Design of facility fire detection/suppression systems; life safety studies. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Mechanical Engineer | Design of site wide process and domestic water systems; facility HVAC systems; control systems. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Structural Engineer | Design of building and underground enclosure structures; equipment supports. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | CFS Operations Engineer | Electrical Engineer (O&M) | Operation/maintenance of site wide high & medium voltage and facility medium & low voltage power distribution. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Fire Protection Engineer (O&M) | Operation/testing/maintenance of facility fire detection/suppression systems. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Mechanical Engineer (O&M) | Operation/maintenance of site wide process and domestic water systems; facility HVAC systems; building control systems. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | CFS Technical Manager | Administrative Management | Management of facility design and construction groups or departments. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Project Management | Management of project specific facility design and construction activities. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
| Electrical Engineer | ASIC Design Engineer | Analog ASIC | Design and oversee fabrication of integrated circuits used in analog applications (experiment data acquisition) | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Digital ASIC | Design and oversee fabrication of integrated circuits used for digital applications (Digital Signal Processing, Clock systems, etc. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Control System Engineer | Data Acquisition | Design and oversee construction and integration of systems to provide control or data acquisition for accelerators or experiments | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Embedded processing | Design and oversee construction, testing and programming of microprocessors used in embedded portions of data acquisition systems | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Process control | Design and oversee the implementation of PLC systems used in processes for monitoring and control | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Electrical Design Engineer | DC Power Supply and Distribution | Design and oversee the installation of DC Power supplies with respect to AC supply distribution and magnet distribution. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | High-voltage AC Distribution | Design, specify and monitor AC distribution systems. 345KV, 13.8KV, 480V typically used on site. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Magnet design | Design, specify and oversee construction of magnets used in accelerators, beam transport lines and for pulsed power applications. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Magnet Systems Power Supply | Design, specify and oversee construction of DC High Current, High Precision power supplies used in accelerators and beam transport lines. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Pulsed Power | Design, specify and oversee construction of pulsed power systems such as Kickers or Modulators. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Electrical Technical Manager | Administrative Management | Manage electrical engineering teams and departments. Includes leadership skills, budgeting skills, resource management skills, and personnel management skills. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Project Management | Manage medium to large projects with responsibilities ranging from guiding engineers through review processes to overseeing and compiling cost and schedule estimates. Includes leadership/management skills as well as a good understanding of ES&H requirements. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Electronics Design Engineer | Beam instrumentation | Design and oversee construction of systems for monitoring beam characteristics profile, intensity, position, etc. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Flexible and hybrid circuits | Design and oversee construction of hybrid circuits used in detector systems | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | High-speed digital | Design and oversee the implementation of high speed processing systems used for direct control of high speed feedback systems (stochastic cooling, beam dampers etc.) | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Low-noise analog | Design and oversee the implementation of systems used to acquire signals from accelerator or experimental detectors | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Interlock Engineer | Safety interlock system | Design and oversee construction of the Machine and Personnel Safety systems used to ensure safe operations. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | RF Design Engineer | High-level RF | Design and oversee construction of the High Power RF systems for Accelerators | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Low-level RF | Design and oversee construction of low power, high speed systems to control RF to be applied to Accelerators | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
| Mechanical Engineer | Cryogenics Engineer | Cryogenic Components | Design cryostats and cryogenic transport systems for superconducting magnetic and RF devices. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Cryogenic Process Systems | Analyze and design cryogenic process systems. Develop heat load estimates and modify process cycles to match system requirements. Skilled in operations and commissioning of cryogenic systems. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | SRF Systems | Design superconducting RF cavities, feedthroughs, and associated components for SRF systems. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Magnet Design Engineer | NC Magnets | Design normal conducting magnetic devices with high current carrying elements, high voltages, vacuum, and water cooling. Magnetic devices may operate DC, ramped, pulsed, or faster. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | SC Magnets | Design superconducting magnetic devices with high precision mechanical components, current carrying elements, high voltages, vacuum, and cryogenic cooling. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Materials Engineer | Material Science | Work with material behavior and failure in various loading and exposure environments. Can include knowledge of common metals and plastics as well as more exotic materials and ceramics, fracture mechanics, materials testing, and rate dependent processes such as creep. Can include science of materials joining techniques such as welding/brazing/diffusion bonding/adhesives. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Mechanical Analysis Engineer | Mechanical Analysis/FEA | High level analytical skills required to build analytic or numerical models to simulate complex and/or coupled field analyses of challenging mechanical engineering problems. Usually involves FEA skills, especially involving coupled field analysis (electro-thermal-structural), elastic-plastic analysis, and time/rate dependent analysis. Skilled at the magnetic design of devices using analytical and computational tools to model DC and AC performance. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Mechanical Design Engineer | Accelerator Technology | Design and build accelerator machines, beamlines, and tunnels. Skilled at laying out machine elements, alignment concerns, remote positioning techniques, and overseeing installation. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Detector Technology | Design and build HEP detectors and associated systems. Skilled at conceptual and detailed design of common detector sub-system technology such as silicon tracking and calorimetry. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | General Mech Design | Design and fabricate mechanical components and systems including familiarity with machine elements, strength of materials, theoretical applied mechanics, heat and mass transfer, material failure criteria, and industrial fabrication techniques and methods. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Structural Design | Design and fabricate large load bearing structures and equipment using applicable codes and standards such as the AISC ASD. Requires knowledge of common construction and fabrication practices. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Target Technology | Design HEP target and focusing systems and components including Radioactive Component Handling techniques and procedures. Includes design and construction of components and systems that can survive the high energy density, temperatures, radiation, and pulsed nature of HEP targets. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | UH Vacuum | Design and fabricate ultra-high vacuum systems and components compatible with particle free, ultra high vacuum requirements. Includes everything from out gassing calculations and pump sizing, to RGA analysis and clean room procedures. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Mechanical Technical Manager | Administrative Management | Manage mechanical engineering teams and departments. Includes leadership skills, budgeting skills, resource management skills, and personnel management skills. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Project Management | Manage medium to large projects with responsibilities ranging from guiding engineers through review processes to overseeing and compiling cost and schedule estimates. Includes leadership/management skills as well as a good understanding of ES&H requirements. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  | Process/Controls Engineer | Chemical Systems | Design and analyze chemical processes and systems such as electropolishing and chemical etching. Also includes skills involved in water treatment and polymer blending for detector components. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Fluid/Pressure Systems | Design, fabricate and operate small and large fluid and gas systems and components including code stamped vessels, piping, pump sizing, heat and mass transfer and a working knowledge of applicable codes and standards such as ASME BPV code and ASME B31 piping code series. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Instrumentation/Controls | Work with sensors, electronics, electromechanical devices, etc. for measuring, monitoring, and controlling processes and performance of devices during fabrication, testing, and use. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Operational M&D | Operate, maintain, and upgrade operational systems and equipment including trouble-shooting, crisis management, problem solving, and other "in the field" talents. Still requires good working/engineering knowledge of the systems and equipment. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
|  |  | Quality Assurance | Trained and certified in Quality Assurance techniques including developing procedures and controlling associated data. | Engineer I, Engineer II, Engineer III, Engineer IV, Engineer V, Engineering Associate, Engineering Associate Sr., Engineering Physicist I, Engineering Physicist II, Engineering Physicist III, Engineering Physicist Manager, Senior Engineering Physicist, Gu
ES&H | ES&H | Construction Safety |  | Oversees design and safety of construction projects
|  | Electrical Safety |  | Consults on electrical safety design and operations
|  | Emergency Planner |  | Coordinates lab-wide emergency planning and response
|  | Environmental |  | Consults on environmental compliance issues, obtains environmental permits, conducts environmental monitoring, or audits environmental program elements
|  | General ES&H |  | An ES&H professional who does not work predominantly in one particular discipline but support all disciplines????
|  | Industrial Hygienist |  | Consults on industrial hygiene issues and audits compliance with industrial hygiene –related regulations
|  | Laboratory Analysis |  | Analyses radioactive samples
|  | Occupational Medicine Nurse |  | Performs wide variety of nursing functions and health counseling
|  | Occupational Medicine Physician |  | Performs wide variety of physician functions and health counseling
|  | Radiation Protection |  | Consults on radiation safety issues and audits compliance with radiation–related regulations
|  | Safety |  | Consults on safety issues and audits compliance with safety–related regulations
|  | Waste Management |  | Collects, characterizes, prepares for disposal, and ships radioactive and hazardous waste
Facilities Mgmt | Facilities Management | Building Services |  | Perform building management activities to identify, procure, request, perform and coordinate delivery of maintenance and services to tenants.
|  | Business Administration |  | Provide business management to all functions.
|  | Carpenter |  | Perform and coordinate carpentry type or related services.
|  | Communications/Dispatcher |  | Answers phones and dispatches Fire Department and Security.
|  | Construction Coordinator |  | Coordinates, oversees, and inspects fixed price construction projects.
|  | Driver |  | Transports materials.
|  | Facilities Mgmt. |  | Real property management activities for buildings and infrastructure.
|  | Firefighter |  | Responds to fire alarms/emergency situations and checks fire protection systems.
|  | Groundskeeping |  | Upkeep and management of natural resources, herbicide application, maintenance of roads, parking lots, and ditches, winter safety activities.
|  | Housing/ Accommodations |  | Provide housing accommodations to users/visitors. Manage Food Services.
|  | Logistics |  | Provide Shipping, Receiving, transportation of goods, and Mailroom Services.
|  | Maintenance |  | Perform or coordinate upkeep and preservation of real property assets including specialized repair and maintenance activities.
|  | Material Services |  | Inventory and control of government owned personal property.
|  | Mechanic |  | Maintenance and repair of motor vehicles.
|  | Security |  | Provide Site-wide security/emergency response.
|  | Telecommunication |  | Coordinate site-wide telecom/radio/paging services.
Information Technology | Information Technology | Applications Development & Systems Analyst |  | Analysis & documentation of user needs; design, development, testing and documentation of software solutions; deployment of new or integration with existing applications; support developed applications and infrastructure software. | Applications Development & Systems Analyst I, Applications Development & Systems Analyst II, Applications Development & Systems Analyst III, Applications Development & Systems Analyst IV, Applications Development & Systems Analyst V, Applications Developm
|  | Communications Website Coordinator |  | Responsible for ensuring that a major project’s web site meets and supports the changing needs of the project’s management and collaborating communities. | Communications Website Coordinator
|  | Computational Physics Developer |  | Formulates and defines system scope and objectives, and participates as high level technical expert in design, development, coding, testing, and debugging new software or significant enhancements to existing software. Devises or modifies procedures to solve complex problems considering needs and methodologies of physics analysis and/or computational modeling. Works with technical staff and scientists to understand problems with software and develops specifications to resolve them. | Computational Physics Developer I, Computational Physics Developer II, Computational Physics Developer III, Computational Physics Developer IV, Computational Physics Developer V
|  | Computer Customer Support |  | Responds to and diagnoses problems for the Laboratory's computing systems users in the areas of hardware, software and warranty/service availability. Uses the problem management database and help desk systems. Applies broad knowledge of computing equipment and systems used at the Laboratory and specialist services provided by the Computing Division both in house and under service contracts. | Computer Customer Support Representative, Computer Customer Support Representative Manager, Computer Customer Support Representative Senior
|  | Computer Science Researcher |  | Research and develop new IT techniques and methodologies. Model system requirements and trends. Analyze emerging technologies for projects. Advise and consult on planning, evaluations and | Computer Science Researcher I, Computer Science Researcher II, Computer Science Researcher III
|  | Computer Security Analyst |  | Planning, organization and management of security requirements for the IT complex; testing and enhancement of security tools deployed; monitoring of compliance with and enforcement of computer security policies; security incident/breach response and investigation. | Computer Security Analysis & Architecture Manager, Computer Security Analyst I, Computer Security Analyst II, Computer Security Architect
|  | Computing Services Specialist |  | Planning, definition, evaluation, operation, administration, analysis, documentation, deployment, recommendation, testing, scheduling and coordination of system and service software upgrades deployment; maintenance of the integrity of systems environments; ensuring systems compliance with current security requirements; monitoring and tuning of systems for performance and reliability, | Computing Services Architect I, Computing Services Architect II, Computing Services Manager I, Computing Services Manager II, Computing Services Specialist I, Computing Services Specialist II, Computing Services Specialist III, Computing Services Speciali
|  | Database Administration Analyst |  | Administration & control of databases; includes collection and analysis of performance and usage information, data planning, development and the establishment of policies and procedures pertaining to data management, security, maintenance, data integrity and utilization, tuning of database parameters. | Database Administration Analysis Manager, Database Administrator Analyst I, Database Administrator Analyst II, Database Administrator Analyst III, Database, Administrator Analyst IV
|  | Functional Analyst |  | Based on in-depth knowledge of functional activities - analysis, evaluation and documentation of revisions for existing or proposed new systems to enable specialized business functions; deployment of computer programs, systems and related procedures to process specialized (function specific?) business data. | Functional Analyst I, Functional Analyst II, Functional Analyst III
|  | Network Analyst |  | Planning, definition, recommendation and deployment of new network systems; monitoring, evaluation of performance and security of existing network systems; recommendation for and deployment of improvement/upgrade of existing systems. | Network Analysis & Architecture Manager I, Network Analysis & Architecture Manager II, Network Analyst I, Network Analyst II, Network Analyst III, Network Architect I, Network Architect II
|  | PC Support Associate |  | Performs and applies fundamental knowledge of computing activities and assignments, which may include computing hardware, software, systems, networks, and/or applications. | PC Support Associate I, PC Support Associate II, PC Support Associate III
|  | Systems Administrator |  | Planning, definition, evaluation, operation, administration, analysis, documentation, deployment, recommendation, testing, scheduling and coordination of system and service software upgrades deployment; maintenance of the integrity of systems environments; ensuring systems compliance with current security requirements; monitoring and tuning of systems for performance and reliability, | Systems Administration Manager, Systems Administrator I, Systems Administrator II, Systems Administrator III, Systems Administrator IV
|  | Web Applications Developer |  | Design, deployment and maintenance of web site content and infrastructure; design and development of programs and databases for website(s), user interface features and special-effect elements, scripts and programs for special web projects. | Web Applications Developer I, Web Applications Developer II, Web Development & Operations Manager
Scientific | Scientist | Accelerator Physicist Experimental |  |  | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
|  | Accelerator Physicist Theory |  |  | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
|  | Chemist |  |  | Materials Scientist I, Materials Scientist II, guest scientist
|  | Magnet Scientist |  | Engages in physics research related to magnet design and development; has a scientific appointment at a national laboratory, or a faculty or research position at a University; typically requires a PhD | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
|  | Particle Physicist Experimental |  |  | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
|  | Particle Physicist Theory |  |  | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
|  | Particle-Astro Physicist Experimental |  |  | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
|  | Particle-Astro Physicist Theory |  |  | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
|  | RF Scientist |  |  | Applications Physicist I, Applications Physicist II, Applied Scientist I, Applied Scientist II, Applied Scientist III, Associate Scientist, Research Associate, Scientist I, Scientist II, Scientist III, guest scientist
Technical | Alignment | Geodesist | Alignment Coordinator | Provides oversight to alignment activities, lays out coordinate systems and global alignment strategies and performs numerical translations of collected data
|  | Metrologist | Alignment | Use optical and laser tracker surveying equipment to measure and align devices an layout coordinate systems
| Design | Cryo Designer | Cryogenic Design | Design and document cryogenic devices, system components, piping layouts and P&ID
|  | Electrical Designer | Elec General Design | Provide high level electrical design for electrical equipment, power sources, cable routing, controls and PC boards
|  | Electrical Drafter | Electrical drafting | Prepare detail drawings for applications such as electrical power distribution, electrical panel menus, single-line electrical drawings
|  |  | Electro-mechanical drafting | Prepare detail drawings for infrastructure items such as chassis, panels, cables, and enclosures
|  |  | Flexible & hybrid circuit layout | Implement the layout for the interconnecting copper traces for flexible and hybrid circuits
|  |  | Printed circuit board layout | Implement the layout for the interconnecting copper traces for components on printed circuit boards
|  | Magnet Designer | Magnet Design | Design superconducting or normal conducting magnet coil packages, mechanical systems and cryostats
|  | Mechanical Designer | 3D CAD General Design | 3D solid part and general assembly modeling
|  |  | Complex Assemblies / Weldments | Coordinate or layout complex assemblies and systems. Design and document welded assemblies
|  |  | Detector Technology | Design complex detector systems including silicon tracking detectors, calorimeters and chambers
|  |  | UHV/HV Design | Design and document High Vacuum and Ultra High Vacuum systems, including particle free clean room systems
|  | Mechanical Drafter | 2D CAD General Design | Creation of 2D CAD production drawings and layouts
| Electrical Technician | Electrical Assembly Technician | Circuit board assembly | Solder electronic components to printed circuit boards
|  |  | Electro-mechanical fabrication | Fabricate and assemble infrastructure items such as cables, chassis, panels and enclosures
|  |  | Wire-bonding | Operate wire-bonding machine to make electrical connections to IC chip pads
|  | Electrical Interlock Technician | Safety interlock system | Interlock system development, maintenance, repair
|  | Electrical Task Manager | Elec Task Management | Provide oversight and knowledge of electrical contracts
|  | Electrical Technician | Operations & maintenance | Provide electrical operations and maintenance support for major accelerator or experimental systems
|  |  | Power Systems | Power supply development, maintenance, repair
|  |  | Pulsed Power | Support the development, construction and maintenance of pulsed power systems such as Kickers or Modulators.
|  |  | RF Power | Support the development, construction and maintenance of the High Power RF systems for Accelerators
|  | Electrical Technician Supervisor | Supervise technicians | Supervise a group of electrical technicians
|  | Electronics Technician | Analog development | Assemble, checkout, troubleshoot, install and maintain analog electronics
|  |  | Computer programming | Write programs for embedded processing and FPGA applications
|  |  | Digital development | Assemble, checkout, troubleshoot, install and maintain digital electronics
|  |  | Electronics repair | Troubleshoot and repair broken electronics equipment
| Mechanical Technician | Cryo Technician | Cryogenic Fabrication / Operation | Skilled at fabrication of cryogenic components and/or operation and maintenance of cryogenic refrigeration systems.
|  | High Vac Technician | Vacuum | Fabricate and operate vacuum systems including Helium Leak Detection and Residual Gas Analyzer. Provide skill in selection of material, cleaning, vacuum degassing, leak detection, clean assembly, use of RGA, and the analysis from the associated RGA scan. Provide skill in setup, cleaning, assembly and test components by Helium Leak Detection.
|  | Mechanical Assembly Technician | Accel Component Fabrication | Build, assemble, and test precision accelerator beam components i.e. Pulsed magnets, Lithium Collection Lens and Transformer set, Magnetic Focusing Horns.
|  |  | Detector Component Fabrication | Build, assemble, and test precision components including silicon and pixel detector mechanical systems and other intricate detector systems
|  |  | Mechanical Assembly - delicate | Fabricate and assemble delicate mechanical devices using hand tools and dedicated tooling. Follows, helps develop, and documents procedures.
|  |  | Mechanical Assembly - heavy | Fabricate and assemble big mechanical devices using hand or power tools and dedicated tooling. Follows, helps develop, and documents procedures.
|  | Mechanical Instrument Technician | Instrumentation/Controls | Skilled at mounting instrumentation, installing controls and measuring magnets, RF cavities, and other devices using custom equipment.
|  | Mechanical SRF Technician | Clean Room Assembly | Trained and experienced in working in a clean room environment, including operation of Leak Detection and Residual Gas Analysis equipment. Provide skill in selection of material, cleaning, packaging, vacuum degassing, and leak detection. Able to work in a class 100 or better clean room environment
|  |  | RF Processing / Testing | Provide skill in the transport, RF measurement, ultra sonic cleaning, acid etching, rinsing, ability to work in Particle Free Ultra High Vacuum environment, vertical and horizontal testing. Skilled at handling chemicals in a safe manner.
|  | Mechanical Systems Technician | Material Handling | Move material safely and efficiently. Operation cranes and forklifts. Handle highly controlled manual or remote manipulation and/or repair of radioactive components and systems. Assemble parts kits and take inventory
|  |  | Water/piping systems | Repair, maintain and install a variety of water/gas systems, associated piping and controls. Includes maintenance of D.I systems and regeneration of resin
|  | Mechanical Task Manager | Mech Task Management | Provide oversight and knowledge for mobile crane setup, piping and mechanical installation contracts
|  | Mechanical Technician Supervisor | Crew Leader | Lead a repair or installation team providing the necessary technical guidance.
|  |  | Supervisor | Supervise a group of mechanical technicians
| Operations | Accelerator Operator | Accelerator Operations | Operate the accelerator on a 24x7 basis
|  | Accelerator Systems Specialist | Operations and Maintenance | Provide engineering operations and maintenance support for major accelerator or experimental systems.
|  | Operations Manager | Supervisor | Responsible for staffing, training, and hiring of operations staff. Oversees safe operation of the complex and is the line manager for operators and/or operations specialists. Provides statistics on operations of the complex as required.
|  | Operations Specialist | Accelerator and Systems Operations | Responsible for the operation of accelerators or major systems. Has in depth knowledge of the accelerator or system and is regarded as the operations expert. If help is needed in solving technical problems with the accelerator or system, the operations
| Other Technical | Construction Manager | Construction Management | Provide oversight and knowledge of construction contracts
|  | Fabrication Specialist | Fabrication | Prepare requisitions, identify possible vendors and work with Fermilab Procurement Dept. to complete the procurement process. Serves as point of contact for vendors. Monitors progress of contracts and reports on status. Makes vendor QC inspections and is the person responsible for assuring the fabrication process is completed properly.
|  | Machinist | Machining | Provide on site machining of parts and repairs to existing components
|  | QC Technical | QC Process Control | Inspect devices during fabrication and upon delivery from vendors for conformance to tolerances, including visual, dimensional, electrical, hydro, and vacuum using standard and custom equipment, and document results.
|  | Quality Assurance | QA Process Control | Assures quality processes are in place and are being adhered to.
|  | Welder | Welding | Provide on site welding of assemblies and piping systems