## FY09 FNAL Actuals
2009-07-01
|  | 40.44.80.01 | 40.44.80.02 | 40.44.80.03 | 40.44.80.04 | 20.12.16.12 | 29.100.10.43
|  | LBNE Det.R&D | LBNE Det. Sci. | LBNE Beam R&D | LBNE Beam Sci. | DUSEL Beam - Pre-CD0 | Pre-CD0 DUSEL BL
|  | KA 11 02 034 | KA 11 01 02 | KA 11 02 034 | KA 11 02 034 | KA 11 02 034 | KA 11 02 034
Totals
Budget | 2770.3 | 917.5 | 321 | 732.5 | 85 | 714.3
M&S Obligatons | 370.804 | 60.66 | 25.98 | 177.58 | 59.134 | 47.45
SWF | 447.26 | 14.8 | 224.7 |  |  | 202.25 | 5.51
M&S Costs | 159.68 | 59.6 | 25.98 | 60.58 |  | 13.52
Indirect | 398.64 | 24.9 | 140.19 | 9.71 | 36.17 | 182.7 | 4.97
Total Costs | 1005.58 | 99.3 | 390.87 | 70.29 | 36.17 | 398.47 | 10.48
Total Obligations | 1216.704 | 100.36 | 390.87 | 187.29 | 95.304 | 432.4 | 10.48

## 1.0 - Summary
NO DATA SHOULD BE ENTERED ON THIS SHEET!!
Plan from now to CD-1
WBS | Task name |  | Labor (FTE)
|  | Sum non-Sci | Technical |  |  | Administrative |  |  | Scientists |  |  | RA/Post-doc |  |  | Sum Sci
|  |  | W | A | N | W | A | N | W | A | N | W | A | N
1 | LBNE
SWF
1.1 | Project Management | 9 | 0.9 | 0.5 | 3 | 0.5 | 2.1 | 2 | 3.3 | 2.25 | 0 | 0 | 0 | 0 | 5.55
1.2 | Neutrino Beam | 4.05 | 0.5 | 1.05 | 2.5 | 0 | 0 | 0 | 1.55 | 0.95 | 1 | 0 | 0 | 0.5 | 4
1.3+1.1.3 | ND - LANL |  | 0 | 1 | 0 | 0 | 0.1 | 0 | 0.45 | 3.5 | 0 | 0 | 3 | 0 | 6.95
1.3 | ND - Universities
1.4+1.1.4 | WC - Labs | 16.2 | 0 | 10.5 | 4.5 | 0 | 0.2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | WC - Universities
1.5 | LAr Labs | 5.9 | 5.9 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | LAr - Univiersities | 2 | 1.3 | 0 | 0.7 |  |  |  | 2.4 | 4.5 | 0 | 1 | 0 | 1.7 | 9.6
| FTE Labs | 36.25 | 7.3 | 13.05 | 10 | 0.5 | 2.4 | 3 | 5.3 | 6.7 | 1 | 0 | 3 | 0.5 | 16.5
| FTE Universities | 2 | 1.3 | 0 | 0.7 | 0 | 0 | 0 | 2.4 | 4.5 | 0 | 1 | 0 | 1.7 | 9.6
| FTE Totals | 38.25 | 8.6 | 13.05 | 10.7 | 0.5 | 2.4 | 3 | 7.7 | 11.2 | 1 | 1 | 3 | 2.2 | 26.1
| fraction of year | 1
| $(K) - Laboratories | 10875 | 2190 | 3915 | 3000 | 150 | 720 | 900 | 1590 | 2010 | 300 | 0 | 450 | 75 | 4425
| $(K) - Universities | 600 | 390 | 0 | 210 | 0 | 0 | 0 | 720 | 1350 | 0 | 300 | 0 | 510 | 2880
| $(K) - Total | 11475 | 2580 | 3915 | 3210 | 150 | 720 | 900 | 2310 | 3360 | 300 | 300 | 450 | 585 | 7305
M&S |  | Travel | Project Office Support | Contract Engineering | Contract Services | Materials Procurement | Other | Total M&S
1.1 | Project Management | 85 | 60 | 150 | 200 | 0 | 0 | 495
1.2 | Neutrino Beam | 50 | 0 | 1300 | 700 | 15 | 0 | 2065
1.3+1.3.1 | Near Detector | 100 | 0 | 0 | 0 | 0 | 0 | 100
1.4+1.4.1 | WC | 63 | 0 | 1403 | 0 | 50 | 0 | 1516
1.5 | Lar | 50 | 0 | 1324 | 0 | 1070 | 0 | 2444
| Total M&S | 348 | 60 | 4177 | 900 | 1135 | 0 | 6620
| Total $(K) for SWF | 15900
| Total $(K) for M&S | 6620
| Total $(K) | 22520
| Total $(K) for University Scientisits on Base | 2880
This budget calculation is not correct - Do not use...

## 1.1
CD0 - CD1
WBS | Task name |  |  |  | Labor (FTE)
|  | Total | non-Sci | Sci | Technical |  |  | Administrative |  |  | Scientists |  |  | RA/Post-doc
[5 empty] | W | A | N | W | A | N | W | A | N | W | A | N
1.1 | Project Management
SWF
1.1.1 | Project Coordination | 7.15 | 4.4 | 2.75 | 0.4 |  | 1 | 0.5 | 1.5 | 1 | 1 | 1.75
1.1.2 | Neutrino Beam | 3.4 | 2.4 | 1 | 0.4 | 0.5 | 1 |  | 0.5 |  | 1
1.1.4 | Water Cerenkov Detector | 3 | 2 | 1 |  |  | 1 |  |  | 1 | 0.5 | 0.5
1.1.5 | Liquid Argon Detector | 1 | 0.2 | 0.8 | 0.1 |  |  |  | 0.1 |  | 0.8
| FNAL FTE Totals | 14.55 | 9 | 5.55 | 0.9 | 0.5 | 3 | 0.5 | 2.1 | 2 | 3.3 | 2.25 | 0
| SWF ($K) | 3905 | 2240 | 1665 | 270 | 150 | 900 | 100 | 420 | 400 | 990 | 675 | 0
M&S |  | Sum | Travel | Project Office Support | Contract Engineering | Contract Services | Materials Procurement | Other
1.1.1 | Project Coordination |  | 40 | 60 |  | 200
1.1.2 | Neutrino Beam |  | 25
1.1.5 | Liquid Argon Detector |  | 20 |  | 150
| Sum ($K) | 495 | 85 | 60 | 150 | 200 | 0 | 0
Note on F7: Regina Rameika: Integration - Laughton
Note on L7: Regina Rameika: Rameika
Note on M7: Regina Rameika: new PM, FNAL scientists to help with documentation
Note on H8: Regina Rameika: Project Engineer
Note on L8: Regina Rameika: Papadimitriou + Lundberg
Note on F10: Regina Rameika: Rich Schmitt
Note on L10: Regina Rameika: Baller
Note on G33: Regina Rameika: Independent cavern design and cost estimates - managed by Laughton
Note on I7: Regina Rameika: Admin, DO Budget, DO schedule
Note on F8: Regina Rameika: Laughton - civil coordination
Note on J10: Regina Rameika: Budget, project controls
Note on E33: Regina Rameika: offices, furniture,computers,supplies
Note on J8: Regina Rameika: AD budget and schedule support
Note on G8: Regina Rameika: ES&H coordination
Note on H7: Regina Rameika: Project Engineer or Manager
Note on F35: Regina Rameika: half of a contract engineer
Note on J7: Regina Rameika: additional half admin Project controls and budget person half time each
Note on K7: Regina Rameika: Add more support in 2nd half of year for CD-1 preparation
Note on L9: Regina Rameika: P. Mantsch - PM for PMTs
Note on M9: Regina Rameika: Deputy PM for PMTs
Note on H9: Regina Rameika: Project Engineer for PMTs
Note on K9: Regina Rameika: Project Controls Specialist for PMTs

## 1.2
CD0 - CD1
WBS | Task name |  | Labor (FTE)
|  | Total | non-Sci | Sci | Technical |  |  | Administrative |  |  | Scientists |  |  | RA/Post-doc
[5 empty] | W | A | N | W | A | N | W | A | N | W | A | N
1.2 | Neutrino Beam
SWF
1.2.1 | Primary Beam | 2.4 | 1.1 | 1.3 | 0.4 | 0.7 |  |  |  |  | 0.75 | 0.3 |  |  |  | 0.25
1.2.2 | Target Hall Devices | 4.85 | 2.7 | 2.15 | 0.1 | 0.1 | 2.5 |  |  |  | 0.4 | 0.5 | 1 |  |  | 0.25
1.2.3 | Integration | 0.45 | 0.25 | 0.2 |  | 0.25 |  |  |  |  | 0.05 | 0.15
1.2.4 | Civil Construction | 0.35 | 0 | 0.35 | 0 | [5 empty] | 0.35
| 1.2 FTE Totals | 8.05 | 4.05 | 4 | 0.5 | 1.05 | 2.5 |  |  |  | 1.55 | 0.95 | 1 |  |  | 0.5
| 1.2 SWF ($K) | 2340 | 1215 | 1125 | 150 | 315 | 750 |  |  |  | 465 | 285 | 300 | 0 | 0 | 75
M&S |  | Sum | Travel | Project Office Support | FESS Engineering | Contract Engineering | Contract Services | Materials Procurement | Other
1.2 | General |  | 50
1.2.1 | Primary Beam
1.2.2 | Neutrino Beam |  |  |  |  | 200 | 300 | 15
1.2.3 | Systems and Integration |  |  |  |  | 100
1.2.4 | Civil Construction |  |  |  | 500 | 1000 | 400
| 1.2 M&S($K) | 2565 | 50 | 0 | 500 | 1300 | 700 | 15 | 0
Note on L9: Regina Rameika: Hylen - 0.3 Martens - 0.1
Note on G30: Regina Rameika: Contract engineering for High Power target, Target Material testing
Note on H32: Regina Rameika: Site Investigation
Note on G32: Regina Rameika: A&E for PDR and CDR, Underground consultants for value engineering and cost estimating
Note on G31: Regina Rameika: Contract engineer
Note on H30: Regina Rameika: NuMI Target autopsey
Note on L8: Regina Rameika: Childress - .25 Lucas - .5
Note on M8: Regina Rameika: G. Velev or TD equivalent
Note on Q8: Regina Rameika: new RA to work with Bob Zwaska
Note on Q9: Regina Rameika: New RA to work on Beam Fluxes for MC studies
Note on L10: Regina Rameika: person like Bob Zwaska
Note on L11: Regina Rameika: Childress
Note on M9: Regina Rameika: Redirected Scientific Effort to assist in cost and schedule prep - person like Baller or Grossmann
Note on N9: Regina Rameika: New AS assignment ES&H Rad Safety Physicist
Note on F8: Regina Rameika: Koizumi
Note on G8: Regina Rameika: Engineering, Designing, Estimating from TD for new magnets (.4); AD Power Supplies, systems (.3)
Note on G9: Regina Rameika: 0.1 addional of P.Hurh;
Note on H9: Regina Rameika: AD New Hires if not available from existing staff - ME to become part of project team to be ready for next phase of design; at least 1.0 on target; rest on other
Note on G10: Regina Rameika: AD Engineering Support for System Leader
Note on F11: Regina Rameika: FESS effort in M&S
Note on I30: Regina Rameika: Computers and software for beam modeling
Note on F9: Regina Rameika: P. Hurh

## 1.3
CD0 - CD1
WBS | Task name |  | Labor (FTE)
|  | non-Sci | Technical |  |  | Administrative |  |  | Scientists |  |  | RA/Post-doc |  |  | Sci
|  |  | W | A | N | W | A | N | W | A | N | W | A | N
1.3 | Near Detector
SWF
1.1.3 | Project Management | [5 empty] | 0.1 |  | 0.2 | 1
1.3.1 | Strategy and Integration | [13 empty] | 0
1.3.2 | Hadron Beam Detectors | [7 empty] | 0.05 | 0.5 |  |  | 0.5 |  | 1.05
1.3.3 | Muon Detectors | [7 empty] | 0.05 | 0.5 |  |  | 0.5 |  | 1.05
1.3.4 | Neutrino Detectors |  |  | 0.75 |  |  |  |  | 0.05 | 1 |  |  | 2 |  | 3.8
1.3.5 | Civil Integration |  |  | 0.25 |  |  |  |  | 0.1 | 0.5 |  |  |  |  | 0.85
| FTE Totals | 1.1 | 0 | 1 | 0 | 0 | 0.1 | 0 | 0.45 | 3.5 | 0 | 0 | 3 | 0 | 6.75
M&S |  |  | Travel | Project Coordination | Technical Engineering | RA for Conceptual Design | Materials Procurement | Other
1.1.3 | Project Management |  | 100
1.3.1 | Strategy and Integration
1.3.2 | Hadron Beam Detectors
1.3.3 | Muon Detectors
1.3.4 | Neutrino Detectors
1.3.5 | Civil Integration
| Sum |  | 100 | 0 | 0 | 0 | 0 | 0

## 1.4
CD0 to CD1
WBS | Task name |  | Labor (FTE)
|  | non-Sci | Technical |  |  | Administrative |  |  | Scientists |  |  | RA/Post-doc |  |  | Total Sci
|  |  | W | A | N | W | A | N | W | A | N | W | A | N
1.4 | Water Cerenkov
SWF
1.1.4 | Project Management | 4 |  | 1.8 | 1 |  | 0.2 | 1
1.4.1 | Water Containment | 4.55 |  | 4.05 | 0.5 |  |  |  | 0.7 | [5 empty] | 0.7
1.4.2 | Photon Detectors | 0.85 |  | 0.85 |  |  |  |  | 0.8 | [5 empty] | 0.8
1.4.3 | Electronics/Readout | 1 |  | 1 |  |  |  |  | 0.2 |  |  | 0.5 |  |  | 0.7
1.4.4 | Calibration | 0 | [6 empty] | 0.2 | [5 empty] | 0.2
1.4.5 | Water System | 2.1 |  | 1.1 | 1 |  |  |  | 0.8 | [5 empty] | 0.8
1.4.6 | Civil Integration | 1 |  | 0.5 | 0.5 |  |  |  | 0.14 | [5 empty] | 0.14
1.4.7 | Software and Simulation | 0.5 |  | 0.5 |  |  |  |  | 1.25 |  |  | 1 |  | 1 | 3.25
1.4.8 | Installation | 2.2 |  | 0.7 | 1.5 | [9 empty] | 0
| FTE Totals | 16.2 | 0 | 10.5 | 4.5 | 0 | 0.2 | 1 | 4.09 | 0 | 0 | 1.5 | 0 | 1 | 6.59
M&S |  |  | Travel | Project Office Support | Contract Engineering | Contract Services | Materials Procurement | Other | Sum
1.1.4 | Project Management |  | 101 |  |  |  | 179 |  | 280
1.4.1 | Water Containment |  | 63 |  | 761 |  |  |  | 824
1.4.2 | Photon Detectors |  |  |  | 398 |  | 50 |  | 448
1.4.3 | Electronics/Readout
1.4.4 | Calibration
1.4.5 | Water System |  |  |  | 143 |  |  |  | 143
1.4.6 | Civil Integration |  |  |  | 101 |  |  |  | 101
1.4.7 | Software and Simulation | [5 empty] | 60
1.4.8 | Installation |  |  |  | 101 |  |  |  | 101
| Sum |  | 63 | 0 | 1403 | 0 | 50 | 0 | 1516
Note on F21: Regina Rameika: Indpendent consultants for cavern/liner
Note on H20: Regina Rameika: Computers,software,liscences,video
Note on F22: Regina Rameika: FEA Modeling, pressure testing
Note on H22: Regina Rameika: purchase PMTs
Note on F25: Regina Rameika: Consult at UCI
Note on F26: Regina Rameika: mining engineer (double counted)
Note on F28: Regina Rameika: same consultant as for integration

## 1.5 - new
|  | FY10 | [10 empty] | FY11
WBS | Task name |  | Labor (FTE)
|  | Total | non-Sci | Sci | Technical |  | Administrative |  | Scientists |  | Post-docs |  | Technical
[5 empty] | A | N | A | N | A | N | A | N | A
1.5 | LAr Detector
Labor
FNAL
1.5.1 | Project Management
1.5.2 | Cryogenics System |  |  |  | 0.5 | [7 empty] | 1
1.5.3 | Cryostat |  |  |  | 1 | [7 empty] | 2
1.5.4 | TPC |  |  |  | 0.5 | [7 empty] | 2
1.5.4 | Readout and DAQ
1.5.5 | Cavern and Infrastructure
1.5.7 | Installation |  |  |  | 0.5 | [7 empty] | 1
1.5.8 | Photon Detectors
| 1.5 FNAL FTE Totals | 0 | 0 | 0 | 2.5 | 0 | 0 |  | 0 | 0 |  | 0 | 6
| 1.5 FNAL SWF ($K) |  |  |  | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800
Labor
non-FNAL (M&S)
1.5.1 | Project Management
1.5.2 | Cryogenics System
1.5.3 | Cryostat
1.5.4 | TPC
1.5.4 | Readout and DAQ
1.5.5 | Cavern and Infrastructure
1.5.7 | Installation
1.5.8 | Photon Detectors
| 1.5 non-FNAL FTE Totals | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
| 1.5 non-FNAL Labor ($K) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M&S |  | Sum | Travel | Project Office Support | FESS Engineering | Contract Engineering | Contract Services | Materials Procurement | Other
1.5
1.5.1 | Project Management |  | 50
1.5.2 | Cryogenics System |  |  |  |  | 90
1.5.3 | Cryostat |  |  |  |  | 90
1.5.4 | TPC
1.5.4 | Readout and DAQ
1.5.5 | Cavern and Infrastructure |  |  |  |  | 200
1.5.7 | Installation |  |  |  |  | 90
1.5.8 | Photon Detectors
| 1.5 M&S($K) | 520 | 50 | 0 | 0 | 470 | 0 | 0 | 0
Note on F14: Bruce Baller: Kilmer - installation planning + designer support
Note on F9: Bruce Baller: Schmitt - monitor engineering consultants
Note on F10: Bruce Baller: Schmitt,Tope - cryostat, LAPD & ArgoNeut support, ODH analysis + designer support
Note on G43: Bruce Baller: MSD contract eng or engineering conultants
Note on F11: Bruce Baller: ASIC eng + support tech Cold Electronics
Note on N9: Bruce Baller: Start final design using outside services (eg Air Liquide). FNAL eng writes specs, monitors contracts
Note on N10: Bruce Baller: Final design: 1 eng, 0.2 designer 1kt prototype design: 0.5 eng, 0.2 designer
Note on N11: Bruce Baller: Cold electronics: 1 ASIC eng + tech Feedthrough?: 0.5 cryo eng, designer
Note on N14: Bruce Baller: Installation planning 1kt prototype planning
This sheet is not yet complete due to re-working the WBS

## 1.5 - old
FY09 + FY10
WBS | Task name |  | Labor (FTE)
|  |  | Technical-Lab |  |  | Technical-University |  |  | Scientists |  |  | RA/Post-doc |  |  | Sci
|  | non-Sci | W | A | N | W | A | N | W | A | N | W | A | N
1.5 | Liquid Argon
SWF
1.5.1 | Related R&D | 0.6 | 0.6 | [5 empty] | 0.3 | 0.3 |  |  |  |  | 0.6
1.5.2 | Detector | 2.6 | 2.6 | 0 |  | 0.5 |  | 0.7 | 1.9 | 2.2 |  | 1 |  |  | 5.1
1.5.3 | Cryogenics | 0.2 | 0.2 | 0 |  | 0.1 |  |  | 0.2 | 0.5 |  |  |  |  | 0.7
1.5.4 | Electronics & DAQ | 1.9 | 1.9 | 0 |  | 0.7 |  |  |  | 1.3 |  |  |  | 1.7 | 3
1.5.5 | Installation & Commissioning | 0.6 | 0.6 | 0 | [5 empty] | 0.2 |  |  |  |  | 0.2
| FTE Totals | 5.9 | 5.9 | 0 | 0 | 1.3 | 0 | 0.7 | 2.4 | 4.5 | 0 | 1 | 0 | 1.7 | 9.6
M&S |  |  | Travel | Project Office Support | Contract Engineering | Contract Services | Materials Procurement | Other | Sum
1.5.1 | Related R&D |  | 10 |  |  |  | 345
1.5.2 | Detector |  | 10 |  | 518 |  | 123
1.5.3 | Cryogenics |  | 10 |  | 518
1.5.4 | Electronics & DAQ |  | 10 |  |  |  | 602
1.5.5 | Installation & Commissioning |  | 10 |  | 288
| Sum |  | 50 |  | 1324 | 0 | 1070 | 0 | 2394
Note on H17: Regina Rameika: long drift at IU - part 2 complete LAPD at FNAL
Note on H18: Bruce Baller: $40k software (maybe contract Eng?) + UCLA Hex module prototype
Note on H20: Bruce Baller: Include $70k from FY11 for cold ASIC test. The rest is for subcircuit tests w various IC processes
Note on F21: Bruce Baller: Chris Laughton Task 2 and 3

## Rates
| ANL | BNL | FNAL | LANL | LBNL | LLNL
Technical
Engineer |  | 325
Designer |  | 180
Safety Pro |  | 295
Technician |  | 210
Administrative
Budget |  | 235
Schedule
Controls
Clerical
Scientist
Low
Med |  | 280
High
RA/post-doc |  | 120
adjusted for rest of FY09
Generic
Technical | 300
Administrative | 200
Scientist | 300
RA/PD | 150

## FY09 Effort
| Name | Type | YTD | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
1.1.1 | Rameika, R. | Scientist | 1550.7 |  | 144 | 168 | 144 | 132 | 176 | 208 | 160 | 176 | 176 | 66.7
1.1.1 | Name: Wright, S.; YTD: 10.9; Aug: 10.9
1.1.2 | Name: Papadimitriou, V; Type: Scientist; YTD: 8; Aug: 8
1.1.5 | Name: Baller, B.; Type: Scientist; YTD: 30; Aug: 30
1.2.1 | Lucas, P. | Ap. Scientist | 919 |  |  | 109.4 | 87.4 | 57.2 | 147.8 | 135.9 | 60.8 | 79.2 | 110.1 | 131.2
1.2.1 | Koizumi, G. | Eng. Physicist | 373.9 |  |  | 88.2 | 43.2 | 32 | 35.2 | 36.1 | 32.6 | 37 | 35.2 | 34.4
1.2.1 & 1.2.4 | Childress, S. | Scientist | 481.5 |  |  | 56.2 | 42.2 | 39.7 | 33.8 | 42.2 | 64 | 58.4 | 67.7 | 77.3
1.2.2 | Hurh, P. | Engineer | 173.1 | [5 empty] | 45.8 | 18.2 | 32.6 | 27.4 | 20.3 | 28.8
1.2.2 | Name: Hurd, D.; Type: Designer; YTD: 92; May: 75; Jun: 17
1.2.2 | Hylen, J. | Scientist | 545.9 |  |  | 102.8 | 26.6 | 62.3 | 89.6 | 67.2 | 50.4 | 34.4 | 63.9 | 48.7
1.2 | Name: Lundberg, B.; Type: Scientist; YTD: 366.7; Feb: 48; Mar: 70.4; May: 96; Jun: 73.9; Aug: 78.4
1.2.2 | Name: Martens, M.; Type: Scientist; YTD: 92.3; Dec: 44.9; Feb: 25.8; Aug: 21.6
1.2 | Zwaska, B. | Scientist | 93.8 |  |  | 25.9 | 4.1 | 10.4 | 15.8 | 16 | 8 | 3.4 | 8.6 | 1.6
1.2.4 | Hammond, L. | FESS Engineer | 98.4 |  |  |  |  | 2 | 3 | 0 | 25.4 | 30 | 28 | 10
1.2.4 | Lackowski, T. | FESS Engineer | 183.1 |  |  | 9 | 20 | 22.9 | 8.3 | 29 | 22 | 32.9 | 21.1 | 17.9
1.2.4 | Name: Federowicz, C.; Type: FESS Engineer; YTD: 39; Jul: 7; Aug: 32
1.2.4 | Name: Vanzandbergen, G; Type: FESS Engineer; YTD: 5; May: 1; Jun: 2; Jul: 2
1.2.4 | Name: Wyman, T.; Type: FESS Engineer; YTD: 14.8; Aug: 14.8
1.2.4 | Name: Laughton, C.; Type: Ap. Scientist; YTD: 232; May: 64; Jun: 88; Aug: 80
1.4 & 1.5 | Laughton, C. | Ap. Scientist | 812 | 90 | 149.6 | 108.8 | 68 | 70 | 88 | 68 | 64 |  | 105.6
1.4.1 & 1.4.3 | Name: Allspach, D.; Type: Engineer; YTD: 71.1; Mar: 8; Apr: 16; May: 14.4; Jun: 16; Jul: 16.7
1.5 | Name: Schmitt, R.; Type: Engineer; YTD: 46.5; Jun: 10.4; Jul: 25.9; Aug: 10.2
? | Name: Krempetz, K.; Type: Engineer; YTD: 91.6; Apr: 16; May: 30; Jun: 13.2; Jul: 26.4; Aug: 6
|  |  |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
|  |  |  | 90 | 293.6 | 713.2 | 435.5 | 502.3 | 721.7 | 652.6 | 800.2 | 699.2 | 714.5 | 708.5